KPI Q3-021
QUALITY, SAFETY & PROFESSIONALISM
SPONSOR / Sr. Ida Zuraida binti Mohd Yusoff
OWNER / Ar. Sharina Intan binti Abdullah
OIC / Noriman bin Muhammad
KPI LEADER / JKT (KPKT)
KPI DESCRIPTION / e-submission and e-approval rolled-out across at least 20 Local Authorities (LAs) by Q4 2020
INITIATIVE / Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE / Q3b - Strengthen One-Stop Centre for all construction permits/approvals
ANNUAL TARGET
2016 / Weightage : 5%	2017 / Weightage : 5%	2018 / Weightage : 15%	2019 / Weightage : 35%	2020 / Weightage : 40%
Activities/ work breakdown and leaders for each activities identified. / 6 Local Authorities identified as the 1st batch to pilot e-submission and e-approval.	Procedure for appointment of consultant to conduct study on existing OSC Online System finalised / Consultant to conduct study on existing OSC Online System appointed	Final report on existing OSC Online System completed / JKT conduct study to implement existing OSC Online system by PBT and Technical agency / Procedure for appointment of consultant to develop new OSC Online System. New OSC 3 Plus online system. 2 Local Authorities (LAs) to be pioneer: i. MPSJ / ii.MPKj / Pilot project report is used as a reference to improve new OSC online 3 Plus system	Budget to develop/ enhance new OSC Online System applied under RMKe-11 / OSC online piloted and finalised for 10 Local Authorities (LAs)	OSC 3.0 online launched at national level / OSC 3.0 online implemented by 20 Local Authorities (LAs)
PROGRESS REPORT UNTIL Q3 2018
This KPI is under the purview of IWG4.
e-submission and e-approval
e-submission and e-approval form part of an integrated Construction Permit Management System designed to strengthen the delivery processes for the approval of Construction Permits. In line with the Eleventh Malaysia Plan (RMKe-11) that emphasizes on wider adoption of ICT, the new system will be based on open-source, fully integrated with existing systems, utilise cloud computing and customer-centric transaction processing. This initiative is expected to provide substantial cost saving and at the same time ensure higher productivity. This new application system has been designed to complement the existing 6 processes as follows:-
Pre-Construction
Process 1 - Data gathering (not mandatory)
Process 2 - Approval
Process 3 - Notification to start work
Construction
Process 4 - Interim inspection
Post-Construction
Process 5 - Final inspection
Process 6 - Building certification (CCC)
World Bank Ranking
Dealing with Construction Permit (DCP) is one of the ratings used by the World Bank in determining the ranking for Ease of Doing Business among 190 countries. Malaysia’s rank for Dealing with Construction Permit from year 2015 to 2017 is shown as below:
** DTF : Distance To Frontier ATL : External Technical Agencies
    PSP : Principal Submitting Person OSC: One Stop Centre
Local Authorities identified to pilot e-submission
In 2016, 6 Local Authorities have been identified for the study on their respective requirement, process flows and issue identification and verification. These 6 are among the first batch of Local Authorities and the outcome of the study will be used to pilot the e-submission and e-approval. The six Local Authorities are:
Majlis Bandaraya Ipoh 4) Majlis Bandaraya K. Terengganu
Majlis Bandaraya Pulau Pinang 5) Majlis Perbandaran Kota Bahru
3) Majlis Bandaraya Johor Bahru 6) Majlis Bandaraya Shah Alam
Study on existing OSC Online system
The existing OSC online is an online system used by relevant stakeholders (PBT, PSP, ATL) to process the application for Development Approval. This system involves the use of 2 main modules which are e-submission and e-processing for Process 1 and Process 2 only.
JKT has decided for the appointment of consultant to be re-tendered proposed following the conditional approval by CIDB for the consultant’s project team to be replaced.
The findings of the study will be utilised to strengthen the budget request under Rolling Plan 4.
Pre-council meeting (KPI Leaders)
19 March 2018
19 march 2018 – online servey on implement existing OSC Online system by PBT and Technical agency
ICT Unit to liaise with MAMPU to name 3 new consultants/companies.
Proposed 3 consultants submitted to CIDB : 14 Mei 2018.
Letter on status appointment of consultant submitted to CIDB : 6 June
2018.
New OSC 3 Plus online Meeting for (Procurement process & scope of works) : 16 August 2018 & 20 Sept 2018
Year	DTF score	Ranking
2015	81.14	28/189
2016	81.08	13 /189
2017	82.17	13/190
2018	82.19	11/190

---
KPI Q3-022
OWNER / Ar. Sharina Intan Abdullah
KPI LEADER / MPC/ JKT (KPKT)
KPI DESCRIPTION / Average number of construction permit approval procedures nationwide reduced to 13 and number of days reduced to 74 for small scale development projects (i.e., same as Kuala Lumpur) by Q4 2020
INITIATIVE / Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE / Q3b - Strengthen One-Stop Centre for all construction permits/approvals
2016 / Weightage : 10%	2017 / Weightage : 15%	2018 / Weightage : 25%	2019 / Weightage : 30%	2020 / Weightage : 20%
Activities/ work breakdown and leaders for each activities identified. / 6 Local Authorities identified in the 1st batch to pilot e-submission and e-approval.	Standard procedures on permit approval for small scale development for 5 Local Authorities established / Locality / DBKK : 70% / MBJB : 50% / MBI : 50% / MBPP : 15% / MPSP : 50%	Standard procedures on permit approval for small scale development for 5 / Local Authorities established / Locality / DBKK : 100% / MBJB : 100 % / MBI : 100 % / MBPP : 100 % / MPSP : 100 %	Standard procedures on permit approval for small scale development for 5 / Local Authorities established / State / Selangor : 100% / N.Sembilan : 100 % / Kedah : 100 % / Sarawak : 100 % / Kelantan : 100 %	Standard procedures on permit approval for small scale development for 4 Local Authorities established / State / Melaka : 100% / Pahang : 100 % / Perlis : 100 % / Terengganu : 100 % / Standard procedures on permit approval for small scale development rolled out nationwide
pilot project
6 regions/states/ PBTs (Perak, Penang, Johor, Kelantan & Selangor) have been identified in the 1st batch to pilot enhancement to the construction permit approval procedures in 2016. Majlis Bandaraya Ipoh had been engaged on 22 Dec 2016.
Standard procedures on permit approval for small scale development
Currently the average number of procedures nationwide is 55 and the average number of days required to process approvals for construction permit is 106. The study on Standard Procedures for Permit Approval for Small Scale Development has commenced since 2016 with the following progress:-
Pertubuhan Arkitek Malaysia (PAM) was appointed, on 18 Dec 2017 to continue with the study for a period of 6 months beginning 2 Jan 2018, with the interim budget allocated by CIDB. The findings of the study will be utilised to strengthen the budget request under Rolling Plan 4.
Memorandum of Agreement (MoA) signed on 29 Jan 2018 and grant RM1Mn disbursed on 2 Mar 2018.
List of Local Authorities engaged
Comittment Stage
Mapping Stage
Streamline Stage
MPSP and MBJB are under process in producing the manual for procedure on permit approval.
Kick-off for the signing of MOA to PAM : 29 January 2018.
Grant allocation to PAM : 2 March 2018.
Workshop on SOP MBI : 12 Apr to 13 Apr 2018.
Renewed engagement with MBPP : 23 Apr 2018.
Proposed Workshop for SOP MSPS : 16 July to 17 July 2018.
Pilot Stage
DBKK : 28 July 2018
Locality	Date
MBJB	4 Jan 2017
MBPP	20 Jan & 17 Oct 2017
Locality	Date
MPSP	20 Jan 2017
DBKK	6 Feb 2017
Locality	Date
MBPP	18 Apr 2018
MBI	4 Jan 2018
Locality	Date
MBJB	12 Jan 2017
DBKK	21 Feb 2017
Locality	Date
DBKK	14-15 Nov 17
MPSP	11 Sep 17
DBKK	18 Aug 17
MBI	12-13 Apr 18
MBJB	26-27 Sept 18
Locality	Date
DBKK	11-12 May 17
DBKK	25 May 17
MBJB	20-21 Nov 17
MPSP	29-30 Nov 17
MBI	27-28 Feb 17
Locality	Target 2018	Progress Q2 2018
DBKK	100%	86%
MBJB	100%	71%
MBI	100%	71%
MBPP	100%	33%
MPSP	100%	83%
MBSA	100%	0%

---
KPI Q3-023
KPI DESCRIPTION / 100% of disputes applications resolved by the Dispute Resolution Mechanism (DRM) within 6 month of receipt starting in Q4 2020
INITIATIVE / Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE / Q3c - Set up tribunal for construction permit dispute resolution
2016 / Weightage : 10%	2017 / Weightage : 10%	2018 / Weightage : 40%	2019	2020
			Weightage : 40%
Activities/ work breakdown and leaders for each activities identified. / Task force for disputes applications resolution established / Problems Identifiaction Dialog with Locality Authority, / Agencies, PEMUDAH & / FGDCP conducted / Directions to proceed establishment of DRM / obtained	Selected existing mechanism / to resolve dispute application mapped / Scope, TOR, authority, / mechanism, membership, / funding, jurisdiction and framework for DRM finalized / Established gaps in the existing Appeal Board mechanism which justifies for the need of a Construction Dispute Tribunal. / Comparison of foreign mechanism for technical construction dispute and administrative dispute resolution. / Draft of Technical Construction Dispute Settlement & development of questionnaires: Technical agencies and operators.	Completion of findings of focus group discussions (technical agencies) & partial focus group for operators &partial/progress findings on impact assessment. / Final analysis of the feedback from the stakeholders. / Conclusion of Impact assessment / Conclusion of level of acceptance of stakeholders / Final suggested Framework for Technical Construction Dispute Settlement.	Consultation with other states in Peninsular Malaysia. (by zones) / Upgrade the framework / Identify suitable real case study. / Conduct pilot study for the indentified project. / Open consultation will all construction industry stakeholders (professional boards and institutions, developers)	Suggestions of required amendments to the law. / Get the necessary clearance for the establishment of the dispute mechanism. / Road show and awareness programme. / Announcement to the public
Dispute Resolution Mechanism (DRM)
Dispute Resolution Mechanism (DRM) is an instrument established to resolve any technical disagreement or dispute arising from the construction permit approval processes. The mechanism is jointly formulated by a working group consisting of MPC, JKT and stakeholders in construction industry (Professional bodies and other industry players). The DRM will be handling disputes not currently covered under the existing Appeal Boards, that has been created under Town and Country Planning Act 1976 (Act 172) (TCPA). The framework for DRM will be formulated based on the best pratices of a number of Tribunals and Appeal Boards from the Commonwealth Countries.
Study on ‘Cadangan Penubuhan Tribunal untuk Pertikaian Permit Pembinaan di bawah Inisiatif Q3c CITP’
UiTM has been appointed to study and prepare a report on the establishment of a tribunal to resolve construction permit disputes on 5 Oct 2017. The study will take 6 months and should be completed by 5 April 2018.
Stakeholders’ Engagement:
PBTs in Selangor	: 11 Dec, 13 Dec, 18 Dec & 20 Dec 2017
IEM	: 22 Dec 2017 & 3 Feb 2018
PBTs in Negeri Sembilan	: 3 Jan 2018
PBTs in Melaka	: 10 Jan 2018
PAM	: 11 Jan & 13 Jan 2018
Industry players	: 5 Feb, 8 Feb, 12 Feb & 19 Feb 2018
Reports
Inception Report	: 12 Nov 2017
Progress Report 1	: 6 Dec 2017
Progress report 2	: 8 Mar 2018
Stakeholders’ Engagement:
1) Technical Agencies : 6 February 2018 at KPKT.
2) Operators :
a) PAM (Session 1) : 11 January 2018
b) PAM (Session 2) : 13 January 2018
c) IEM (Session 2) : 3 February 2018
Final Report (phase 1)
7 May 2018