## Slide 1
2016 Weightage : 20% | 2017 Weightage : 40% | 2018 Weightage : 40% | 2019 | 2020
150 QLASSIC assessors accredited 100 CIDB QLASSIC Assessors Accredited 300 QLASSIC Assessment QLASSIC portal completed | 350 QLASSIC assessors accredited 150 CIDB QLASSIC Assessors Accredited 300 QLASSIC Assessment | 500 QLASSIC assessors accredited 200 CIDB QLASSIC Assessors Accredited 300 QLASSIC Assessment QLASSIC portal launched |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Mohd Faizal Abdul Hamid
KPI LEADER CIDB
KPI DESCRIPTION 500 accredited QLASSIC assessors produced by Q4 2018
INITIATIVE Q1 - Increase Emphasis On Quality And Implement Quality Assessments
SUB-INITIATIVE -
QUALITY, SAFETY & PROFESSIONALISM
KPI Q1-006
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG1.
QLASSIC which stands for Quality Assessment System in Construction started in 2006. This was adopted from CONQUAS, Singapore.
This report focuses on QLASSIC Assessor, CIDB QLASSIC Assessor, QLASSIC Assessment and QLASSIC Portal.
4 Steps to become a CIDB QLASSIC Assessor.
Step 1: Awareness Course (1 Day)
Step 2: Assessor Course with Theory Exam (2 Days)
Step 3: Practical Test (2 Days)
Step 4: Hands-On (2-3 Days)
QLASSIC Assessors
401 out of the targeted 500 QLASSIC assessors were accredited by CIDB from 2016 to Q2 2018. All these assessors have undergone Step 1 to Step 3 of the training andaccreditation program. Most of these assessors serve their respective individual company needs for QLASSIC assessment during construction. To qualify as CIDB QLASSIC assessors require them to undergo Step 4 : Hands-On
CIDB QLASSIC Assessors
156 out of the targeted 200 CIDB QLASSIC assessors were accredited from 2016 to Q2 2018. These assessors have completed Step 1 to Step 4 and are registered with CIDB. CIDB appoints this group of assessors to carry out QLASSIC assessment. There are 14 internal assessors within CIDB and 142 external assessors from various industry players such as developers, consultants and contractors. Currently, there are about 40 full time QLASSIC assessors. They may perform up to 8 projects per month.
QLASSIC Assessment
774 out of the targeted 900 projects have been assessed using QLASSIC from 2016 to Q2 2018. 732 out of 774 (94.57%) are private projects and 42 (5.43%) are public projects.
In Q2 2018, approximately 55% of the projects assessed are located in Klang valley (Selangor, Kuala Lumpur and Putrajaya), while Johor and Kedah contributed 8.8% and 11.8% respectively.
For Q2 2018, in terms of building category, 33 out of 68 projects (48.53%) are landed housing, 22 (32.35%) are stratified housing, 11 (16.18%) consist of public/ commercial/industrial buildings (without centralised cooling system) and 2 (2.94%) consists of public/ commercial/industrial buildings (with centralised cooling system)
The highest QLASSIC score for projects in Q2 2018 is 86%, the lowest QLASSIC is 62% and the average QLASSIC score is 74.2%.
In Q2 2018, 51 projects (75%) achieved QLASSIC score of at least 70% while 17 projects (25%) achieved score of less than 70%
QLASSIC Portal
Minister of Works soft-launched QLASSIC Portal on 21 Aug 2017 at Royale Chulan Hotel, Kuala Lumpur. The portal functions include QLASSIC online application, training online-application, application assessment based on the new CIS 7 (QLASSIC Apps), database, announcement and publication. QLASSIC portal can be accessed at qlassic.cidb.gov.my.

## Slide 2
2016 Weightage : 20% | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 10% | 2020 Weightage : 10%
10% of public building projects achieve 70% QLASSIC Score Policy paper on QLASSIC adoption approved by Ministry of Works | 20% of public building projects achieve 70% QLASSIC Score QLASSIC analysis on 7 JKR pilot projects produced Public stakeholders’ feedback secured on QLASSIC implementation Impact study on project cost in implementing QLASSIC completed | 30% of public building projects achieve 70% QLASSIC Score Tenders for public building projects to adopt QLASSIC score as part of tender evaluation criteria for tenders open to G7 contractors QLASSIC analysis on 3 JKR pilot projects produced Contractual requirement guideline for minimum QLASSIC score of 70 completed for incorporation into tender documents for public building projects participated by G7 contractors Quality Assurance/Quality Control guideline published for implementation by G7 contractors undertaking public projects Mechanism on implementing QLASSIC as a deciding factor for tender proposal completed | 40% of public building projects achieve 70% QLASSIC Score | 50% of public building projects achieve 70% QLASSIC Score
SPONSOR Datuk Ir. Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Mohd Faizal Abdul Hamid
KPI LEADER KKR
KPI DESCRIPTION More than 50% of public building projects completed annually by G7 contractors achieve a minimum QLASSIC score of 70 by Q4 2020
INITIATIVE Q1 - Increase Emphasis On Quality And Implement Quality Assessments
SUB-INITIATIVE -
This KPI is under the purview of IWG1. This KPI will focus on QLASSIC assessments on public projects implemented by G7 contractors only.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q1-007
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Year | Baseline | No. of Projects Targeted | No. of Projects Assessed | No. of Projects Achieved >70% | Achievement
2016 | 48 | 5 (10%) | 8 | 2 | (2/5) x100 = 40%
2017 | 48 | 10 (20%) | 20 | 10 | (10/10) x100 = 100%
2018 | 166 | 50 (30%) | 14 | 11 | (11/50) x100 = 22%
QLASSIC Score on Public Projects
Scoring For The QLASSIC Assessment
In Q1 2018, the highest QLASSIC score for projects is 79%, the lowest QLASSIC is 66% and the average QLASSIC score is 72.1%
In Q2 2018, the highest QLASSIC score for projects is 77%, the lowest QLASSIC is 72% and the average QLASSIC score is 74.5%.

## Slide 3
SPONSOR Datuk Ir. Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Mohd Faizal Abdul Hamid
KPI LEADER KKR
KPI DESCRIPTION More than 50% of public building projects completed annually by G7 contractors achieve a minimum QLASSIC score of 70 by Q4 2020
INITIATIVE Q1 - Increase Emphasis On Quality And Implement Quality Assessments
SUB-INITIATIVE -
QUALITY, SAFETY & PROFESSIONALISM
KPI Q1-007
PROGRESS REPORT UNTIL Q2 2018
Policy paper on QLASSIC adoption
Subsequent to obtaining feedback from Government and private sector, the enhanced policy paper (concept paper) has been tabled at Mesyuarat Jawatankuasa Kerja Dasar Kementerian Kerja Raya (JKDKKR) on 10th April 2018. The meeting has agreed to the following:
Policy paper to be reviewed including considerations on :
i) promotion
ii) feedback from higher level of management within relevant agencies
Mandating of QLASSIC to be postponed until reviewing process has been done as per item a.
A meeting between Kementerian Kerja Raya, Jabatan Kerja Raya and CIDB is scheduled to be held on 2 July 2018 to discuss further on item a and b.
Impact Study on Project Cost Implementing QLASSIC
UiTM was appointed in Nov 2017 and the report was completed on 22 Jan 2018.
Findings from the study concluded that the cost implications with the implementation of QLASSIC is very minimal i.e., <3% increase of cost for the QLASSIC assessed elements. The figure will be very much lower if this increase is divided by the overall construction cost.
QLASSIC Analysis on 3 JKR Pilot Projects
QLASSIC analysis on 3 JKR pilot projects was completed in Q4 2017. Common defects identified are :
floor & wall - finishing, hollowness, jointing
ceiling - finishing & jointing
door/window/M&E fittings - material damages, joints & gaps
Contractual Requirement guideline completed
CIDB appointed Canaan Building Inspections & Rectification Services on 28 Feb 2018 to develop the contractual requirement guideline and it was completed on 30 June 2018. It is expected to be tabled to IWG1 for required feedback in July 2018.
Quality Assurance/Quality Control guideline published
CIDB appointed Global Quality Excellence Academy Sdn Bhd on 22 Feb 2018 to develop a QA/QC guideline with the completion date at the end of November 2018. The guideline is 80% completed. It is scheduled to be tabled to IWG1 for required feedback in July 2018.
QLASSIC as a deciding factor for tender proposal
CIDB appointed Canaan Building Inspections & Rectification Services in Feb 2018 to develop the mechanism on implementing QLASSIC as a deciding factor for tender proposal with the completion date at the end of September 2018.

## Slide 4
2016 | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 20% | 2020 Weightage : 20%
- | 20% of private residential project achieve minimum of 70% QLASSIC Score | 30% of private residential project achieve minimum of 70% QLASSIC Score Tenders for private residential building projects to adopt QLASSIC score as part of tender evaluation criteria for tenders exceeding RM10m Quality Assurance/Quality Control guideline published for implementation by G7 contractors undertaking private residential projects Contractual requirement guideline for minimum QLASSIC score of 70 completed for incorporation into tender documents for private residential projects exceeding RM10m | 40% of private residential project achieve minimum of 70% QLASSIC Score | 50% of private residential project achieve minimum of 70% QLASSIC Score
SPONSOR Datuk Ir. Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Mohd Faizal Abdul Hamid
KPI LEADER REHDA
KPI DESCRIPTION More than 50% of private residential projects with contract sum exceeding RM10m completed annually to achieve a minimum QLASSIC score of 70 by Q4 2020
INITIATIVE Q1 - Increase Emphasis On Quality And Implement Quality Assessments
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG1.
QLASSIC Score on Private Projects
In Q2 2018, 64 projects were assessed using QLASSIC. The total projects assessed up till Q2 2018 is 141.
In Q1 2018, the highest QLASSIC score for projects is 84%, the lowest QLASSIC score is 59% and the average QLASSIC score is 73.9%.
In Q2 2018, the highest QLASSIC score for projects is 86%, the lowest QLASSIC score is 62% and the average QLASSIC score is 74.2%.
Quality Assurance/Quality Control guideline published
CIDB appointed Global Quality Excellence Academy Sdn Bhd on 22 Feb 2018 to develop a QA/QC guideline with the completion date at the end of November 2018. The guideline is 80% completed. It is scheduled to be tabled to IWG1 for required feedback in July 2018.
QLASSIC as a deciding factor for tender proposal
CIDB appointed Canaan Building Inspections & Rectification Services in Feb 2018 to develop the mechanism on implementing QLASSIC as a deciding factor for tender proposal with the completion date at the end of September 2018.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q1-111
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Year | Baseline | No. of Projects Targeted | No. of Projects Assessed | No. of Projects Achieved >70% | Achievement
2017 | 292 | 58 (20%) | 298 | 208 | (208/58) x100 = 358.6%
2018 | 91 | 27 (30%) | 141 | 107 | (107/27) x100 = 396.3%

## Slide 5
2016 | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 40% | 2020
- | 30% of G7 contractors undertaking building projects shall have minimum one qualified QLASSIC assessor | 60% of G7 contractors undertaking building projects shall have minimum one qualified QLASSIC assessor | 100% of G7 contractors undertaking building projects shall have minimum one qualified QLASSIC assessor | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Mohd Faizal Abdul Hamid
KPI LEADER MBAM
KPI DESCRIPTION Minimum of one qualified QLASSIC assessor for every G7 contractor undertaking building projects by end of 2019
INITIATIVE Q1 - Increase Emphasis On Quality And Implement Quality Assessments
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG1.
The statistic of qualified QLASSIC assessors for every G7 contractors undertaking building projects are as follows :
In Q1 2018, CIDB appointed CIDB Holdings to organize the practical test (step 3) to produce Qualified QLASSIC Assessors with the first practical test executed on 24 April 2018.
The record of these assessors can be found in the CITP portal via www.citp.my
QUALITY, SAFETY & PROFESSIONALISM
KPI Q1-112
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
 | 2017 | 2018
Baseline | 340 projects | 500 projects
Target | 102 (30% of 340) | 300 (60% of 500)
Achievement | 102 | 87 trained 39 qualified (Q2 2018)
Achievement % | 100% | 13%

## Slide 6
2016 | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 20% | 2020 Weightage : 20%
- | 10% of JKR’s building projects exceeding RM10Mn shall have one site supervisory staff trained on QLASSIC | 30% of JKR’s building projects exceeding RM10Mn shall have one site supervisory staff trained on QLASSIC | 60% of JKR’s building projects exceeding RM10Mn shall have one site supervisory staff trained on QLASSIC | 100% of JKR’s building projects exceeding RM10Mn shall have one site supervisory staff trained on QLASSIC
SPONSOR Datuk Ir. Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Mohd Faizal Abdul Hamid
KPI LEADER CREATE
KPI DESCRIPTION Minimum of one Site Supervisory Staff (SSS) for public building projects trained on QLASSIC by 2020
INITIATIVE Q1 - Increase Emphasis On Quality And Implement Quality Assessments
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG1.
The statistic of site supervisory staff (SSS) for public building projects trained on QLASSIC are as follows :
QUALITY, SAFETY & PROFESSIONALISM
KPI Q1-113
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
The table below shows the training conducted:
With the high commitment given by JKR in ensuring many more of their site supervisor staff gets trained in QLASSIC, it is expected that the number of JKR projects achieving a high QLASSIC score will increase substantially in the years to come.
Date | Venue | No. of JKR’s SSS | Accredited Trainer
15 – 17 Oct 2017 | Create, Melaka | 40 | Ir. Shahrin
21 – 23 Nov 2017 | Menara PJD | 35 | Ir. Shahrin
6 - 8 Feb 2018 | Create, Melaka | 50 | Hj Mokhtar
27 - 29 Mac 2018 | Menara PJD | 32 | Hj. Rahlan
 | 2017 | 2018
Baseline | 145 projects | 259 projects
Target | 15 (10% of 145) | 78 (30% of 259)
Achievement | 75 | 82 (Q2 2018)
Achievement % | 500% | 105%

## Slide 7
2016 | 2017 Weightage : 40% | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020
- | REHDA support to incorporate QLASSIC in contractual requirement secured 20 key developers identified Guideline on contractual requirement on QLASSIC adoption completed Minimum of 5 promotional events on QLASSIC undertaken | Tenders for private residential building projects to adopt QLASSIC score as part of tender evaluation 10 key developers adopt guideline for minimum QLASSIC score of 70 in their tenders Minimum of 5 promotional events on QLASSIC undertaken | 10 key developers adopt guideline for minimum QLASSIC score of 70 in their tenders Minimum of 5 promotional events on QLASSIC undertaken | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Mohd Faizal Abdul Hamid
KPI LEADER REHDA
KPI DESCRIPTION 20 key developers adopt guideline for minimum QLASSIC score of 70 in their contractual requirement for residential projects by 2019
INITIATIVE Q1 - Increase Emphasis On Quality And Implement Quality Assessments
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG1.
REHDA’s support
On 6 March 2018, meeting with REHDA agreed on the following:-
Tenders for private residential building projects to adopt QLASSIC score as part of tender evaluation
10 key developers adopt guideline for minimum QLASSIC score of 70 in their tenders
promotional events on QLASSIC to be undertaken
To incorporate QLASSIC in contractual requirement secured
Key developers adopt guideline for minimum QLASSIC score of 70 in their tenders
20 key developers were identified in 2017 to adopt the guideline for minimum QLASSIC score of 70 in their tenders.
Promotional events on QLASSIC
CIDB plans to have the following series of seminar :
Kuantan : 5 Jul 2018
Melaka : 2 Aug 2018
Alor Setar : 29 Aug 2018
Tawau : 20 Sep 2018
Kuching : 14 Nov 2018
QUALITY, SAFETY & PROFESSIONALISM
KPI Q1-133
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 8
2016 Weightage : 100% | 2017 | 2018 | 2019 | 2020
MS2593:2015 on construction worker’s amenities published by Q1 2016 |  |  |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB
KPI DESCRIPTION Malaysian Standards for Temporary Construction Workers' Amenities and Accommodation (Code of Practice ) published by Q1 2016
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2a - Regulate minimum level of construction workers' amenities
This KPI is under the purview of IWG2.
CIDB together with the Department of Malaysian Standards (DoSM), government agencies, NGOs, universities and industry stakeholders have developed the content of MS2593:2015 Malaysian Standard For Temporary Construction Site Workers' Amenities And Accommodation - Code Of Practice. This standard was officially issued by the DoSM on 19 January 2016 and was subsequently published by SIRIM.
Crucial elements from MS2593:2015 specifically for temporary accommodation regarding the minimum requirement sizes for sleeping area and toilet ratio were identified to be included in Rang Undang-Undang Penginapan Pekerja 201X (RUU).
This KPI is 100% achieved.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-008
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 9
2016 Weightage : 34% | 2017 Weightage : 36% | 2018 Weightage : 30% | 2019 | 2020
Draft on amendment to Act 446 or new Act by JTK completed | MS2593:2015 on construction worker’s amenities aligned to amended Act446 or new Act Report on industry feedback on Act 446 amendments obtained Final Draft on new Act completed | Promotion activities to enhance awareness on amended Act 446 for construction conducted Act 446 amended/ tabled at Parliament |  | 
KPI DESCRIPTION Act 446 on workers' minimum standard of housing and amenities for all sectors including construction sector tabled in Parliament by Q4 2018.
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2a - Regulate minimum level of construction workers' amenities
This KPI is under the purview of IWG2.
Act 446 tabled at Parliament
Act 446 is in the process of being amended by JTK. JTK plan to table the proposed amendment at Parliament in October 2018.
Promotion activities
Promotion activities to enhance the awareness on the amendment of Act 446 for construction was conducted at 3 locations as below:
Penang : 2 April 2018
Johor : 23 April 2018
Sarawak : 25 June 2018
Another 2 promotional activities will be held as follows:
Kuala Lumpur : 9 July 2018
Sabah : 25 July 2018
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-009
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB

## Slide 10
2016 Weightage : 30% | 2017 Weightage : 40% | 2018 Weightage : 10% | 2019 Weightage : 20% | 2020
2 pilot projects on MS2593:2015 compliant worker dormitories constructed by GAMUDA Engineering 2 pilot projects agreed by identified client 2 reports on implementation of MS-compliant worker dormitories published | 3 pilot projects implemented by identified clients 3 reports on implementation of MS-compliant worker dormitories published | 1 pilot project implemented by identified clients 1 report on implementation of MS2593:2015 or other relevant authority requirement for worker dormitories compliance published | 2 pilot projects implemented by identified clients 2 reports on implementation of MS2593:2015 or other relevant authority requirement for worker dormitories compliance published | 
KPI DESCRIPTION Minimum 8 Centralised Workers’ Accommodation Models Implemented by Q4 2019
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2a - Regulate minimum level of construction workers' amenities
This KPI is under the purview of IWG2.
6 Pilot Projects Implemented (for 2016 - 2018 targets)
6 pilot projects on Centralised Labour Quarters (CLQ) models were implemented as follows:
Sunway Construction Sdn Bhd (Southern Region CLQ, Cobra Camp, Kampung Sg Melayu Johor)
Sunway Construction Sdn Bhd (CLQ Package V201, Sg Buloh Selangor)
Ahmad Zaki Sdn Bhd (CLQ Package V202, Sg Buloh Selangor)
IJM Construction Sdn Bhd (CLQ Package V203, Sg Buloh Selangor)
Construction Labour Exchange Berhad (CLAB) (CLQ V1, Sg Buloh Selangor)
Tecnicas Reunidas (TR) at Pengerang Project, Johor
6 Reports on the Implementation of Worker Dormitories (for 2016 - 2018 targets)
6 reports on the implementation to MS2593:2015 were prepared and published as follows :
Southern Region CLQ
CLQ V1
CLQ Package V201
CLQ Package V202
CLQ Package V203
CLQ PRPC Pengerang
These following sites were visited to identify potential projects that complies to MS2593:2015 to be included as the KPI’s pilot project :
Site visit to CLQ Mantin, Negeri Sembilan was held on 30 March 2017 in collaboration with JTK.
Site visit to 2 CLQs belonging to CLAB and IJM in Sg Buloh, Selangor area was held on 14 June 2017
Site visit to CLQ belonging to PETRONAS in Pengerang Project, Johor was held on 17th October 2017.
Site visit to CLQ belonging to MYR Entry Sdn Bhd in Puchong, Selangor was held on 28 November 2017.
Based on the visits, the above sites have not fully met the requirements of MS2593:2015 to be eligible as pilot projects.
A Memorandum of Understanding (MoU) was proposed between CIDB and MRT (for CLQs managed by Sunway, IJM and AZSB) . The MoU was later declined due to insignificant mutual benefit to be gained by both parties.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-010
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB

## Slide 11
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
Construction-specific SHO/SSS modules developed reviewed and made part of training programme by Q4 2016 203 SHO and 125 SSS trained Report on SHO and SSS trained produced | 223 SHO and 137 SSS trained Report on SHO and SSS trained produced | 245 SHO and 151 SSS trained Report on SHO and SSS trained produced | 270 SHO and 166 SSS trained Report on SHO and SSS trained produced | 297 SHO and 183 SSS trained Report on SHO and SSS trained produced
KPI DESCRIPTION SHO/SSS trained increased by 10% per year from 2015 baseline (SHO-2030, SSS-1250)
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2b - Improve level of occupational safety and health at construction site
This KPI is under the purview of IWG2.
Safety Health Officers (SHO) trained
The statistic of Safety Health Officers (SHO) trained are as follows :
The above achievements had exceeded the target set.
Site Safety Supervisor (SSS) trained
The statistic of Site Safety Supervisor (SSS) trained are as follows :
The above achievements had also exceeded the target set.
Report on SHO And SSS Trained Produced
Report on the SHO/SSS trained will be produced by Q4 2018. Currently compilation of the data is on going.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-012
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB
 | 2016 | 2017 | 2018 | 2019 | 2020
Target | 203 | + 20 (10% of 203) = 223 | + 22 (10% of 223) = 245 | + 25 (10% of 245) = 270 | + 27 (10% of 270) = 297
Achieved | 373 | 572 (cumulative = 945) | 294 (cumulative = 1,239) |  | 
Achievement % | 183% | 424% | 505% |  | 
 | 2016 | 2017 | 2018 | 2019 | 2020
Target | 125 | + 12 (10% of 125) = 137 | + 14 (10% of 137) = 151 | + 15 (10% of 151) = 166 | + 17 (10% of 166) = 183
Achieved | 396 | 954 (cumulative = 1,350) | 486 (cumulative = 1,836) |  | 
Achievement % | 317% | 985% | 1,215% |  | 

## Slide 12
2016 | 2017 Weightage : 10% | 2018 Weightage : 20% | 2019 Weightage : 30% | 2020 Weightage : 40%
 | 10 contractors registered to be trained on OSH Management system | 30 contractors trained on OSH Management system | 35 contractors trained on OSH Management system 25% of contractors trained on OSH management system gets certified | 35 contractors trained on OSH Management system 50% of contractors trained on OSH management system gets certified
KPI DESCRIPTION 50% of 100 contractors trained in Occupational Safety & Health Management System (MS1722/OHSAS18001/ISO OSH-MS45001) gets certified by Q4 2020
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2b - Improve level of occupational safety and health at construction site
This KPI is under the purview of IWG2.
CIDB appointed 3 consultants to conduct the training for OSH Management system on 28 August 2017.
1) Total Organisation Management Consulting (M) Sdn Bhd
2) QAI Sdn. Bhd.
National Institute of Occupational Safety and Health
The scope of work for the consultants cover key areas such as :
Occupational Safety & Health Management (OSHMS) System Design and Development Integration
Awareness & Documentation Training
Workshop on HIRARC
Emergency Response Plan (ERP)
Legal Requirement Review Workshop
OHSMS Implementation Guidance
Internal Auditor Training
Preparation Audit Report
Pre-Compliance Audit
This program is open to all contractors. The selection criteria are :
No certification to any Management System such as QMS ISO 9001;
Commitment from top management in establishing and managing OSHMS
Adequate resources in establishing and managing OSHMS;
Participation in any CIDB’s program;
Current ongoing projects and the progress.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-014
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This program is fully borne by CIDB with an amount of RM40,300.00 per contractor. CIDB will do the selection of contractors. To guarantee the contractor’s commitment in this program, contractor is required to provide a Bank Guarantee to CIDB for the total sum of fee (RM40,300). This serves as an evidence of contractor's commitment but will be returned after Contractor has successfully attained certification. In any case, if the Contractor failed to complete the certification process and does not achieve the certification to OSHMS MS 1722 & OSHAS 18001, partial or full amount will be deducted from the Bank Guarantee depending on the development period.
10 contractors were selected to undergo this program.
Perkhidmatan Nyaman Niaga (G2) – training in progress
Luibina (M) Sdn Bhd (G7) - training in progress
Hatimuda Sdn Bhd (G7) - training in progress
Elektro Serve (M) Sdn Bhd (G7)
HDK Potential Engineering Sdn Bhd (G5)
Infrastructure Builders Sdn Bhd (G5)
Ambang Jitu Tech Sdn Bhd (G4)
Dynamic Wave Sdn Bhd (G7)
Kota Giam Constructions (G2)
Malinaz Enterprise (G1)
30 contractors trained on OSH Management system
3 out of 30 contractors had completed a 3 to 6 months OSH Management System training since January 2018.
Seminar on training of ISO45001:2018 (OSH Management System) was conducted on 29 June 2018 with 51 contractors participated.
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB

## Slide 13
2016 Weightage : 30% | 2017 Weightage : 50% | 2018 Weightage : 20% | 2019 | 2020
10% study on adequateness of relevant laws and regulations on safety completed | Industry feedback on draft of study rolled out Study report on the adequateness of relevant laws and regulations on safety published | Recommendations to government on the findings of the study submitted |  | 
KPI DESCRIPTION Recommendations to improve the legal and regulatory framework related to construction Occupational Safety & Health (OSH) submitted to government by Q2 2018.
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2b - Improve level of occupational safety and health at construction site
This KPI is under the purview of IWG2.
Report on Adequateness of Relevant Laws and Regulations on Construction Safety
The report on 'Kajian Mengenai Keberkesanan dan Kecukupan Undang-Undang dan Peraturan yang berkaitan dengan Keselamatan Pembinaan' was published in October 2017.
Among the key contents of the report are :
Difference in level of achievement in safety and health between oil and gas and construction industry
Identification of the laws and effectiveness on implementation of enforcement between Malaysia and other developed countries (United Kingdom, Australia and Singapore)
Identification of the existence of overlap of authority
Identification of prevailing weaknesses in construction industry practices
Recommendations for improvement
The recommendations for improvement includes revision of relevant laws, imposing penalty and fines, enforcement and role of industry players. These two recommendations were submitted to DOSH to improve the legal and regulatory framework related to Construction Occupational Safety and Health (OSH) :
DOSH to introduce the Construction Design and Management (CDM) Regulations
DOSH to enhance OSHA 1994 and FMA 1967
CIDB has presented the findings of HSE UK’s report to OSHCIM Steering Committee and in principle the committee decided OSHCIM is to be introduced as regulations under OSH Act 1994. The above recommendations and the regulations on OSHCIM and amendment to OSH Act 1994 will be tabled in the Parliament sitting in October 2018. Currently the proposed regulations and revised draft OSH Act 1994 has been submitted to AG Chamber by DOSH.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-015
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB

## Slide 14
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
Development of OSH BQ agreed by CIDB, DOSH and JKR | Gap analysis on the current OSH BQ documents of JKR, DOSH and CIDB finalised | Committee for development of standardised OSH BQ established Standard OSH BQ for government projects developed | Study report on impact of OSH BQ produced Recommendation to incorporate OSH BQ in government projects submitted to MOF | Circular on OSH BQ issued by MOF Report on OSH BQ implementation published
KPI DESCRIPTION Cost of Occupational Safety & Health (OSH) to be provided in all government tenders and contracts by Q4 2020.
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2b - Improve level of occupational safety and health at construction site
This KPI is under the purview of IWG2.
OSH BQ Documents
CIDB, JKR, and DOSH each have developed their own version of the OSH BQ.
  CIDB - Guideline For Occupational Safety and Health (OSH) Specification's Schedule of Prices
  JKR - Specifications for Occupational Safety and Health for Engineering Construction Works 2011; Bill of Quantities for Occupational Safety and Health Management . JKR has confirmed the element of OSH has been incorporated in their BQ under Preliminary Items based on circular JKR.KPKR:113.020.050/03 Jld 2 (9) dated 5 Jan 2012
  DOSH - Guideline on Contract Management
Gap analysis on JKR, DOSH and CIDB OSH BQ
UiTM was appointed to conduct the gap analysis through a workshop from 21- 23 Nov 2017 with the following objectives :
To investigate the current content of available OSH documents
To determine the content suitability for government tenders and contracts
Based on the recommendation of the gap analysis study conducted, CIDB, JKR, and DOSH have agreed at a meeting on 20 December 2017, that one standard OSH BQ document should be developed for government projects.
The recommendation from the gap analysis study was endorsed at the IWG2 meeting in February 2018.
Committee for development of standardised OSH BQ
CIDB has identified potential members of the industry from PAM, ACEM, RISM, MBAM, JKR, DOSH, UM for the formation of the committee. This committee is expected to be formed in mid August 2018. The 1st meeting of this committee will be called once the final draft of the OSH BQ is prepared by UiTM.
Standard OSH BQ for Government Projects
UiTM was appointed in April 2018 to develop a Standard OSH BQ for government projects. The standard is at 50% progress and scheduled to be completed in November 2018.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-016
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB

## Slide 15
This is a new KPI introduced in 2017 under the purview of IWG2.
20% of qualifying public projects achieve 3 star SHASSIC rating
For Q2 2018, 32 out of 42 public projects assessed, achieved 3 star and above SHASSIC rating. Achievement for Q2 2018 is 76.2%.
SHASSIC Assessments
In Q2 2018, 149 projects were assessed using SHASSIC assessment against the target of 300 in 2018. The breakdown of the projects’ star rating are as follows :
Report on SHASSIC adoption by government
The report will be produced by Q4 2018.
Improvement to SHASSIC score proposed
Improvement on SHASSIC assessment and score (CIS10) is currently being studied and expected to be completed by Q4 2018.
Minimum of 5 promotional events on SHASSIC conducted
3 promotional events on SHASSIC had been conducted at the following locations:
Penang : 2 - 3 Apr 2018
Johor : 23 - 24 Apr 2018
Sarawak : 25 - 26 Jun 2018
Another 2 promotional events on SHASSIC will be held as follows:
Kuala Lumpur : 9 - 10 Jul 2018
Sabah : 26 – 26 July 2018
Policy paper on SHASSIC adoption approved by Ministry of Works
Policy paper on SHASSIC adoption was submitted to Ministry of Works on 21 March 2018 where it was presented at the Mesyuarat JKDKKR on 10 April 2018. JKDKKR requested CIDB to arrange further discussions scheduled to be held on 2 July 2018 with JKR and KKR on the adoption of SHASSIC in government projects.
2016 | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 30% | 2020 Weightage : 30%
 | Policy paper on SHASSIC adoption submitted to Ministry of Works 50 SHASSIC assessors accredited 120 projects assessed using SHASSIC Minimum of 5 promotional events on SHASSIC conducted | 20% of qualifying public projects achieve 3 star SHASSIC rating 300 projects assessed using SHASSIC Report on SHASSIC adoption by government produced Improvement to SHASSIC score proposed Minimum of 5 promotional events on SHASSIC conducted Policy paper on SHASSIC adoption approved by Ministry of Works | 30% of qualifying public projects achieve 3 star SHASSIC rating 400 projects assessed using SHASSIC Report on SHASSIC adoption by government produced Improvement to SHASSIC score completed Minimum of 5 promotional events on SHASSIC conducted | 50% of qualifying public projects achieve 3 star SHASSIC rating 500 projects assessed using SHASSIC Report on SHASSIC adoption by government produced Minimum of 5 promotional events on SHASSIC conducted
KPI DESCRIPTION More than 50% of public projects completed achieves minimum SHASSIC assessment score of 3 star by Q4 2020
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2b - Improve level of occupational safety and health at construction site
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-114
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Projects | 1 star | 2 star | 3 star | 4 star | 5 star | Total | % Achieved ≥ 3 star
Public | 2 | 8 | 10 | 14 | 8 | 42 | 32/42 = 76.2%
Private | 9 | 21 | 31 | 20 | 26 | 107 | -
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB

## Slide 16
2016 | 2017 Weightage : 40% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
 | Guideline on Occupational Safety & Health (OSH) in construction industry (management) published Technical committee to develop module and promote guideline on OSH in construction industry (management) established Study on Securing Improvement in the Health & Safety Performance of Malaysia’s Construction Industry executed 3 seminars to promote Guideline on OSH in construction industry (management) conducted | Module on OSH in construction industry (management) developed “Train the Trainers" on OSH in construction industry (management) conducted 1 pilot project to use guideline on OSH in construction industry (management) executed Study report from HSE on Securing Improvement in the Health & Safety Performance of Malaysia’s Construction Industry completed Pilot project to use HSE study report executed 3 seminars to promote Guideline on OSH in construction industry (management) conducted | Module on OSH in construction industry (management) established Training OSH in construction industry (management) established in training institute 1 pilot project to use guideline on OSH in construction industry (management) executed 3 seminars to promote Guideline on OSH in construction industry (management) conducted | The new regulations for Occupational Safety & Health (OSH) in Construction Industry (Management) drafted Guideline on OSH in construction industry (management) implemented 1 pilot project to use guideline on OSH in construction industry (management) executed
SPONSOR Datuk Ir. Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Khairunnizam Sulaiman
KPI LEADER DOSH
KPI DESCRIPTION Guideline on Occupational Safety & Health (OSH) in Construction Industry (Management) implemented by 2020
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2b - Improve level of occupational safety and health at construction site
This is a new KPI introduced in 2017 under the purview of IWG2.
Guideline on Occupational Safety & Health in construction industry (management) (OSHCI(M))
The guideline was published by DOSH on 28 Feb 2017. During International Construction Week (ICW) 2017 on 13 April, this guideline was presented to major stakeholders for implementation.
Module on OSHCI(M)
DOSH has appointed UTM to develop modules for developers, designers, contractors, government agencies and student. The draft module is being reviewed by experts and expected to be completed in October 2018.
Train the Trainers
Train the Trainers will be conducted once the modules are completed.
Pilot Projects
The usage of OSHCI(M) for the 2 pilot projects from JKR & Lendlease previously identified was unable to be continued due to technical issues.
It may be difficult to identify pilot project to implement OSHCI(M) within this year since it involves client’s input, design stage & construction stage.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-115
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Study on Securing Improvement in the Health & Safety Performance of Malaysia’s Construction
The study report from HSE was presented by Mr. Nic Rigby of HSE UK’s on 29 March 2018 during ICW 2018. The report will be published and distributed to interested parties.
Pilot Project to use HSE Report
OSHCI(M) Steering Committee in its meeting on 6 Jun 2018 decided to review this KPI due to unavailability of pilot project to implement those recommendations put forward by HSE report . However, the recommendation on CDM was taken up by DOSH (OSHCI(M)) and it is being reviewed by AG Chambers before tabling it to Minister/Parliament for approval.
Seminars
3 seminars on OSHCI(M) were conducted as follows:
2 April 2018 in Penang
23 April 2018 in Johor
25 Jun 2018 in Sarawak
A special briefing session was also held on 26 April 2018 between Building Industry President’ Council (BIPC) members and OSHCIM steering committee.

## Slide 17
2016 | 2017 Weightage : 30% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 30%
 | Guideline for Safe Design of Building & Structure completed. Guideline for Site Supervision completed. Committee for Guideline On Design of Temporary / False Work established | Guideline on Design of Temporary / False Work 50% completed Committee for Guideline on Risk Management established | Guideline on Design of Temporary / False Work 100% completed. Guideline on Risk Management 50% completed | Guideline on Risk Management 100% completed
KPI DESCRIPTION Four strategic Guidelines on Safety in Construction published by Q4 2020
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2b - Improve level of occupational safety and health at construction site
This is a new KPI introduced in 2017 under the purview of IWG2.
Guideline for Safe Design of Building & Structure
Guideline for Safe Design of Building & Structure is completed.
Guideline for Site Supervision by CIDB
Guideline for Site Supervision by CIDB known as “Program Latihan Penyelia Tapak Binaan Bagi Tujuan Pentauliahan Dan Akreditasi Penyelia Tapak Binaan” is completed .
Guideline for Supervision by Board of Engineers Malaysia (BEM)
Guideline by BEM known as Supervision of Construction Works is completed.
Guideline On Design of Temporary / False Work
The final draft of the above guideline was tabled to the Committee on 27 Feb 2018. It was approved by CIS 23 committee members for public comment. The public comment period was from 17 May 2018 – 14 June 2018. Comments received are being reviewed by CIS 23 committee members. A meeting is scheduled be held on 24 July 2018.
Committee for Guideline on Risk Management
A meeting with industry players was held on 16 April 2018 to clarify whether ‘risk management’ of safety in construction has the same meaning as HIRARC. It was confirmed that Guideline on Risk Management is the HIRARC. A consultant is expected to be appointed in July 2018 to prepare draft Guideline on HIRARC to be tabled to the above committee. Members of the above committee have been identified and is expected to be appointed once the draft HIRARC is ready.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-116
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB

## Slide 18
2016 | 2017 Weightage : 15% | 2018 Weightage : 35% | 2019 Weightage : 30% | 2020 Weightage : 20%
 | Safety Culture Tool developed | 4 pilot projects assessed for using safety culture tools. | 3 pilot project assessed for using safety culture tools. | 3 pilot project assessed for using safety culture tools.
KPI DESCRIPTION 10 pilot projects assessed using Safety Culture Tools achieve acceptable score by Q4 2020
INITIATIVE Q2 - Improve workplace safety and workers' amenities
SUB-INITIATIVE Q2b - Improve level of occupational safety and health at construction site
This is a new KPI introduced in 2017 under the purview of IWG2.
The Safety Culture Tool developed by CIDB is based on the Behaviour Based Safety (BBS), which is a broad term used to describe everything from basic employee behaviour audits and feedback to a comprehensive safety management system designed to change a company's safety culture.
There are 2 stages of the BBS Safety Culture Tool :
Stage 1 is to develop the BBS guideline and documentations that can be implemented by the construction industry in Malaysia
Stage 2 is to implement proactive BBS in Occupational Safety and Health management organisation; and to create a safe and healthy work culture in the workplace.
Safety Culture Tool developed
The Behaviour Based Safety (BBS) safety culture tool was endorsed by IWG2 in Feb 2018.
Pilot projects assessed using safety culture tools.
NIOSH was appointed by CIDB on February 2018 to carry out four pilot projects assessment using safety culture tools. The four projects are:
Ahmad Zaki Sdn Bhd (AZRB)
Naza Engineering and Construction (NEC)
ACRE Works Sdn Bhd
ECO World
Two out of four pilot projects (AZRB and NEC) were assessed and another two are scheduled to be assessed in July/August 2018.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q2-117
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M.Ramuseren
OIC Chuang Kuang Hong
KPI LEADER CIDB

## Slide 19
2016 Weightage : 10% | 2017 Weightage : 40% | 2018 Weightage : 40% | 2019 Weightage : 10% | 2020
Agreement by 6 key stakeholders on single contractor registration portal secured | Study on stakeholder’s contractor registration requirements completed | IT system on new CIDB contractor registration portal completed | CIDB contractor registration portal piloted by Q2 2019 | 
SPONSOR Sr.Ida Zuraida Binti Mohd. Yusoff
OWNER Suhaimi Mansor
OIC Zalina Mat
KPI LEADER CIDB
KPI DESCRIPTION New CIDB contractor registration portal piloted with agreements from 6 key stakeholders to collaborate by Q2 2019
INITIATIVE Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE Q3a - Streamline and enhance contractor registration
This KPI is under the purview of IWG3.
The contractor registration portal is a one stop online registration portal that enables local and foreign contractors to register with the relevant licensing agencies, hence eliminating the need to deal individually with each agency. The objective of the portal is to streamline the registration requirements to avoid duplication via information sharing thus saving time and cost for contractors and improving the ease of doing business in the construction sector. The Contractor Report Card is an important by-product of the portal whereby the comprehensive information shared by all agencies will benefit the clients and industry as a whole.
Agreement by 6 key stakeholders on single contractor registration portal
Six (6) key stakeholders have agreed in writing to establish a single contractor registration portal. They are :
1. PETRONAS
2. Unit Pendaftaran Kontraktor dan Juruperunding (UPKJ) Sarawak
3. Suruhanjaya Perkhidmatan Air Negara (SPAN)
4. Suruhanjaya Tenaga (ST)
5. Pusat Kontraktor Sabah (PUKONSA)
6. Bahagian Pembangunan Kontraktor & Usahawan (BPKU) Ministry of Works
Study on stakeholder’s contractor registration requirements
Study on the 6 key stakeholders registration requirements was completed in Q3 2017.
The contractor registration portal will enable contractors to access the Centralised Information Management System (CIMS) for their need to improve ease of doing business with the six (6) registering bodies.
IT system on new CIDB contractor registration portal
HiTech Padu Berhad is preparing the System Requirement Specification (SRS) for each 6 key stakeholders for the purpose of integrating the information between CIMS CIDB and their respective systems. 4 out of 6 SRS have been completed as follows :
Unit Pendaftaran Kontraktor dan Juruperunding (UPKJ) Sarawak
Suruhanjaya Perkhidmatan Air Negara (SPAN)
Suruhanjaya Tenaga (ST)
CIDB / Bahagian Pembangunan Kontraktor & Usahawan (BPKU) Ministry of Works
The SRS for the other two stakeholders i.e PETRONAS and PUKONSA are still on going.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q3-018
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 20
2016 Weightage : 100% | 2017 | 2018 | 2019 | 2020
Minister of Works’ approval on registration and accreditation criteria secured by Oct 2016 Registration launched by Dec 2016 |  |  |  | 
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Sr Ida Zuraida Mohd Yusoff
OIC Zalina Mat
KPI LEADER CIDB
KPI DESCRIPTION Criteria of registration and accreditation for facility management contractors launched by Q4 2016
INITIATIVE Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE Q3a - Streamline and enhance contractor registration
This KPI is under the purview of IWG3.
Minister of Works’ approval on registration and accreditation criteria
Currently, the registration of contractors covers four (4) categories i.e:
CE - Civil Engineering (43 specialisations)
B - Building (29 specialisations)
ME - Mechanical & Electrical (M-21 specialisations, E-35 specialisations)
FM - General Building & Infrastructure Facilities (F01), Healthcare Facilities (F02)
There are three ways to be registered as FM contractors:
For existing contractors, they can register under category F when they are awarded contracts on FM works
For new contractors with qualified FM technical personnel according to the registration grade
For new contractors without qualified FM technical personnel, but having the required FM project experience
However, CIDB only registers contractors grade G4 and above for this category.
To date, a total of 213 contractors with the following breakdown have been registered under FM:
This KPI is 100% achieved.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q3-019
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Contractors category | G4 Contractors | G5 Contractors | G6 Contractors | G7 Contractors | Total
No. of contractors registered F01 | 31 | 48 | 50 | 60 | 189
No. of contractors registered F02 | 4 | 1 | 1 | 18 | 24

## Slide 21
2016 Weightage : 60% | 2017 Weightage : 10% | 2018 Weightage : 10% | 2019 Weightage : 10% | 2020 Weightage : 10%
6 contractors facilitated to achieve 5* SCORE | 7 contractors facilitated to achieve 5* SCORE | 8 contractors facilitated to achieve 5* SCORE | 9 contractors facilitated to achieve 5* SCORE | 10 contractors facilitated to achieve 5* SCORE
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Sr Ida Zuraida Mohd Yusoff
OIC Zalina Mat
KPI LEADER CIDB
KPI DESCRIPTION 10 contractors facilitated in achieving 5 Star SCORE rating by Q4 2020
INITIATIVE Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE Q3a - Streamline and enhance contractor registration
This KPI is under the purview of IWG3.
SCORE is a program to measure the capacity and capability of contractors based on these parameters:
Business performance
Financial capability
Technical capability
Project management
Procurement management
Best practices
Management capability
Nine (9) construction companies obtained 5 star SCORE rating until Q2 2018 :-
Companies that have a potential to obtain 4/5 stars CIDB SCORE rating will undergo an audit at the contractors’ office where CIDB will facilitate them on how to improve marks on each scope in the evaluation form.
The targeted 8 contractors facilitated to achieve 5* SCORE rating is met.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q3-020
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
No. | Construction companies | Expiry Date
1. | Acre Works Sdn Bhd | 22 Apr 2020
2. | Advance Pact Sdn. Bhd | 2 Nov 2019
3. | Gamuda Berhad | 8 Jan 2020
4. | Irama Duta Sdn. Bhd | 8 Jan 2020
5. | George Kent Sdn. Bhd | 8 Jan 2020
6. | IJM Construction Sdn. Bhd | 8 Jan 2020
7. | Urusan Teknologi Wawasan Sdn. Bhd | 8 Jan 2020
8. | Iswarabena Sdn. Bhd. | 11 Feb 2020
9. | Putra Perdana Constructions Sdn. Bhd | 23 Sep 2019

## Slide 22
This KPI is under the purview of IWG4.
e-submission and e-approval
e-submission and e-approval form part of an integrated Construction Permit Management System designed to strengthen the delivery processes for the approval of Construction Permits. In line with the Eleventh Malaysia Plan (RMKe-11) that emphasizes on wider adoption of ICT, the new system will be based on open-source, fully integrated with existing systems, utilise cloud computing and customer-centric transaction processing. This initiative is expected to provide substantial cost saving and at the same time ensure higher productivity. This new application system has been designed to complement the existing 6 processes as follows:-
Pre-Construction
Process 1 - Data gathering (not mandatory)
Process 2 - Approval
Process 3 - Notification to start work
Construction
Process 4 - Interim inspection
Post-Construction
Process 5 - Final inspection
Process 6 - Building certification (CCC)
World Bank Ranking
Dealing with Construction Permit (DCP) is one of the ratings used by the World Bank in determining the ranking for Ease of Doing Business among 190 countries. Malaysia’s rank for Dealing with Construction Permit from year 2015 to 2017 is shown as below:
DTF : Distance To Frontier
2016 Weightage : 5% | 2017 Weightage : 5% | 2018 Weightage : 15% | 2019 Weightage : 35% | 2020 Weightage : 40%
Activities/ work breakdown and leaders for each activities identified. 6 Local Authorities identified as the 1st batch to pilot e-submission and e-approval. | Procedure for appointment of consultant to conduct study on existing OSC Online System finalised Consultant to conduct study on existing OSC Online System appointed | Final report on existing OSC Online System completed | Budget to develop/ enhance new OSC Online System applied under RMKe-11 OSC online piloted and finalised for 10 Local Authorities (LAs) | OSC 3.0 online launched at national level OSC 3.0 online implemented by 20 Local Authorities (LAs)
SPONSOR Sr. Ida Zuraida binti Mohd Yusoff
OWNER Ar. Sharina Intan binti Abdullah
OIC Noriman bin Muhammad
KPI LEADER JKT (KPKT)
KPI DESCRIPTION e-submission and e-approval rolled-out across at least 20 Local Authorities (LAs) by Q4 2020
INITIATIVE Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE Q3b - Strengthen One-Stop Centre for all construction permits/approvals
QUALITY, SAFETY & PROFESSIONALISM
KPI Q3-021
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Local Authorities identified to pilot e-submission
In 2016, 6 Local Authorities have been identified for the study on their respective requirement, process flows and issue identification and verification. These 6 are among the first batch of Local Authorities and the outcome of the study will be used to pilot the e-submission and e-approval. The six Local Authorities are:
Majlis Bandaraya Ipoh
Majlis Bandaraya Pulau Pinang
Majlis Bandaraya Johor Bahru
Majlis Bandaraya K. Terengganu
Majlis Perbandaran Kota Bahru
Majlis Bandaraya Shah Alam
Study on existing One Stop Centre (OSC) Online system
The existing OSC online is an online system used by relevant stakeholders such as Local Authorities (PBT), Principal Submitting Person (PSP) and External Technical Agencies (ATL) to process the application for Development Approval. This system involves the use of 2 main modules which are e-submission and e-processing for Process 1 and Process 2 only.
The objective of the study is to propose a framework for the development of an integrated construction permit management system for the PBTs. The findings of the study will be utilised to strengthen the budget request under Rolling Plan 4.
JKT has decided for the appointment of consultant to be re-tendered via open tender following the conditional approval by CIDB for the consultant’s project team to be replaced.
Pre-council meeting with KPI Leaders held on 19 March 2018 agreed for the ICT Unit of JKT to liaise with MAMPU to name 3 new consultants/companies.
The list of the proposed 3 consultants was submitted to CIDB on 14 May 2018. A follow-up letter on the status of the appointment was submitted to CIDB on 6 June 2018.
Year | DTF score | Ranking
2015 | 81.14 | 28/189
2016 | 81.08 | 13 /189
2017 | 82.17 | 13/190
2018 | 82.19 | 11/190

## Slide 23
2016 Weightage : 10% | 2017 Weightage : 15% | 2018 Weightage : 25% | 2019 Weightage : 30% | 2020 Weightage : 20%
Activities/ work breakdown and leaders for each activities identified. 6 Local Authorities identified in the 1st batch to pilot e-submission and e-approval. | Standard procedures on permit approval for small scale development for 5 Local Authorities established Locality DBKK : 70% MBJB : 50% MBI : 50% MBPP : 15% MPSP : 50% | Standard procedures on permit approval for small scale development for 5 Local Authorities established Locality DBKK : 100% MBJB : 100 % MBI : 100 % MBPP : 100 % MPSP : 100 % | Standard procedures on permit approval for small scale development for 5 Local Authorities established State Selangor : 100% N.Sembilan : 100 % Kedah : 100 % Sarawak : 100 % Kelantan : 100 % | Standard procedures on permit approval for small scale development for 4 Local Authorities established State Melaka : 100% Pahang : 100 % Perlis : 100 % Terengganu : 100 % Standard procedures on permit approval for small scale development rolled out nationwide
SPONSOR Sr. Ida Zuraida binti Mohd Yusoff
OWNER Ar. Sharina Intan Abdullah
OIC Noriman bin Muhammad
KPI LEADER MPC/ JKT (KPKT)
KPI DESCRIPTION Average number of construction permit approval procedures nationwide reduced to 13 and number of days reduced to 74 for small scale development projects (i.e., same as Kuala Lumpur) by Q4 2020
INITIATIVE Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE Q3b - Strengthen One-Stop Centre for all construction permits/approvals
This KPI is under the purview of IWG4.
Local Authorities identified to pilot e-submission
6 regions/states/ PBTs (Perak, Penang, Johor, Kelantan & Selangor) have been identified in the 1st batch to pilot enhancement to the construction permit approval procedures in 2016. Majlis Bandaraya Ipoh had been engaged on 22 Dec 2016.
Standard procedures on permit approval for small scale development
Currently the average number of procedures nationwide is 55 and the average number of days required to process approvals for construction permit is 106. The study on Standard Procedures for Permit Approval for Small Scale Development has commenced since 2016 with the following progress:-
Pertubuhan Arkitek Malaysia (PAM) was appointed, on 18 Dec 2017 to continue with the study for a period of 6 months beginning 2 Jan 2018, with the interim budget allocated by CIDB. The findings of the study will be utilised to strengthen the budget request under Rolling Plan 4.
Memorandum of Agreement (MoA) signed on 29 Jan 2018 and grant RM1Mn disbursed on 2 Mar 2018.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q3-022
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
List of Local Authorities engaged
MPSP and MBJB are in the process of producing the manual for procedure on permit approval.
Renewed engagement with MBPP was conducted on 23 Apr 2018.
Proposed Workshop for SOP MPSP is scheduled on 16 – 17 July 2018.
The Pilot Stage for DBKK is scheduled on 28 July 2018
Locality | Target 2018 | Progress Q2 2018
DBKK | 100% | 75%
MBJB | 100% | 55%
MBI | 100% | 71%
MBPP | 100% | 20%
MPSP | 100% | 67%
MBSA | 100% | 0%
pilot project
Locality | Date
COMMITMENT STAGE | 
MBJB | 4 Jan 2017
MBPP | 20 Jan & 17 Oct 2017
MPSP | 20 Jan 2017
DBKK | 6 Feb 2017
MAPPING STAGE | 
MBJB | 12 Jan 2017
DBKK | 21 Feb 2017
MBI | 4 Jan 2018
MBPP | 18 Apr 2018
Locality | Date
STREAMLINE STAGE | 
MBI | 27-28 Feb 2017
DBKK | 11-12 May 2017
DBKK | 25 May 2017
MBJB | 20-21 Nov 2017
MPSP | 29-30 Nov 2017
DBKK | 14-15 Nov 2017
DBKK | 18 Aug 2017
MPSP | 11 Sep 2017
MBI | 12-13 Apr 2018

## Slide 24
2016 Weightage : 10% | 2017 Weightage : 10% | 2018 Weightage : 40% | 2019 | 2020
 |  |  | Weightage : 40% | 
Activities/ work breakdown and leaders for each activities identified. Task force for disputes applications resolution established Problems Identifiaction Dialog with Locality Authority, Agencies, PEMUDAH & FGDCP conducted Directions to proceed establishment of DRM obtained | Selected existing mechanism to resolve dispute application mapped Scope, TOR, authority, mechanism, membership, funding, jurisdiction and framework for DRM finalized Established gaps in the existing Appeal Board mechanism which justifies for the need of a Construction Dispute Tribunal. Comparison of foreign mechanism for technical construction dispute and administrative dispute resolution. Draft of Technical Construction Dispute Settlement & development of questionnaires: Technical agencies and operators. | Completion of findings of focus group discussions (technical agencies) & partial focus group for operators &partial/progress findings on impact assessment. Final analysis of the feedback from the stakeholders. Conclusion of Impact assessment Conclusion of level of acceptance of stakeholders Final suggested Framework for Technical Construction Dispute Settlement. | Consultation with other states in Peninsular Malaysia. (by zones) Upgrade the framework Identify suitable real case study. Conduct pilot study for the unidentified project. Open consultation with all construction industry stakeholders (professional boards and institutions, developers) | Suggestions of required amendments to the law. Get the necessary clearance for the establishment of the dispute mechanism. Road show and awareness programme. Announcement to the public
SPONSOR Sr. Ida Zuraida binti Mohd Yusoff
OWNER Ar. Sharina Intan Abdullah
OIC Noriman bin Muhammad
KPI LEADER MPC/ JKT (KPKT)
KPI DESCRIPTION 100% of disputes applications resolved by the Dispute Resolution Mechanism (DRM) within 6 month of receipt starting in Q4 2020
INITIATIVE Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE Q3c - Set up tribunal for construction permit dispute resolution
This KPI is under the purview of IWG4.
Dispute Resolution Mechanism (DRM)
Dispute Resolution Mechanism (DRM) is an instrument established to resolve any technical disagreement or dispute arising from the construction permit approval processes. The mechanism is jointly formulated by a working group consisting of MPC, JKT and stakeholders in construction industry (Professional bodies and other industry players). The DRM will be handling disputes not currently covered under the existing Appeal Boards, that has been created under Town and Country Planning Act 1976 (Act 172) (TCPA). The framework for DRM will be formulated based on the best pratices of a number of Tribunals and Appeal Boards from the Commonwealth Countries.
Study on ‘Cadangan Penubuhan Tribunal untuk Pertikaian Permit Pembinaan di bawah Inisiatif Q3c CITP’
UiTM has been appointed to study and prepare a report on the establishment of a tribunal to resolve construction permit disputes on 5 Oct 2017. The study has taken 6 months and it was completed on 7 May 2018.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q3-023
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Stakeholders’ Engagement:
PBTs in Selangor : 11 Dec, 13 Dec, 18 Dec &
20 Dec 2017
2) IEM : 22 Dec 2017 & 3 Feb 2018
PBTs in N. Sembilan : 3 Jan 2018
PBTs in Melaka : 10 Jan 2018
PAM : 11 Jan & 13 Jan 2018
Industry players : 5 Feb, 8 Feb, 12 Feb &
19 Feb 2018
7) Technical Agencies : 6 Feb 2018 at KPKT
Reports
Inception Report : 12 Nov 2017
Progress Report 1 : 6 Dec 2017
Progress report 2 : 8 Mar 2018
Final Report (phase 1) : 7 May 2018

## Slide 25
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
CIDB construction law report (CLR) 2015 published | CIDB construction law report 2016 published CCLR web-based system with mobile compatibility30% completed 50% of IPTA adopted CLR as learning reference | CIDB construction law report 2017 published CCLR web-based system with mobile compatibility100% completed 100% of IPTA adopted CLR as learning reference 50% of IPTS adopted CLR as learning reference | CIDB construction law report 2018 published 100% of IPTS adopted CLR as learning reference | CIDB construction law report 2019 published 500 new users on CCLR web/app registered
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Mohamad Nor
KPI LEADER CIDB
KPI DESCRIPTION 1 annual journal summarising key lessons from decided construction cases with not less than 20 commentaries, beginning Q4 2016
INITIATIVE Q3 - Improve ease of doing business by addressing regulatory constraints
SUB-INITIATIVE Q3d - Enhance culture and practices by learning from decided construction cases
CCLR is a document consisting of construction related cases with case summaries derived from High Courts and Appellate Courts decisions from January to December each year beginning 2016. Commentaries by professionals from the construction industry, namely engineers, architects and quantity surveyors have been included, adding to the perspective of legal opinions provided by experts from the legal fraternity.
Publication of CIDB CLR
CCLR 2015 was published in June 2016 with 20 commentaries which is accessible from the CIDB website
CCLR 2016 was published in August 2017 with 40 commentaries
Publication of CCLR 2017
Latest statistics of construction cases collected in 2017 for CCLR 2017 are as follows:-
Federal Court (cases registered 20, cases resolved 14)
Appeal Court (cases registered 151, cases resolved 86)
High Court (cases registered 49, cases resolved 53)
Sessions Court (cases registered 18, cases resolved 22)
Magistrates Court (cases registered 8, cases resolved 7)
70% of the commentaries have been completed and CCLR 2017 is expected to be completed by end of July 2018
Web-based system with mobile compatibility development
ARK Knowledge was appointed on 5 December 2017 to develop the web-based system with a completion date in July 2018. As of Q2 2018, the following progress have been recorded:
24 Jan 2018 : Stage 1 (Approval of URC) completed
17 April 2018 : Stage 2 (Development of Prototype) completed
25 June 2018 : Stage 3 (Full completion) Content enrichment completed
In progress : Integration of payment gateway, training sessions and handover of end product
IPTA/IPTS adoption of CCLR as learning reference
Memorandum of Understanding (MoU) with the following nine (9) higher learning institutions was held on 27 March 2018 in conjunction with ICW 2018: UM, UITM, USM, UTM, SEGI U, UTAR, TAR UC, University Of Reading Malaysia, and. Taylors University. INTI International Universities, IIUM and Jabatan Pendidikan Politeknik Malaysia are finalizing their MoU document with legal office.
QUALITY, SAFETY & PROFESSIONALISM
KPI Q3-024
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 26
2016 Weightage : 40% | 2017 Weightage : 15% | 2018 Weightage : 15% | 2019 Weightage : 15% | 2020 Weightage : 15%
CITP portal launched | CITP portal updated and maintained 40,000 unique users on CITP portal captured | CITP portal updated and maintained 40,000 unique users on CITP portal captured | CITP portal updated and maintained 40,000 unique users on CITP portal captured | CITP portal updated and maintained 40,000 unique users on CITP portal captured
SPONSOR Sr Sariah Abd Karib
OWNER Noryani Ismail
OIC Noraini Mohd Fadzil
KPI LEADER CIDB
KPI DESCRIPTION One stop portal on CITP with 40,000 unique users annually beginning 2017
INITIATIVE Q4 - Promote and raise awareness of CITP initiatives
SUB-INITIATIVE -
This KPI is under the purview of IWG5.
CITP portal launched
The CITP portal was launched on 4 November 2016 during the CIDB Industry Appreciation Night.
CITP portal updated and maintained
The CITP portal is regularly being maintained and updated. The latest information updated as follows:
CITP Report Q2 2017
CITP Q3 2017 scorecard
Latest news and events on CITP
Membership of CITP committees
Other relevant CITP content
Unique Users
The statistics are as follows :
QUALITY, SAFETY & PROFESSIONALISM
KPI Q4-025
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
 | 2017 | 2018 | 2019
Target | 40,000 | 40,000 | 40,000
Achievement | 43,514 | 12,413 (Q2 2018) | -
Achievement % | 108% | 31% | -

## Slide 27
2016 Weightage : 18% | 2017 Weightage : 22% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
30 event platforms used to promote CITP | 30 event platforms used to promote CITP | 30 event platforms used to promote CITP | 30 event platforms used to promote CITP | 30 event platforms used to promote CITP
SPONSOR Sr Sariah Abd Karib
OWNER Noryani Ismail
OIC Noraini Mohd Fadzil
KPI LEADER CIDB
KPI DESCRIPTION CITP promoted in 30 industry/CIDB event platforms annually beginning 2016
INITIATIVE Q4 - Promote and raise awareness of CITP initiatives
SUB-INITIATIVE -
This KPI is under the purview of IWG5.
Event platforms to promote CITP :
The statistics of event platforms conducted are as follows:
In Q2 2018, a total of 4 events were organized as follows:
QUALITY, SAFETY & PROFESSIONALISM
KPI Q4-026
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
No | Events | Date | Venue
1. | Majlis Perasmian CIDB Convention Centre Sarawak | 27 April 2018 | Kuching, Sarawak
2. | Bengkel Pengurusan Projek Kontraktor Binaan dan Majlis Penyampaian Sijil Personel Belia di Daerah Papar | 5 May 2018 | Papar, Sabah
3. | Majlis Penyerahan Projek Pembinaan Semula Tabika KEMAS, Kampung Kudei Baru, Kuching Sarawak | 8 May 2018 | Kampung Kudei Baru, Kuching, Sarawak
4. | Sesi Taklimat Serta Perbincangan Meja Bulat Program Akreditasi Pekerja Mahir dan Penyelia Tapak Binaan CIDB Pulau Pinang Bagi Tahun 2018 | 26 Jun 2018 | Eastin Hotel, Pulau Pinang
 | 2016 | 2017 | 2018 | 2019 | 2020
Target | 30 | 30 | 30 | 30 | 30
Achievement | 47 | 71 | 43 (Q2 2018) |  | 
Achievement % | 156% | 236% | 143% |  | 

## Slide 28
2016 Weightage : 50% | 2017 Weightage : 40% | 2018 Weightage : 4% | 2019 Weightage : 3% | 2020 Weightage : 3%
5 strategic partnership sealed | 5 strategic partnership sealed | 5 strategic partnership sealed | 5 strategic partnership sealed | 5 strategic partnership sealed
SPONSOR Sr Sariah Abd Karib
OWNER Noryani Ismail
OIC Noraini Mohd Fadzil
KPI LEADER CIDB
KPI DESCRIPTION 5 strategic partnerships secured annually between CIDB and key private/public organisations towards achieving CITP targets
INITIATIVE Q4 - Promote and raise awareness of CITP initiatives
SUB-INITIATIVE -
This KPI is under the purview of IWG5.
Strategic Partnerships Sealed :
The statistics on strategic partnerships sealed are as follows :
The list of strategic partnerships sealed in 2016 and 2017 between CIDB and key private/public organisations can be accessed via CITP portal at www.citp.my
Strategic Partnership via Memorandum of Understanding was signed with the following organisations in 2018 :
Perbadanan Produktiviti Malaysia (MPC), 6 Feb 2018, Olive Tree Hotel, Bayan Lepas, Pulau Pinang
Persatuan Kontraktor Perumahan Kelantan (PKPK) dalam Penggunaan IBS, 25 Feb 2018, Perdana Hotel, Kota Bharu, Kelantan (with CIDB MyIBS)
University of Reading Malaysia in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
Universiti Teknologi Malaysia in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
Universiti Sains Malaysia in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
Universiti Malaya in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
University Tunku Abdul Rahman in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
SEGi University in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
Universiti Teknologi MARA in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
Taylor's University in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
Tunku Abdul Rahman University College in MyCESMM, 27 March 2018, Exhibition Hall 4, KLCC
QUALITY, SAFETY & PROFESSIONALISM
KPI Q4-027
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
 | 2016 | 2017 | 2018 | 2019 | 2020
Target | 5 | 5 | 5 | 5 | 5
Achievement | 11 | 7 | 11 (Q2 2018) |  | 
Achievement % | 220% | 140% | 220% |  | 

## Slide 29
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
PR value of RM 20Mn achieved | PR value of RM 20Mn achieved | PR value of RM 20Mn achieved | PR value of RM 20Mn achieved | PR value of RM 20Mn achieved
SPONSOR Sr Sariah Abd Karib
OWNER Noryani Ismail
OIC Noraini Mohd Fadzil
KPI LEADER CIDB
KPI DESCRIPTION Public relation (PR) value on media coverage involving industry captains of at least RM20m achieved annually beginning 2016
INITIATIVE Q4 - Promote and raise awareness of CITP initiatives
SUB-INITIATIVE -
This KPI is under the purview of IWG5.
The Public Relation (PR) value is derived from the numbers of news published in the mass media namely television, radio, newspapers, magazine, newsletters and other print publications. The PR Value is calculated by an appointed media monitoring agency (ISENTIA (M) Sdn Bhd), who monitored the media coverage regularly and reported to CIDB quarterly or whenever required.
PR Value Achieved :
The statistics on PR value achieved are as follows :
QUALITY, SAFETY & PROFESSIONALISM
KPI Q4-028
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
 | 2016 | 2017 | 2018 | 2019 | 2020
Target | RM20Mn | RM20Mn | RM20Mn | RM20Mn | RM20Mn
Achievement | RM38Mn | RM48Mn | RM78.22Mn (Q2 2018) |  | 
Achievement % | 190% | 240% | 391% |  | 

## Slide 30
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
7 million users reached on Social Media | 7 million users reached on Social Media | 7 million users reached on Social Media | 7 million users reached on Social Media | 7 million users reached on Social Media
SPONSOR Sr Sariah Abd Karib
OWNER Noryani Ismail
OIC Noraini Mohd Fadzil
KPI LEADER CIDB
KPI DESCRIPTION CITP communications on Social Media reach 7 million users annually
INITIATIVE Q4 - Promote and raise awareness of CITP initiatives
SUB-INITIATIVE -
This KPI is under the purview of IWG5.
This KPI has been enhanced by IWG5 from the target of 3Mn to a new target of 7Mn beginning 2017.
Users Reached On Social Media :
The statistics on users reached on social media are as follows :
QUALITY, SAFETY & PROFESSIONALISM
KPI Q4-029
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
 | 2016 | 2017 | 2018 | 2019 | 2020
Target | 3Mn | 7Mn | 7Mn | 7Mn | 7Mn
Achievement | 7.3Mn | 7.1Mn | 5.6Mn (Q2 2018) |  | 
Achievement % | 243% | 101% | 80% |  | 

## Slide 31
2016 | 2017 Weightage : 10% | 2018 Weightage : 35% | 2019 Weightage : 35% | 2020 Weightage : 20%
 | 3 pilot projects for the implementation of Gerbang Nilai identified. Study on the implementation of Gerbang Nilai in previous projects completed | All 3 pilot projects assessed by Gerbang Nilai No.1 (Planning Phase), Gerbang Nilai No.2 (Design Phase), and Gerbang Nilai No.3 (Tender Phase) | All 3 pilot projects assessed by Gerbang Nilai No.4 (Hand Over Phase) | JKR to submit report on the use of Gerbang Nilai for all public projects to KKR for onward submission to MoF ‘s enforcement. All public projects adopted Gerbang Nilai by Q4 2020
SPONSOR Sr Sariah Abd Karib
OWNER Haslina Abdul Halim
OIC Nur Hafizah Mohd Nor
KPI LEADER JKR
KPI DESCRIPTION All public projects to adopt Gerbang Nilai by Q4 2020
INITIATIVE Q5 - Enhance Integrity and Increase Governance
SUB-INITIATIVE -
QUALITY, SAFETY & PROFESSIONALISM
KPI Q5-130
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG19
Gerbang Nilai is an adaption of the United Kingdom’s Office of Government Commerce’s Gateway Review Study which provides advice on the progress and likely success of the delivery of major projects. There are 4 phases of the Gerbang Nilai assessment as follows :-
Phase 1 – Planning Phase
Phase 2 – Design Phase
Phase 3 – Tender Phase
Phase 4 – Hand Over Phase
Pilot Projects
Each of the 3 pilot projects identified has the construction period of under two years to enable the projects to undergo the complete cycle of the 4 phases of Gerbang Nilai. The 3 pilot projects are as follows :-
Projek Menaiktaraf Blok Asrama di Institut Kemajuan Desa (Infra) Bangi
Pembinaan Dua Blok Bangunan Tambahan 24 bilik Darjah di SJKC Kay Sin, Seberang Perai Tengah, Pulau Pinang
Cadangan Menaiktaraf Kemudahan Asas, Infrastruktur dan Utiliti di Pulau Besar dan Pulau Pemanggil, Johor
Assessment of Pilot Projects :
Study on the implementation of Gerbang Nilai
The study on the past implementation of Gerbang Nilai was completed and presented on 19 Dec 2017 during IWG19 meeting. The study was carried out by JKR for a period of 10 months from February until December 2017. The objective of the study was to strengthen the delivery system of JKR projects. The findings confirmed the low application of Gerbang Nilai in JKR projects was primarily due to its non-mandatory requirements on its use.
Phase | Asrama (Bangi) | SJKC Kay Sin (P.Pinang) | Infrastruktur (P. Pemanggil)
Phase 1 – Planning | Completed | Completed | Completed
Phase 2 – Design | Completed | Completed | Completed
Phase 3 – Tender | Completed | Completed | Completed
Phase 4 – Hand Over | By 13 November 2019 | By 11 June 2020 | By 18 August 2019

## Slide 32
2016 | 2017 Weightage : 5% | 2018 Weightage : 30% | 2019 Weightage : 35% | 2020 Weightage : 30%
 | Feasibility study on National Works Procurement System (WPS) for Public Projects completed | National Works Procurement System (WPS) developed | National Works Procurement System (WPS) developed | National Works Procurement System (WPS) developed
SPONSOR Sr Sariah Abd Karib
OWNER Haslina Abdul Halim
OIC Nur Hafizah Mohd Nor
KPI LEADER KKR
KPI DESCRIPTION National Works Procurement System (WPS) completed by 2020
INITIATIVE Q5 - Enhance Integrity and Increase Governance
SUB-INITIATIVE -
QUALITY, SAFETY & PROFESSIONALISM
KPI Q5-131
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG19.
National Works Procurement System (WPS) is a centralized databse system designed to manage the procurement of all public construction projects. The system is aimed at achieving efficiency and a measure of transparency in public works procurement. Authorised parties will also be able to access an up-to-date progress of a construction works.
Feasibility study on National Works Procurement System (WPS)
The study was conducted by KPMG PLT. The study commenced on 4 Dec 2016 and was completed on 30 June 2017. The objective of the study was to develop a framework for an online procurement system that would effectively and efficiently manage end-to-end project delivery processes.
The study was presented to the Ketua Setiausaha Negara (KSN) through Jawatankuasa Perancang Pembangunan Negara (JPPN) on 8 Nov 2017 for the procurement and implementation of WPS.
Further to this, additional scope was identified to enhance the study which is scheduled to commence later. Application for additional budget to proceed with the study was requested from Ministry of Finance. KKR is still awaiting its approval.
National Works Procurement System (WPS)
The development of the National Works Procurement System will commence after the above study is completed.

## Slide 33
2016 | 2017 Weightage : 15% | 2018 Weightage : 15% | 2019 Weightage : 30% | 2020 Weightage : 40%
 | Adoption of ISO 37001 (ABMS) as Malaysian Standard completed by Q4 | At least 1 Certification Body for ISO 37001 /MS ISO 37001 accredited by DSM by Q3 2018 4 promotional events/ seminar to promote MS ISO 37001 (ABMS) conducted at 4 states by Q4 2018 | 4 construction related organizations / PBT certified with ISO 37001 /MS ISO 37001 | 6 construction related organizations / PBT certified with ISO 37001/MS ISO 37001
SPONSOR Sr Sariah Abd Karib
OWNER Haslina Abdul Halim
OIC Nur Hafizah Mohd Nor
KPI LEADER DSM
KPI DESCRIPTION 10 construction related organizations/ PBT to be certified with ISO 37001 /MS ISO 37001 (Anti Bribery Management System) by Q4 2020
INITIATIVE Q5 - Enhance Integrity and Increase Governance
SUB-INITIATIVE -
QUALITY, SAFETY & PROFESSIONALISM
KPI Q5-132
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG19
ISO 37001 (Anti Bribery Management System) was developed by ISO Technical Committee and published in Oct 2016.
Adoption of ISO 37001 (Anti Bribery Management System) as a Malaysian Standard was approved by the Ministry of Science, Technology and Innovation on 17 Oct 2017 and was subsequently launched on 27 Oct 2017 at Putrajaya. Department of Standard Malaysia together with CIDB will be promoting this Malaysian Standard starting from Q1 2018 onwards.
Certification Body accredited by DSM
Standards Malaysia has successfully carried out a public comment on the additional criteria prepared by Suruhanjaya Pencegahan Rasuah Malaysia (MACC). Comments from 58 entities involving 44 certification bodies (36 accredited CBs and 8 applicants) and 14 assessors were obtained. Those feedback and comments were submitted to MACC on 17 May 2018 for their further action. According to MACC, it needs to be referred to their legal adviser prior to be used for accreditation purposes.
MACC is in the final stage of finalizing the additional criteria and training modules for certification bodies. Once completed, Department of Standard Malaysia will start the process of accrediting SIRIM as a certified Certification Body.
Promotional events/seminar to promote MS ISO 37001
A seminar was conducted on 26 Apr 2018 to promote MS ISO 37001 at Pullman KLCC Hotel & Residences where 60 participants attended.
3 more events have been identified to promote MS ISO 37001 (Anti Bribery Management System) to the industry players. The dates and venues are as follows :-
27 August 2018 – KSL Resort, Johor Bahru
19 September 2018 – Cititel Hotel, Penang
29 October 2018 – Concorde Hotel, Shah Alam

## Slide 34
2016 Weightage : 80% | 2017 Weightage : 20% | 2018 | 2019 | 2020
Sustainability assessment on 2 pilot projects using CEEQUAL identified | Sustainability assessment on 2 pilot projects using CEEQUAL completed |  |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 2 Projects piloted for infrastructure sustainability rating using CEEQUAL by 2017
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
ENVIRONMENTAL SUSTAINABILITY
KPI E1-030
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG6.
CEEQUAL (Civil Engineering Environmental Quality Assessment & Award Scheme), ENVISION and other infrastructure sustainability rating tools were benchmarked by USM from Feb – May 2016 to analyse the benefits, cost comparison and suitability of the tools to be used in the Malaysian construction industry. The objective of this study are:
Benchmark available sustainable infrastructure rating tools worldwide.
Benchmark and compare selected available sustainable infrastructure rating tools worldwide.
Categorise strengths and weaknesses of sustainable infrastructure rating tools assessed.
After conducting the study, CEEQUAL was chosen as fundamental towards the development of Malaysia Infrastructure Sustainable Rating Tool based on its broad applicability and adoptability in the global perspective.
These two (2) pilot infrastructure sustainability assessments were performed to test the suitability of CEEQUAL in Malaysia :
West Coast Expressway (WCE) Section 4 by IJM Construction
DUKE Phase 3 by Ekovest
IWG6 Meeting No.3 on 26 May 2017 approved the assessment report that concluded CEEQUAL is suitable for the development of the Malaysia sustainable infrastructure rating tool.
The infrastructure sustainability assessments using CEEQUAL for the 2 pilot projects were completed in June 2017.
This KPI is 100% achieved.

## Slide 35
2016 | 2017 Weightage : 100% | 2018 | 2019 | 2020
 | 16 CEEQUAL assessors trained and accredited |  |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 16 assessors being trained in CEEQUAL by Q2 2017
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
This KPI is under the purview of IWG6.
In order to test CEEQUAL for use in Malaysia, it is critical to have qualified assessors to test the tool. The criteria for the selection of assessors are background in build environment, construction and engineering. 16 assessors were trained by CEEQUAL for 3 days in March 2017. Below are the list of CEEQUAL assessors trained :
Ir. Chua Soo Kok (DUKE)
Ir. Mohd Zaini Abu Hassan (Green Tech Malaysia)
Ir. Md Zarulazam Md Eusofe - Konsortium Lebuhraya Utara- Timur (KL) SdnBhd
Khoo Sik Khui (IJM Corporation)
S. Ramesh A/L V. Subramaniam (IJM Corporation)
Timothy Pang - Konsortium Lebuhraya Utara- Timur (KL) SdnBhd
Yuvabalan A/L Govindasamy (CAST JKR)
Ab Halim Hussein (IJM Corporation)
Dr. Farid Ezanee Mohamed Ghazali (USM)
Dr. Mohd Rosli (USM)
Dr. Rozana Zakaria (UTM)
Zuraihi Abd Ghani (CIDB)
Emasria Ismail (CIDB- MAMPAN)
Noor FazierahYaakub (CIDB)
Fuhairah Ahmad Fuad (CIDB)
Norzaidi Nordin (CIDB-MAMPAN)
All the trained 16 CEEQUAL Assessors were appointed as Technical Committee members for the development of Malaysia Sustainable Infrastructure Rating Tool. The appointment starts from January 2018 until the completion of the Rating Tool.
This KPI is 100% achieved.
ENVIRONMENTAL SUSTAINABILITY
KPI E1-031
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 36
2016 Weightage : 30% | 2017 Weightage : 10% | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020
1st batch of 3 qualifying research partnerships approved 1st batch of 3 research MOU signed | 4 R&D topics identified 100% R&D commenced Board of Advisory under CREAM established | Hazard map, risk map & risk assessment on flood for critical infrastructure established Hazard map, risk map & risk assessment on land slide for critical infrastructure established Guidelines for construction on peat & organic soil in Malaysia improved Roadmap on Peat and Organic Soils in Malaysian Construction Industry established | Guidelines for flood assessment of Critical Infrastructure in specified areas established Guidelines for land slide assessment of Critical Infrastructure in specified areas established | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION At least 3 sustainable R&D by MAMPAN completed by Q4 2019
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
This KPI is under the purview of IWG6.
Four (4) qualifying research partnerships with Universiti Malaya (UM), Universiti Sains Malaysia (USM), Universiti Teknologi Malaysia (UTM) and Universiti Kebangsaan Malaysia (UKM) were approved and MoU signed.
Sustainable Excellence Centre (MAMPAN) launched on 1 Dec 2016 is a unit under Construction Research Institute of Malaysia (CREAM) as a reference center for sustainable construction and development. Later on 20 Feb 2017, the Research Advisory Council (RAC) also under CREAM was established to advise on the research areas. From the Five (5) topics identified by RAC, 4 topics were enhanced & endorsed by the Board of Trustee (BOT) of CREAM. The 4 topics that are managed by MAMPAN are as follows :
ENVIRONMENTAL SUSTAINABILITY
KPI E1-032
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
R&D Title | Start | End | Output | Progress
Development of Flood Risk Assessment (FRA) and Flood Vulnerability Index (FVI) for Critical Infrastructure (CI) in Malaysia | Dec 2017 | Dec 2019 | Flood risk map, FVI for CI, Flood & development zoning and guidelines of FVI for critical infrastructure (CI) | Content manual guidelines was revised according to the latest template from PLANMalaysia. GIS process of FVI and flood hydrodynamic model of the study area in Kelantan and Penang being develop. The flood data (DTM, flood model, and flood hazard map) obtained from JPS Malaysia. Technical Working Group held 3 meetings to monitor and comment on the development of R&D. 40% progress on track
Guidelines for Landslides Vulnerability Assessment for Critical Infrastructure (CI) in Malaysia (Parameters, Vulnerability Index, Risk Index, Vulnerability Assessment) | Dec 2017 | Dec 2019 | Parameters for landslides vulnerability assessment and risk index for CI, landslides vulnerability assessment, risk index for CI, guidelines for landslides vulnerability assessment and risk index for CI | Content manual guidelines was revised according to the latest template from PLANMalaysia. Characterization of critical element-at-risk mapped. The vulnerability determination for identified CI has been addressed. Technical Working Group held 3 meetings to monitor and comment on the development of R&D. 45% progress on track.
Review on Adequacy of Guidelines for Construction on Peat & Organic Soils in Malaysia | Dec 2017 | June 2018 | Reviewed Guidelines on Peat Soils | Guidelines for construction on Peat soils was completed on 30 June 2018. 100% completed.
Geotechnical Engineering on Peat & Organic Soils in Malaysian Construction Industry Roadmap | Dec 2017 | Dec 2018 | Implementation strategy for the Roadmap | Technical Working Group committee has been identified. Workshop on identification of research themes and titles was held on 22 Feb 2018. Term & Condition for the appointment of consultant has been finalized and RFP was called in May 2018. The appointment of the consultant is expected to be finalized by Aug 2018. 45% progress on track.
2 years period
2 years period
7 mths period
12 mths period

## Slide 37
2016 | 2017 Weightage : 20% | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020 Weightage : 20%
 | 1st Draft of Malaysia sustainability infrastructure rating tool completed by Q4 2017 4 pilot infrastructure projects identified for sustainability rating | 4 infrastructure projects piloted using Malaysia sustainability infrastructure rating tool Stakeholder engagement to refine sustainability infrastructure rating tool conducted Malaysia sustainability infrastructure rating tool finalised by Q4 2018 | Malaysia sustainability infrastructure rating tool adopted for government projects Report on adoption of Malaysia sustainability infrastructure rating tool produced | Cabinet paper/ Circular on adoption Malaysia sustainability infrastructure rating tool for public projects submitted
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION Malaysia environmental sustainability rating tool for infrastructure projects established by 2018
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG6.
First Draft of Malaysia Sustainability Infrastructure Rating Tool
The draft of Malaysia Sustainability Infrastructure Rating Tool was developed and finalised by USM in Dec 2017 and ready to be tested for viability in 2018.
Sustainable Infrastructure Rating Tool Task Force Committee chaired by CIDB agreed on four (4) types of infrastructure projects to be piloted for Malaysia Sustainability Infrastructure Rating Tool. They are :
Highway Project
Jetty / Port Project
Dam Project
Utility Services Project
Infrastructure Projects Piloted Using Malaysia Sustainability Infrastructure Rating Tool
The four (4) infrastructure projects piloted for Malaysia Sustainability Infrastructure Rating Tool and its assessment results are as follows :
ENVIRONMENTAL SUSTAINABILITY
KPI E1-118
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
TYPE OF INFRASTRUCTURE | PROJECTS | DESIGN SCORE (%) | CONS. SCORE (%)
Highway | Projek Setia Pantai – Express way (DUKE 3) |  | NA
Sewerage Treatment Plant | Loji Rawatan Kumbahan Serantau & Rangkaian Paip Pembentungan, Bandar Indera Mahkota, Kuantan Pahang | 54.99 | NA
Dam | Pembinaan Empangan Kahang, Kluang | 33.81 | 2.5
Utility Services | Projek Penghantaran 132:33kV (PMU) Bukit Nanas, Sandakan Sabah | 43.62 | NA
Stakeholder engagement to refine sustainability infrastructure rating tool :
From the result of the pilot projects, industry engagement was held on 8 June 2018 involving 30 experts and industry players from various background including SME’s to review and comment the draft on sustainable infrastructure rating tool. Some minor refinement were made to the document.
Malaysia sustainability infrastructure rating tool finalized :
The Malaysia sustainability infrastructure rating tool is 80% completed and expected to be finalized by Q4 2018.

## Slide 38
2016 | 2017 | 2018 | 2019 Weightage : 60% | 2020 Weightage : 40%
 |  |  | Malaysia sustainability infrastructure rating tool training modules developed | 25 trainers on Malaysia sustainable infrastructure rating tool trained and certified
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 25 trainers certified in Malaysia environmental sustainability rating tool by Q4 2019
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
This KPI is under the purview of IWG6 and was initially targeted to commence in 2018. However due to delay in the completion of Malaysia Sustainability Infrastructure Rating Tool, the target is now rescheduled to commence in 2019.
Development of training modules will commence after the completion of Malaysia Sustainability Infrastructure Rating Tool under KPI E1-118.
ENVIRONMENTAL SUSTAINABILITY
KPI E1-119
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 39
2016 Weightage : 40% | 2017 Weightage : 20% | 2018 Weightage : 40% | 2019 Weightage : 0% | 2020 Weightage : 0%
70% Study on building rating tools in Malaysia completed by Q4 2016 | 100% Study on building rating tools in Malaysia completed by Q4 2017 | Study on building rating tools in Malaysia published by Q1 2018 |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION Building rating tools available in Malaysia analysed and indexed for industry reference and utilization by Q4 2018
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This KPI is under the purview of IWG6.
Study on Analysing and Indexing Building Rating Tools in Malaysia was completed by CREAM in March 2017.
The aim of the study is to ease the industry in selecting the best sustainability rating tool to be implemented in building projects by providing analysis on all sustainability building rating tools in Malaysia.
The study analysed 6 currently available sustainability building rating tools in Malaysia as follows:
MyCREST (CIDB)
Green PASS (CIDB)
Penarafan Hijau (PH-JKR)
Green Building Index (GBI)
GreenRE (REHDA)
IRDA-CASBEE (IRDA)
The outcome of the study was presented to IWG6 in August 2017 and endorsed by TWG2 on 30 Jan 2018. It was published on 30 March 2018.
This KPI is 100% achieved.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-037
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 40
2016 Weightage : 0% | 2017 Weightage : 0% | 2018 Weightage : 30% | 2019 Weightage : 35% | 2020 Weightage : 35%
 |  | Guideline for the implementation of MS 1525 established Engagement session to all states on adoption of MS 1525 conducted Training Module on MS 1525 developed | Training on MS 1525 to 6 states conducted 3 Training on MS 1525 to stakeholders conducted Report on adoption of MS 1525 by all states Requirements of MS 1525 as a condition for building plan approval implemented by 10 local authorities | Training on MS 1525 to 6 states conducted 3 Training on MS 1525 to stakeholders conducted Report on adoption of MS 1525 by all states Requirements of MS 1525 as a condition for building plan approval implemented by 10 local authorities
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER JKT
KPI DESCRIPTION By Law No. 38A on Energy Efficiency Implemented by 20 Local Authorities by Q4 2020
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This KPI is under the purview of IWG6.
The original KPI was ‘UBBL No.38A on Energy Efficiency gazetted for all states by Q4 2020’. Since its endorsement by MNKT in 2012, only 3 states (Penang, Selangor & Terengganu) had gazetted it. Due to the slow uptake by other states in gazetting UBBL No.38A, TWG2 had endorsed the amendment to the KPI on 30 Jan 2018. The revised KPI is 'By Law No 38A on Energy Efficiency Implemented by 20 Local Authorities by Q4 2020'.
Guideline on Implementation of MS 1525
JKT is in the process of preparing the guideline for MS 1525. CIDB provided guideline samples to JKT which were jointly developed by the industry players to be used by JKT as reference document in their development process of the above guideline. The planning for the implementation of MS 1525 on targeted Local Authorities was developed.
Engagement Session on Adoption of MS 1525
The engagement sessions with all states will be initiated by JKT after the completion of the guideline. The first engagement session is scheduled to be held on 9 July 2018.
Training Module on UBBL No 38A
The module will be developed in parallel with the above guideline.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-039
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 41
2016 | 2017 | 2018 Weightage : 30% | 2019 Weightage : 35% | 2020 Weightage : 35%
 |  | 2 awareness programs on ISO14001 to 4 and 5 Star (Rated under SCORE) Contractors 30% of 4 and 5 Star (Rated under SCORE) Non-Certified ISO 14001:2015 Contractors being certified with ISO 14001:2015 | 2 awareness programs on ISO14001 to 4 and 5 Star (Rated under SCORE) Contractors 70% of 4 and 5 Star (Rated under SCORE) Non-Certified ISO 14001:2015 Contractors being certified with ISO 14001:2015 | 2 awareness programs on ISO14001 to 4 and 5 Star (Rated under SCORE) Contractors 100% of 4 and 5 Star (Rated under SCORE) Non-Certified ISO 14001:2015 Contractors being certified with ISO 14001:2015
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 70% of 4 and 5 Star (Rated under SCORE) Non-Certified ISO 14001:2015 Contractors being certified with ISO 14001:2015 by 2020
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This is a new KPI under the purview of IWG6 commencing in 2018.
Awareness Program
One workshop was conducted on 14 May 2018 to raise awareness on ISO 14001:2015 EMS to 8 contractors. Another awareness workshop is scheduled to be conducted on 25 July 2018 which will be participated by at least 18 contractors.
4 and 5 Star SCORE Rated Contractors Certified With ISO 14001:2015
By Q2 2018, the statistics of 4 and 5 star SCORE rated contractors certified with ISO 14001:2015 are as follows :
Contractors are expected to attend the DIY ISO14001:2015 certification program after attending the awareness course.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-135
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SCORE | No. of Contractors | Certified With ISO 14001:2015 | Non-Certified With ISO 14001:2015 | 2018 Target (30%) | Q2 2018 Achievement
4 Star | 52 | 31 | 21 | 6 | 0
5 Star | 7 | 7 | 0 | - | -

## Slide 42
2016 | 2017 Weightage : 25% | 2018 Weightage : 25% | 2019 Weightage : 25% | 2020 Weightage : 25%
 | 50 MyCREST Qualified Professionals accredited | 100 MyCREST Qualified Professionals accredited | 100 MyCREST Qualified Professionals accredited | 100 MyCREST Qualified Professionals accredited
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 350 MyCREST qualified professionals accredited by Q4 2020
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG6.
MyCREST stands for Malaysia Carbon Reduction and Environmental Sustainability Rating Tool. MyCREST Qualified Professionals are the personnel accredited by CIDB whose role is to facilitate the industry in adopting MyCREST in building construction projects.
MyCREST Qualified Professionals Accredited :
The statistics of MyCREST Qualified Professionals Accredited are as follows :
As of 2017, there were 164 accredited MyCREST Qualified Professionals of which 133 are representative from government agencies and 31 are representative from private sectors, academicians and associations.
As of Q2 2018, 3 training courses were conducted as follows :
Out of 101 participants who attended the above courses, 91 passed the MyCREST QP Exam. The accreditation for qualified candidates are expected to be completed in Q4 2018.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-120
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
DATE | COLLABORATION | NO. OF PARTICIPANTS
13-15 Mar 2018 | JKR Putrajaya | 35
10-12 April 2018 | JKR Putrajaya | 34
17-19 April 2018 | Open to public | 32
Total |  | 101
 | Prior 2016 | 2017 | 2018 | 2019 | 2020
Target | - | 50 | 100 | 100 | 100
Achievement | 55 | 109 | 91 (Q2 2018) | - | 
Achievement % | - | 218% | 91% | - | 

## Slide 43
2016 | 2017 Weightage : 20% | 2018 Weightage : 40% | 2019 Weightage : 20% | 2020 Weightage : 20%
 | 25 Assessors Accredited | 25 Assessors Accredited MyCREST enhanced | 25 Assessors Accredited | 25 Assessors Accredited
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 100 MyCREST assessors (MA) accredited by Q4 2020
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG6.
Malaysia Carbon Reduction and Environmental Sustainablity Rating Tool (MyCREST) Assessors are personnel accredited by CIDB whose role is to assess building construction projects using MyCREST. Only MyCREST Qualified Professionals are eligible to become MyCREST Assessors (MA).
Assessors Accredited
The statistics of MA accredited are as follows :
As of 2017, there were 59 MA accredited of which 51 are representative from government agencies and 8 are representative from private sectors, academicians and associations.
For 2018, the arrangement to accredit all 25 Assessors is expected to be held on 15 – 16 August 2018.
MyCREST Enhanced
The consultant to enhance MyCREST was appointed in May 2018. A workshop with projects that adopted MyCREST was conducted on 5 June 2018 to gain feedback for Design and Construction Stage. The same session was conducted on 11 June 2018 for Operation and Maintenance Stage. The Calculator review workshop was conducted on 21 June 2018. The output of all sessions were presented to CIDB on 29 June 2018.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-121
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
 | Prior 2016 | 2017 | 2018 | 2019 | 2020
Target | - | 25 | 25 | 25 | 25
Achievement | 30 | 29 | 0 (Q2 2018) | - | 
Achievement % | - | 116% | - | - | 

## Slide 44
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
Sustainable specification completed by JKR 3 pilot projects for the implementation of sustainable specification identified by JKR | Sustainable specification in pilot projects implemented Status on the implementation of sustainable specification in procurement for public building and infrastructure reported | Report on sustainable specification (GPSS Design Score) in procurement for public building and infrastructure issued | Report on sustainable specification (GPSS Construction Score) in procurement for public building and infrastructure issued | Final report on sustainable specification in procurement for public building and infrastructure issued Circular on implementation of sustainable specification in procurement for public building and infrastructure issued by MOF
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER MOF
KPI DESCRIPTION Sustainable specification mandated in procurement for public buildings/ infrastructure by Q4 2020
INITIATIVE E3-Focus on public projects to lead the charge on sustainable practices
SUB-INITIATIVE -
This KPI is under the purview of IWG7.
Report On Sustainable Specification In Procurement For Public Building
Sustainable specification was included in the contract document for the three (3) pilot projects under JKR in 2016. The Green Product Scoring System (GPSS) was used to measure the percentage of green products used in these projects and the respective cost in monetary value.
Status report on the projects are as follows :
1) Pusat pengajian pengurusan pelancongan Hospitaliti dan Alam Sekitar UUM Colgis
GPSS Score : 1 Star
GPSS design score is 45.78% (1 Star). The Report on GPSS Design Score was submitted to CIDB on 25 April 2018.
2) Fakulti pendidikan teknikal dan vokasional di kampus UPSI Teluk Intan Fasa 2- Bangunan
GPSS Score : Assessment is on-going
MyCREST and GPSS workshop on the design score is scheduled on 4 July 2018 by Head of Project Team, HOPT Cawangan Kerja Pendidikan.
3) Pusat Latihan Keselamatan Perlindungan Malaysia (PLKPM) Bandar Baru Enstek, N.Sembilan
GPSS Score : Assessment is on-going
GPSS workshop for the project has been highlighted in the GGP Committee Meeting on 26 Jun 2018.
In addition, these pilot projects will be used as a reference to develop the Guideline on Government Green Procurement (GGP) for Works. The GGP Guideline for works will be issued by MoF to mandate sustainable specification for public projects as the final outcome by 2020.
ENVIRONMENTAL SUSTAINABILITY
KPI E3-041
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 45
2016 | 2017 | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020 Weightage : 40%
 |  | Status report on 2017 CO2 reduction in new public buildings published | Status report on 2018 CO2 reduction in new public buildings published | Status report on 2019 CO2 reduction in new public buildings published Study on achievement of carbon reduction published
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 6% CO2 emission reduction in new public buildings exceeding RM50Mn by 2020
INITIATIVE E3-Focus on public projects to lead the charge on sustainable practices
SUB-INITIATIVE -
This is a new KPI under the purview of IWG7 commencing in 2018.
Status report on 2017 CO2 reduction in new public buildings :
CO2 emission reduction in new public buildings exceeding RM50Mn by 2020 will be calculated using MyCREST assessment. The assessment was conducted in 2017 and its report published in 2018. Only 1 public project that is Menara KKR2 was assessed in 2017. Menara KKR2 was designed to emit 6302.22 ktCO2e/year and it achieved 64% CO2 emission reduction from its conventional design.
The report is expected to be published by Q4 2018.
2018 CO2 reduction in new public buildings Status Report :
MyCREST assessment on public buildings for 2018 is on going.
ENVIRONMENTAL SUSTAINABILITY
KPI E3-136
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 46
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 10% | 2019 Weightage : 30% | 2020 Weightage : 20%
Green technology tax incentives GITA and GITE mechanism established | Study on the potential of green incentives completed 2 companies benefitted from green incentive 5 promotional activities/programs on green incentives | Stakeholder engagements on the outcome of the study conducted 5 companies benefitted from green incentives 5 promotional activities/programs on green incentives conducted | Recommendations to the Government on the new green incentives 7 companies benefitted from green incentives 5 promotional activities/programs on green incentives conducted | New/ improved green incentives mechanism introduced 10 companies benefitted from green incentives 5 promotional activities/programs on green incentives conducted
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER KeTTHA
KPI DESCRIPTION At least 10 companies benefitted from green incentive for sustainable buildings by Q4 2020
INITIATIVE E4-Facilitate industry adoption of sustainable practices
SUB-INITIATIVE -
This KPI is under the purview of IWG7.
Study on the potential of green incentives
IIUM had completed the study on the potential green incentives in Aug 2017 and the report was submitted to KeTTHA for evaluation on Nov 2017. The study concluded these 10 potential green incentives are suitable to be applied in Malaysia for all stakeholders :
Investment Tax Incentive
Production Tax Incentive
Property Tax Incentive
Value Added Tax (VAT) Reduction
Excise Tax Reduction
Import Duty Reduction
Accelerated Depreciation
R&D Tax Incentive
Tax Holiday
Tax on Conventional Fuels
Guideline for Green Technology Tax Incentive was published by MGTC. 3 types of available tax incentive offered specially to the construction industry are :
1. Green Investment Tax Allowance for Projects (GITA-Project & Assets)
2. Green Income Tax Exemption (GITE) for green technology services
3. MyCREST
ENVIRONMENTAL SUSTAINABILITY
KPI E4-045
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Stakeholder engagements on the outcome of the study :
Engagement with Stakeholder to discuss on the outcome of the study is expected to be held in Q3 2018.
Companies Benefitted From Green Incentives
These six (6) companies have benefitted from Green Income Tax Exemption (GITE) Green Building :
1) DME Solutions Sdn Bhd
2) Exergy CX Sdn Bhd
3) Fenestra Green Sdn Bhd
4) Love Way Avenue Sdn Bhd
5) Green Urban Matters Solution Sdn Bhd
6) Light and Energy Sdn Bhd
Promotional Activities
As of 2017, 12 Nos of promotional activities/programs on green incentives was conducted and participated by 245 companies.
KeTTHA is expected to organise more promotional activities in Q3 and Q4 2018.

## Slide 47
2016 | 2017 | 2018 Weightage : 35% | 2019 Weightage : 35% | 2020 Weightage : 30%
 |  | The regulation gazetted Implementation framework established Stakeholders engagement with 20 Local authorities conducted At least 1 promotional activities / program on the regulation conducted | Regulation incorporated in the construction contract Stakeholders engagement with 13 Local authorities conducted At least 1 promotional activities / program on the regulation conducted | At least 7 states enforce the regulation
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER JPSPN / SW CORP
KPI DESCRIPTION 7 states establish Peraturan-Peraturan Pengurusan Sisa Pepejal dan Pembersihan Awam (Skim bagi Sisa Pepejal Pembinaan) 2018 dan Peraturan-Peraturan Pengurusan Sisa Pepejal dan Pembersihan Awam (Lesen bagi Sisa Pepejal Pembinaan ) 2018
INITIATIVE E5-Reduce irresponsible waste during construction
SUB-INITIATIVE -
This is a new KPI under the purview of IWG7 commencing 2018
Peraturan-Peraturan Pengurusan Sisa Pepejal dan Pembersihan Awam
Draft regulation was submitted and commented by Attorney General. Amendments had been finalized and expected to be approved by the Minister in Q3 2018.
Implementation Framework
Implementation framework will be prepared upon the above regulation is being gazetted.
Promotional Activities
Promotional activities will commence once the implementation framework is ready.
ENVIRONMENTAL SUSTAINABILITY
KPI E5-137
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 48
2016 | 2017 | 2018 Weightage : 40% | 2019 Weightage : 30% | 2020 Weightage : 30%
 |  | Final report on baseline study published Construction & demolition online system completed by Q1 2018 At least 1 awareness seminar on construction waste conducted Status report on the construction and demolition waste recycled published | At least 1 awareness seminar on construction waste conducted Status report on the construction and demolition waste recycled published Collection of construction & demolition waste data through online system gazetted | At least 1 awareness seminar on construction waste conducted Status report on the construction and demolition waste recycled published Study on achievement of construction and demolition waste recycled published
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER JPSPN / SW CORP
KPI DESCRIPTION 20% annual increment in construction and demolition waste (tonnage) recycled
INITIATIVE E5-Reduce irresponsible waste during construction
SUB-INITIATIVE -
This is a new KPI under the purview of IWG7 commencing 2018
Baseline Study
Baseline for the waste recycling rate was established based on data collected from February 2017 till January 2018. The rate of C&D waste that was recycled in 2017 was 13.7%.
C&D Waste Management Online System
The online C&D waste management system was completed in Jan 2018. The system will provide a platform for both waste collectors and waste producers to key-in data on C&D waste generated to assist the relevant authorities in implementing waste management programmes towards sustainability of the environment.
Awareness Seminar
Awareness seminar on construction waste management is scheduled to be held in Sept 2018.
Report on C&D Waste Recycled
Data collection on C&D waste for 2018 is on-going. The report will be prepared when sufficient data is ready.
ENVIRONMENTAL SUSTAINABILITY
KPI E5-138
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 49
This KPI is under the purview of IWG8
Establishment of Construction Industry Competency Forum (CICF)
In June 2016, the CICF was established to study on existing construction related training programs and training providers. CICF is represented by related Technical & Vocational Education & Training (TVET) training providers from various government and private agencies.
Through CICF, 158 construction related TVET programs under 4 main clusters (building, civil & structural, mechanical and electrical) and 12 major training providers were identified.
The identified construction related training programs and all training providers are expected to use the same framework and approach in training and assessment so that a single certification and standardization of training courses could be implemented.
The first CICF workshop in March 2017 had concluded that in principle all construction skills training need to :
standardize the name for courses
use a common skill standard
standardize period of training
adopt a single certification
In the second workshop in October 2017, CIDB had proposed and presented the Competency Training Framework to the forum. The forum had agreed that CIDB and Jab. Pembangunan Kemahiran (JPK) to further discuss and decide on the standardization of;
a) Competency Standards
b) Certification Schemes
Competency Standards
CIDB as the Industry Lead Body (ILB) and JPK has agreed to utilize the National Occupational Skills Standard (NOSS) as the competency standard.
Certification Schemes
Streamlining aspects of these two certification schemes have yet to be finalized between CIDB and JPK :
Sijil Kemahiran Malaysia (SKM)
This certification is under the purview of JPK and it conforms to the Malaysian Qualification Framework (MQF) requirements.
2) Sijil Kecekapan Kemahiran (SKK)
This certification is under the purview of CIDB in fulfilling the provisions under Act 520.
Construction Training Registered
Discussion with JPK on streamlining standards and certifications for construction industry was held on 4 June 2018 and the outcome will be presented to all CICF members on the next CICF meeting in August 2018.
2016 Weightage : 40% | 2017 Weightage : 40% | 2018 Weightage : 20% | 2019 | 2020
Construction Industry Competency Forum established Construction related TVET training programs and providers compiled and validated | Construction related trainings and programs streamlined Streamlined training programs validated and endorsed | Construction related trainings and programs registered by CIDB |  | 
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION All construction related training programs and institutions streamlined and registered by CIDB by Q4 2018
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1a - Streamline construction-related training programmes in Malaysia
PRODUCTIVITY
KPI P1-048
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 50
2016 Weightage : 40% | 2017 Weightage : 40% | 2018 Weightage : 20% | 2019 | 2020
Construction industry blueprint on skilled trades completed Top ten highly demanded construction related skilled trades validated by industry | 1st draft on training maps for top ten skilled trades validated | Training maps for top ten skilled trades published |  | 
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION Top ten highly demanded skilled trades have training need analysis, occupational analysis and training maps by Q4 2018
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1a - Streamline construction-related training programmes in Malaysia
This KPI is under the purview of IWG8.
Construction Industry Competency Blueprint (CICB)
CICB will be the roadmap for the enhancement of the existing competency standards and the development of new competency standards. This blueprint will lead to other aspects of the competency processes such as the need for competency standards, the improvement of the existing competency standards, course of study and training pathways. This development will also lead to the introduction or the improvement of the assessment, internal and external verification processes and will later be identified as the Construction Industry Competency Framework (CICF).
This blueprint was completed by Saiful Training & Consultancy and presented and validated by IWG8 on 3 Aug 2016.
Top Ten High Impact Construction Related Skilled Trades :
They are as follows:
Scaffolding Erection
Welding 3G and 6G
Wireman (PW1, PW2, PW3, and PW4)
Chargeman (A0, A1, B0, B1 and B4)
Gas Pipe Fitting (Fitting / Insulation)
Blasting & Painting
Non Destructive Testing (NDT)
Crane Operation
Plant Operation
Plumbing
Training Maps For Top Ten Skilled Trades
Saiful Training & Consultancy was appointed on 15 May 2017 to develop the training map for the 10 Construction Industry Occupational Title (CIOT) identified by IWG8. Final draft of the training maps for the top ten skilled trades were submitted by the consultant on 18 Dec 2017 and have been validated in IWG 8 meeting on 16 January 2018.
Training Map Published
Training maps for the top ten skilled trades were published in May 2018 and distributed to TVET agencies, related training centers and all CIDB offices.
PRODUCTIVITY
KPI P1-049
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 51
2016 Weightage : 10% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 30%
500 on-the-job apprentices in approved fields produced. | 700 on-the-job apprentices in approved fields produced. | 1000 on-the-job apprentices in approved fields produced. | 1,300 on-the-job apprentices in approved fields produced. | 1,500 on-the-job apprentices in approved fields produced.
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 5,000 on-the-job apprentices produced by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8.
Construction Apprenticeship Program
This program is aimed at producing high skill workers in these three (3) main categories :
Construction Skilled Worker
Construction Site Supervisor
Construction Site Manager
The program is executed via placement of apprentices with various construction stakeholders such as Petronas Chemical Group, Malaysia Mobile Crane Operators Association (MMCOA), Malaysia Offshore Contractors Association (MOCA), PUNB, Jabatan Pembangunan Kemahiran, Lendlease, West Coast Expressway Sdn. Bhd., Ceteau Malaysia Sdn. Bhd., Muhibbah Engineering (M) Bhd, Vision Thermoplastic Sdn. Bhd., Putra Perdana Sdn. Bhd. and others.
Table below shows the number of on-the-job apprentices produced in various skill trades:
PRODUCTIVITY
KPI P1-050
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
CONSTRUCTION SKILLED WORKER | 2016 | 2017 | 2018 (Q2)
Mechanical Fitter | 60 | 117 | 0
Crane Operator | 10 | 31 | 83
Scaffolding | 39 | 109 | 68
Rigging | 20 | N/A | 0
Landscape, Builders, Plumbing, Building Maintenance | 251 | 119 | 32
Architectural Drafting | 20 | 21 | 15
Welding | 34 | 35 | 14
Wet Skills, Blasting & Painting, Aircond | 52 | 165 | 134
Gas Pipe Installer | N/A | 18 | 108
Gas Pipe Insulation | N/A | N/A | 47
IBS | N/A | 17 | 21
Electrical | N/A | 130 | 41
Plant Operation | N/A | 80 | 44
TOTAL: | 486 | 842 | 607
SUPERVISORY | 2016 | 2017 | 2018 (Q2)
Site Supervisor (Building & Architectural, Civil, M&E) | 52 | 18 | 35
TOTAL: | 52 | 18 | 35
MANAGEMENT | 2016 | 2017 | 2018 (Q2)
Contractor Management | 66 | 0 | 0
TOTAL: | 66 | 0 | 0
TOTAL ACHIEVEMENT | 2016 | 2017 | 2018 (Q2)
Skilled Worker | 486 | 842 | 607
Supervisory | 52 | 18 | 35
Management | 66 | 0 | 0
TOTAL: | 604 | 860 | 642
To date, a total of 2,106 against the overall target of 2,200 (2016-2018) on-the-job apprentices were produced in various skill trades.

## Slide 52
This KPI is under the purview of IWG8
Training and certification of supervisory and management personnel
This training and certification program is aimed at producing site supervisors and site managers in these four (4) main areas :
Building & Architectural
Civil & Structural
Mechanical
Electrical
Site supervisors and site managers can be certified through 3 methods:
Training and assessment
Assessment only
Interview
The training and assessment is conducted by Accredited Training Centre certified by CIDB. The following table is the achievement to date :
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
3,000 supervisory and management personnel in approved fields trained and certified. | 3,000 supervisory and management personnel in approved fields trained and certified. | 3,000 supervisory and management personnel in approved fields trained and certified. | 3,000 supervisory and management personnel in approved fields trained and certified. | 3,000 supervisory and management personnel in approved fields trained and certified.
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 15,000 supervisory and management personnel (including QA/QC, site safety etc) trained and certified by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
PRODUCTIVITY
KPI P1-051
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
To date, a total of 11,480 site supervisors and managers were trained and certified in the above four (4) main areas against the target of 9,000 (2016-2018).
 | 2016 | 2017 | 2018 (Q2) | Total
Target | 3,000 | 3,000 | 3,000 | 9,000
Achievement Supervisory Management | 4,123 966 | 3,095 880 | 1,704 676 | 11,480
Total | 5,089 | 3,975 | 2,416 | 
Achievement % | 169% | 132% | 80% | 127%

## Slide 53
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
20,000 construction personnel in approved CPD fields trained | 20,000 construction personnel in approved CPD fields trained | 20,000 construction personnel in approved CPD fields trained | 20,000 construction personnel in approved CPD fields trained | 20,000 construction personnel in approved CPD fields trained
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 100,000 construction personnel completed Continuous Professional Development training by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8
Continuous Professional Development (CPD)
CPD is a continuous program conducted by registered training providers to improve the knowledge and skills of construction personnel in technical, management and finance. Each participant will be eligible for CCD points.
To date, a total of 119,770 personnel had completed the Continuous Professional Development (CPD) Program against the target of 60,000 (2016-2018).
PRODUCTIVITY
KPI P1-052
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 54
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
20,000 graduates in approved skills trained and certified. | 20,000 graduates in approved skills trained and certified. | 20,000 graduates in approved skills trained and certified. | 20,000 graduates in approved skills trained and certified. | 20,000 graduates in approved skills trained and certified.
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 100,000 construction personnel graduated in construction related skills trained and certified by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8
Graduates In Approved Skills
These skills trainings are organized by Akademi Binaan Malaysia (ABM) and Pusat Latihan Bertauliah (PLB) that produce graduates in nine (9) construction related skills and accredited by CIDB.
The Table below shows the number of graduates produced :
To date, 65,578 construction personnel in approved construction related skills trained and certified in the above trades against the target of 60,000 (2016-2018).
PRODUCTIVITY
KPI P1-053
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
NO | TRADE CATEGORIES | 2016 | 2017 | 2018 (Q2) | Total
1. | Building | 7,348 | 8,124 | 4,085 | 65,578
2. | Industrialized Building System | 872 | 595 | 301 | 
3. | Crane Operation | 1,247 | 2,390 | 1,213 | 
4. | Plant Operation | 2,703 | 1,755 | 765 | 
5. | Mechanical & Electrical | 7,991 | 4,397 | 2,598 | 
6. | Drafting | 855 | 634 | 267 | 
7. | Civil | 375 | 150 | 180 | 
8. | Welding | 4,273 | 2,619 | 1,002 | 
9. | Blasting & Painting | 511 | 383 | 110 | 
10. | Non Destructive Testing | 967 | 455 | 90 | 
TOTAL: |  | 37,142 | 21,502 | 6,934 | 
Achievement % |  | 185% | 107% | 35% | 

## Slide 55
2016 Weightage : 20% | 2017 Weightage : 80% | 2018 | 2019 | 2020
Study to identify source countries for assessment centers completed and validated | 2 Skill Assessment Center in major foreign worker source country audited and registered |  |  | 
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 2 assessment centers in major foreign worker source countries established by Q4 2017
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8
Many foreign countries have recognised CIDB’s credibility in assessing and accrediting construction workers assessment centres. CIDB’s accreditation is seen as an added value in recognising the assessment centres overseas. Hence, many requests have been received from major foreign worker source countries for CIDB to accredit their respective assessment centres.
Skill Competency Assessment Centres Accredited In Foreign Worker Source Countries
The targeted numbers of assessment centers in major foreign worker source countries to be audited and registered have been achieved. However CIDB will continue to accredit assessment centers worker source countries from time to time as requested.
This KPI is 100% completed.
PRODUCTIVITY
KPI P1-054
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
NO | SOURCE COUNTRIES | 2016 | 2017
1. | Bangladesh | 10 | 0
2. | India | 9 | 0
3. | Indonesia | 3 | 0
4. | China | 3 | 0
5. | Vietnam | 0 | 2
6. | Thailand | 1 | 0
7. | Myanmar | 1 | 0
8. | Pakistan | 1 | 0
 | SUB-TOTAL | 28 | 2
 | TOTAL | 30 | 

## Slide 56
2016 | 2017 Weightage : 25% | 2018 Weightage : 25% | 2019 Weightage : 25% | 2020 Weightage : 25%
 | 50 documents of Competency Standards, Training Modules and Assessment Questions to be developed/reviewed. 50 Nos of skill trainers/assessors undergo Train the Trainer/Assessors programs. | 50 documents of Competency Standards, Training Modules and Assessment Questions to be developed/reviewed. 50 Nos of skill trainers/assessors undergo Train the Trainer/Assessors programs. | 50 documents of Competency Standards, Training Modules and Assessment Questions to be developed/reviewed. 50 Nos of skill trainers/assessors undergo Train the Trainer/Assessors programs. | 50 documents of Competency Standards, Training Modules and Assessment Questions to be developed/reviewed. 50 Nos of skill trainers/assessors undergo Train the Trainer/Assessors programs.
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 200 competency related documents completed and 200 trainers undergo train the trainer program by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This is a new KPI under the purview of IWG8 and commenced in 2017.
In streamlining all training programs and training providers towards enhancing the competency of the skilled workers in the construction industry, CIDB also undertakes to develop the relevant Competency Standards, Training Modules and Assessment Questions.
Documents of Competency Standards, Training Modules and Assessment Questions :
Until Q2 2018, 156 documents on Competency Standards, Training Modules and Assessment Questions were developed/reviewed against the target of 100 documents (2017-2018).
Skill Trainers/Assessors Undergo Train The Trainer/Assessors Programs :
Until Q2 2018, 158 skill trainers/assessors have completed the Train the Trainer/Assessors programs against the target of 100 trainers and assessors (2017-2018).
PRODUCTIVITY
KPI P1-134
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
TYPE OF DOCUMENTS | 2017 | 2018 (Q2)
Competency Standards | 17 | 3
Training Modules | 18 | 3
Assessment Questions | 81 | 34
TOTAL: | 116 | 40
TRAINER/ASSESSOR | 2017 | 2018 Q2)
Trainer | 92 | 66
Assessor |  | 
TOTAL: | 92 | 66

## Slide 57
This KPI is under the purview of IWG9.
Manpower Study :
UPM Consultancy & Services Sdn Bhd was appointed in 2016 to conduct the manpower study. The ‘Kajian Pengurusan Modal Insan Dalam Industri Pembinaan Di Malaysia’ was published on 26 Dec 2017. Recommendations from this study is useful for multiple agencies with interest such as the Ministry of Human Resource (MOHR), Ministry of Home Affairs (MOHA), Majlis Amanah Rakyat (MARA) and others. The following is the summary of the manpower study:
Objektif kajian:
Mengkaji permintaan dan penawaran terhadap personel pembinaan di Malaysia
Mengkaji strategi dan amalan terbaik di negara lain : (United Kingdom, United Arab Emirates (UAE), Singapura, Jerman dan Australia)
Mencadangkan strategi yang sewajarnya dalam merasionalisasikan personel tempatan dan asing
Menghasilkan model dan kaedah unjuran terhadap penawaran dan permintaan pekerja binaan
Menganggarkan ketidakcukupan keperluan personel dalam industri pembinaan sehingga 2030.
Penemuan:
Construction Personnel Modelling System (CoPMos) telah dibangunkan bagi menghasilkan unjuran permintaan dan penawaran personel binaan di Malaysia sehingga tahun 2020. Model ini boleh digunakan bermula 2018. CopMos juga boleh digunapakai sehingga tahun 2030 dengan input parameter tahunan terkini.
Dashboard Penanda Aras dengan negara maju telah dibangunkan bagi mengenalpasti amalan terbaik dalam pengurusan tenaga kerja dalam industri pembinaan.
Human Capital Management Model (HCMM) dibangunkan bagi mengenalpasti penawaran personel tempatan sebagai pilihan utama sebelum kemasukan pekerja asing dibuat. Sebarang kekurangan akan menjadi asas kepada pembangunan modul latihan oleh institusi TVET.
Manpower Master Plan akan dikeluarkan secara tahunan bagi digunakan oleh kerajaan dan industri dalam merancang pembangunan tenaga kerja.
Blueprint keperluan personel dalam sektor pembinaan akan dikeluarkan secara tahunan berdasarkan kategori MASCO 4-digit.
Presentation of Study to Related Agencies :
The study was presented to the following :
KSU Kementerian Kerja Raya on 7 February 2018.
TWG3 on 6 March 2018
Jawatankuasa Kerja Dasar, KKR on 10 April 2018
UPMCS appointed Pn Satariah Awang Kecik as the ‘proof reader’ from 11 Jan – 18 Jan 2018 as per commented during CITP-IWG9/P2 meeting on 26 Dec 2017 to review the entire study. The study was completely proof read by end of January 2018.
Analysis Report and 2017 Manpower Status :
Meeting with IBS unit on the impact of IBS on manpower supply was held on 16 March 2018. Draft analysis report and manpower status 2017 was presented to GM BPPB on 27 June 2018. The final draft of analysis report and manpower status 2017 will be submitted on 2 July 2018.
2016 Weightage : 10% | 2017 Weightage : 50% | 2018 Weightage : 20% | 2019 Weightage : 10% | 2020 Weightage : 10%
10% of Manpower Study draft completed by Q4 2016 | Manpower Study finalised and published by Q4 2017 | Presentation on manpower study to related agencies and manpower projection 2017 by Q1 2018 Analysis report and manpower status 2017 by Q2 2018 Manpower projection 2018 published by Q4 2018 | Analysis report and manpower status 2018 by Q2 2019 Manpower projection 2020 published by Q4 2019 | Analysis report and manpower status 2019 by Q2 2020 Manpower projection 2021 published by Q4 2020
SPONSOR En Megat Kamil Azmi Megat Rus Kamarani
OWNER Ahmad Ridzuan Ismail
OIC Nurul Hidayah Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION Report on construction manpower supply and demand, published annually from Q4 2017 onwards
INITIATIVE P2 - Enhance control and balance of workforce supply
SUB-INITIATIVE P2a - Implement regular industry manpower planning
PRODUCTIVITY
KPI P2-055
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 58
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
Schedule 3 of Act 520 on skills trades reviewed and gazzeted by Q3 2016 | 100% of 2017 application by assessed skilled workers and supervisory personnel accredited and registered | 2017 Data analytics on accredited skilled workers and supervisory personnel produced by Q1 2018 100% of 2018 application by assessed skilled workers and supervisory personnel accredited and registered | 2018 Data analytics on accredited skilled workers and supervisory personnel produced by Q1 2019 100% of 2019 application by assessed skilled workers and supervisory personnel accredited and registered | 2019 Data analytics on accredited skilled workers and supervisory personnel produced by Q1 2020 100% of 2020 application by assessed skilled workers and supervisory personnel accredited and registered
SPONSOR En Megat Kamil Azmi Megat Rus Kamarani
OWNER Ahmad Ridzuan Ismail
OIC Nurul Hidayah Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION All qualified skilled workers and supervisory personnel accredited from Q4 2016 onwards
INITIATIVE P2 - Enhance control and balance of workforce supply
SUB-INITIATIVE P2a - Implement regular industry manpower planning
This KPI is under the purview of IWG9.
Mandatory accreditation of 59 trades of skilled workers and supervisory personnel under CIDB Act 520 Amended 2011 came into force on 1 June 2016. The Amended Schedule 3 of Act 520 currently have only 25 trades of skilled workers and supervisory personnel gazetted on 10 February 2017.
Data Analytics On Accredited Skilled Workers And Supervisory Personnel 2017 :
Until Dec 2017, 100% of 89,256 (66,024 + 23,232) applications received from assessed skilled workers and supervisory personnel were accredited and registered by CIDB. The table below shows the total number of construction personnel listed by CIDB under the 6 categories of workers as of Dec 2017. For the purpose of this KPI, only category 2 and category 5 is relevant for analysis.
PRODUCTIVITY
KPI P2-056
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
KATEGORI | TEMPATAN | ASING | JUMLAH
1. PEKERJA BINAAN AM | 281,326 | 89,377 | 370,703
2. PEKERJA BINAAN MAHIR | 63,671 | 2,353 | 66,024
3. PELATIH BINAAN | 78,316 | 18 | 78,334
4. PENGURUS PROJEK BINAAN | 66,101 | 1,862 | 67,963
5. PENYELIA BINAAN | 22,986 | 246 | 23,232
6. PERSONEL PENTADBIRAN | 93,848 | 1,921 | 95,405
TOTAL: | 605,884 | 95,777 | 701,661

## Slide 59
SPONSOR En Megat Kamil Azmi Megat Rus Kamarani
OWNER Ahmad Ridzuan Ismail
OIC Nurul Hidayah Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION All qualified skilled workers and supervisory personnel accredited from Q4 2016 onwards
INITIATIVE P2 - Enhance control and balance of workforce supply
SUB-INITIATIVE P2a - Implement regular industry manpower planning
The graph below shows the trend of skilled worker and supervisory personnel accredited and registered by CIDB from January until December 2017.
PRODUCTIVITY
KPI P2-056
PROGRESS REPORT UNTIL Q2 2018
Application by Assessed Skilled Workers And Supervisory Personnel Accredited And Registered 2018 :
Up to Q2 2018, 100% of of 92,944 (69,169 + 20,258) applications received from assessed skilled workers and supervisory personnel were accredited and registered by CIDB. For the purpose of this KPI, only category 2 and category 5 is relevant.
KATEGORI | TEMPATAN | ASING | JUMLAH
1. PEKERJA BINAAN AM | 327,910 | 105,783 | 433,693
2. PEKERJA BINAAN MAHIR | 69,169 | 3,517 | 72,686
3. PELATIH BINAAN | 81,234 | 14 | 81,248
4. PENGURUS PROJEK BINAAN | 82,199 | 3,063 | 85,262
5. PENYELIA BINAAN | 19,955 | 303 | 20,258
6. PERSONEL PENTADBIRAN | 96,531 | 3,391 | 99,922
TOTAL: | 676,998 | 116,071 | 793,069

## Slide 60
2016 | 2017 | 2018 Weightage : 60% | 2019 Weightage : 40% | 2020
 |  | New policy on tiered–visa approved by JKKPA-PATI by Q4 2018 | Tiered visa implemented for construction workers beginning Q1 2019 | 
SPONSOR En Megat Kamil Azmi Megat Rus Kamarani
OWNER Ahmad Ridzuan Ismail
OIC Nurul Hidayah Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION Tiered-visa programme implemented by Q1 2019
INITIATIVE P2 - Enhance control and balance of workforce supply
SUB-INITIATIVE P2b - Introduce mechanisms to raise skills mix for intake of foreign workers
This KPI is under the purview of IWG9.
New Policy On Tiered–Visa
JKKPA-PATI chaired by the Deputy Prime Minister had approved the same programme on Tiered Visa presented by ILMIA, KSM known as Multi-Tier Levy on 17 August 2017. ILMIA from KSM was requested by the JKKPA-PATI to conduct a study on multi-tier levy mechanism. UNIMAS was appointed by ILMIA to conduct the study titled “Developing Multi-Tier Levy: Malaysian Case Study” which covers all sectors in Malaysia including construction sector. The study commenced on 15 Jan 2018 with a completion date on 30 June 2018.
The inception report on the study was approved by the Technical Committee chaired by ILMIA on 2 March 2018. A workshop involving ILMIA and related agencies was held on 8 March 2018 to develop the multi-tier levy. The interim report was later approved by the committee chaired by ILMIA on 19 March 2018.
The mechanism of multi-tier levy was presented to KKR on 6 April 2018. Workshop focusing on construction industry was conducted on 9 – 11 April 2018. The findings of the workshop are still being finalized.
PRODUCTIVITY
KPI P2-057
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Note: 2016 - 2017
Subject to manpower study and policy approval by JKKPA-PATI

## Slide 61
2016 | 2017 | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020 Weightage : 40%
 |  | New policy on proportion of skilled (7%): unskilled (93%)foreign labour implemented by KDN | New policy on proportion of skilled (10%): unskilled (90%)foreign labour implemented by KDN | New policy on proportion of skilled (15%): unskilled (85%)foreign labour implemented by KDN
SPONSOR En Megat Kamil Azmi Megat Rus Kamarani
OWNER Ahmad Ridzuan Ismail
OIC Nurul Hidayah Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION Proportion of skilled : unskilled foreign labour improved from 5 : 95 to 15 : 85 by Q4 2020
INITIATIVE P2 - Enhance control and balance of workforce supply
SUB-INITIATIVE P2b - Introduce mechanisms to raise skills mix for intake of foreign workers
This KPI is under the purview of IWG9.
New Policy On Proportion of Skilled : Unskilled Foreign Labour
The proportion of skilled:unskilled foreign labour is included in the Multi-tier Levy programmme which was approved by JKKPA-PATI chaired by Deputy Prime Minister on 17 August 2017. The Multi-Tier Levy covers all sectors in Malaysia including construction sector. The policy will be formulated after the completion of the study by end of June 2018.
PRODUCTIVITY
KPI P2-058
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Note: 2016 - 2017
Subject to manpower study and policy approval by JKKPA-PATI

## Slide 62
2016 Weightage : 30% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 15% | 2020 Weightage : 15%
2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action on non-compliance AG agreement to audit on IBS non-compliance secured | 2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action non- compliance. Audit Report on IBS non compliance published by AG | 2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action non- compliance JKR corrective action on AG report on IBS | 2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action non-compliance | 2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action non-compliance
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER ICU / CIDB
KPI DESCRIPTION 2 reports annually on status of IBS adoption, submitted by Implementation Coordination Unit (ICU-JPM) to Ministry of Finance (MOF) and Auditor General (AG) for action on non-compliance beginning 2016
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
PRODUCTIVITY
KPI P3-060
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG10.
Report on Status of IBS Adoption
ICU JPM produced 1 report on the status of IBS adoption in government projects and submitted to MOF and AG in June 2016. It was reported that 69.4% (465 out of 670 project) of public projects adopted IBS and achieved 70 IBS score. ICU JPM confirmed that the 2nd report for year 2016 will not be issued as the level of IBS adoption is status quo.
For 2017, ICU JPM produced 1 report on the status of IBS adoption in government projects and submitted to MOF and AG on 31 July 2017 . The title of the report is “Laporan Pematuhan Pelaksanaan Untuk Projek-Projek Kerajaan RMKe-11 Bil.1/2017 (Januari-Jun 2017)”. It was reported that 77.8% (1113 out of 1431 projects) of public projects adopted IBS and achieved 70 IBS score. The 2nd report for year 2017 was not issued .
ICU JPM has submitted the 1st report for year 2018 (Jan-Apr) on 25 May 2018 and the level of adoption was 64%.
Audit Report on IBS Non-compliance
ICU JPM had submitted the report on the status of IBS adoption to AG for AG to audit on IBS non-compliance. No audit report have been received from AG.
It is to be noted that under KPI P3-063, Universiti Sains Malaysia (USM) was appointed by CIDB to conduct a study on “Non-compliance of IBS adoption in Public Project worth RM10 Mn and above”. Refer to KPI P3-063 on the findings of the study.

## Slide 63
2016 Weightage : 40% | 2017 Weightage : 40% | 2018 | 2019 | 2020
 |  | Weightage : 20% |  | 
50% of JKR Pre Approved Plan (PAP) comply to IBS and MC. JKR IBS-PAP drawings documented. | 100% of JKR Pre Approved Plan (PAP) comply to IBS and MC. JKR IBS-PAP drawings documented. |  |  | 
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER JKR/ CIDB
KPI DESCRIPTION All JKR Pre-Approved Plans (PAPs) comply to IBS and Modular Coordination by 2017
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
This KPI is under the purview of IWG10.
JKR Pre-Approved Plan in Compliance to IBS and MC (PAP2.0)
PAP means “reka bentuk bangunan yang tersedia dan lengkap dengan input seni bina, struktur, mekanikal, elektrikal dan ukur bahan yang menepati keperluan teknikal dan perundangan kerajaan iaitu Akta Jalan, Parit dan Bangunan 1974 (Akta 133)”. The objectives of PAP are to reduce the time for planning and design processes, and to give option and alternative to existing building designs. PAP2.0 refers to Pre-Approved Plan in compliance to IBS and MC.
JKR PAP2.0 included drawings for various types of buildings namely school, quarters, klinik kesihatan, dewan, surau, masjid, taska, office, etc.
In 2016, 78 out of 120 PAP2.0 were completed by JKR.
In 2017, all 130 PAP2.0 were completed by JKR.
Until Jun 2018, 15 out of 30 PAP2.0 have been completed by JKR.
PRODUCTIVITY
KPI P3-061
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Note: 2018-2020
All new JKR PAP comply to IBS and MC
(Annual target to be determined later)

## Slide 64
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER JKR/ CIDB
KPI DESCRIPTION All JKR and CIDB’s IBS components catalogue harmonised and issued by 2017
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
PRODUCTIVITY
KPI P3-062
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 70% | 2017 Weightage : 30% | 2018 | 2019 | 2020
Harmonization of JKR and CIDB IBS component catalogue completed | Harmonized IBS component catalogue for Industry reference published |  |  | 
This KPI is under the purview of IWG10.
The JKR and CIDB IBS component catalogue on precast concrete components was harmonised and completed in 2016.
This catalogue was later published as “IBS Component Catalogue For Precast Concrete Building System (Revision 2017)” on 27 September 2017.
The catalogue produced by CIDB will be the basic reference for the design, detailing and manufacturing of IBS components. It aims to provide designers i.e Architects & Engineers and Quantity Surveyors (QS) key information and references, including the description, sizing and detailing of pre-cast concrete components.
The objectives of producing the catalogue are outlined as follows:
To assist the Architects as guide in the preparation of architectural drawings
To assist the Engineers in producing the tender drawings during the designing process
To assist the QS in providing the tender documents during the procurement process
To assist the manufacturers/suppliers in producing shop drawings
The pre-cast concrete components in the catalogue consist of these elements:
Structural elements covering the precast concrete beam, column, load-bearing wall panel and floor slab.
Non-structural elements covering the precast concrete non load-bearing wall and staircase
Connection details covering connections of column to base; pocket foundation; steel base plate; column to column; beam to column; beam to beam; slab to beam; slab to slab; slab to wall and wall to wall.
Other design considerations covering structural stability & integrity; floor diaphragm; fire rating; mechanical & electrical services and site management.
The IBS Catalogue For Precast Concrete Building System Revision 2017 was launched during the MIIE 2018 Official Opening on 28 March 2018.
This KPI is 100% completed.

## Slide 65
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER JKR/ CIDB
KPI DESCRIPTION 80% compliance to amended MOF Circular 1 PPK 1/2013 by 2018
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
This KPI is under the purview of IWG10.
In 2008, the Ministry of Finance (MOF) issued a circular Surat Pekeliling Perbendaharaan Bil. 7 2008 (SPP Bil. 7 2008) to inform all Government Agencies to implement IBS in all public building projects worth RM10Mn and above and to achieve 70 IBS score.
IBS adoption for projects RM5mn and above
In 2016, JKR agreed in principle to broaden IBS adoption for projects RM5Mn and above. However MOF was in the opinion that adoption of IBS for public projects between RM5Mn to RM10Mn is encouraged (not mandated).
Study on non-compliance of IBS adoption in public projects worth RM10 Mn and above
IWG10 during its meeting dated 9 June 2017 agreed to include the above study as the annual target for 2017. The study was conducted by USAINS Holding Sdn Bhd beginning July 2017 and was completed on 30 October 2017. The study utilised data from ICU covering projects executed in 2010-2013, 2015 and 2016. The objectives of this study are:
To identify compliance and non-compliance of IBS adoption in the procurement of public sector building projects
To determine the causing factor towards a non-compliance of IBS adoption in public projects worth RM10Mn and above
To recommend viable improvements that can be made to ensure a full compliance of IBS adoption in all projects worth RM10Mn and above
The study found that the factors causing non compliance are as follows:
The contractors of PDP/PFI procured projects make their own discretion to decide whether to use IBS in their projects
Cost overrun may trigger budget constraints
Achievement of mandatory IBS score in design stage may not be achievable during construction
Insufficient expertise in designing and constructing IBS
Conventional design developed by consultants do not comply with available IBS components
Projects were situated in remote areas where IBS components are not accessible for transportation
Insufficient financial capacity of contractors due to high deposits required
Annual targets for 2018 – 2020 will be determined after MOF circular is issued to achieve the over-arching initiative of P3 i.e. accelerate the adoption of IBS, mechanisation and modern practices across project life-cycle.
A Technical Committee was formed to discuss on the requirement to broaden IBS adoption for Government Projects. The first meeting was held on 20 April 2018. MoF has issued a letter to ICUJPM with the instruction not to review the value for IBS implementation in Government project from RM10 Million to RM5 Million.
CITP IWG10 Bil. 5 dated on 8 June 2018 agreed to drop this KPI.
PRODUCTIVITY
KPI P3-063
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Note 2018-2020
Target to be determined after MOF Circular issued
2016 Weightage : 10% | 2017 Weightage : 40% | 2018 | 2019 | 2020
 |  | Weightage : 50% |  | 
JKR agreement to broaden IBS adoption for projects RM5mn and above secured. | Study on non-compliance of IBS adoption in public projects worth RM10 Mn and above |  |  | 

## Slide 66
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER KPKT/ CIDB
KPI DESCRIPTION 100% new Development Order in Greater Klang Valley for projects RM50 Mn and above achieved minimum 50 IBS Score by 2018
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3b - Drive scale of IBS adoption via private sector projects
PRODUCTIVITY
KPI P3-064
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 30% | 2017 Weightage : 30% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020
Criteria to mandate IBS in Private Sector established and approved by MNKT IBS criteria for new private sector projects announced by KPKT | PBTs in Greater Klang Valley agreement to adopt IBS criteria as a prerequisite for issuance of DO secured and implemented | KPKT Report on IBS adoption for private sector project published. Corrective action for non- compliance of IBS adoption proposed and implemented | KPKT Report on IBS adoption for private sector project published. Corrective action for non- compliance of IBS adoption proposed and implemented | 
This KPI is under the purview of IWG10.
Criteria to mandate IBS in Private Sector
A guideline to mandate IBS adoption in Private Sector for Projects worth RM50Mn and above to achieve a minimum 50 IBS Score was established and submitted to Ministry of Works in 2016. KPKT was to table the guideline to the MNKT for approval. MNKT Meeting held on 10 July 2017 approved the policy to mandate IBS adoption in Private Sector for Projects worth RM50Mn and above to achieve a minimum 50 IBS Score to be adopted via Development Order (DO) or Building Plan approval by PBTs. The policy was also agreed by the Mesyuarat Menteri-Menteri Besar & Ketua Menteri held on 10 October 2017.
In order for the policy to be implemented by the PBTs, it has to be passed in a state EXCO meeting chaired by the Menteri Besar. CIDB is currently putting up road shows to enlighten the PBTs on the implementation and execution of the above policy through engagements with the State Secretary. The road shows were executed to all states except Terengganu and Pulau Pinang. KPKT will issue a circular to all PBTs to enforce the IBS policy approved by MNKT.
CIDB had discussed with KPKT on 20 April 2018 to review the KPI for IBS implementation mechanism as well as draft the IBS state circular for PBT. This revised KPI was presented in IWG10 Meeting Bil. 5 dated 8 June 2018 and approved by the committee.
PBTs in Greater Klang Valley agreement to adopt IBS criteria as a prerequisite for issuance of DO
These Pihak Berkuasa Tempatan (PBT) or Local Authorities in Greater Klang Valley have been engaged as follows:
Dewan Bandaraya Kuala Lumpur (DBKL) – 17/10/2017
Perbadanan Putrajaya (PJC) – 17/10/2017
Majlis Bandaraya Petaling Jaya (MBPJ) – 18/05/2017
Majlis Bandaraya Shah Alam (MBSA)
Majlis Perbandaran Subang Jaya (MPSJ)
Majlis Perbandaran Kajang (MPKJ)
Majlis Perbandaran Selayang (MPS) - 19/01/2018
Majlis Perbandaran Klang (MPK)
Majlis Perbandaran Ampang Jaya (MPAJ)
Majlis Daerah Kuala Langat (MDKL)
IBS adoption had been agreed in principal by DBKL and MBPJ with further details to be refined at the implementation level.

## Slide 67
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER KPKT/ CIDB
KPI DESCRIPTION 100% new Development Order by identified Local Authorities in three states (Selangor, Johor & Pulau Pinang) for projects RM50Mn and above achieved minimum 50 IBS Score by 2020
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3b - Drive scale of IBS adoption via private sector projects
PRODUCTIVITY
KPI P3-065
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Weightage : 20%
2016 Weightage : 30% | 2017 Weightage : 30% | 2018 Weightage : 15% | 2019 Weightage : 15% | 2020 Weightage : 10%
Criteria to mandate IBS in Private Sector established and approved by MNKT IBS criteria for new private sector projects announced by KPKT | PBTs in three states agreement to adopt IBS criteria as a prerequisite for issuance of DO secured and implemented | KPKT Report on IBS adoption for private sector project in three states published. Corrective action for non- compliance of IBS adoption proposed and implemented | KPKT Report on IBS adoption for private sector project in three states published. Corrective action for non- compliance of IBS adoption proposed and implemented | KPKT Report on IBS adoption for private sector project in three states published. Corrective action for non- compliance of IBS adoption proposed and implemented
This KPI is under the purview of IWG10.
Criteria to mandate IBS in Private Sector
A guideline to mandate IBS adoption in Private Sector for Projects worth RM50Mn and above to achieve a minimum 50 IBS Score was established and submitted to Ministry of Work in 2016. KPKT was to table the guideline to the MNKT for approval. MNKT Meeting held on 10 July 2017 approved the policy to mandate IBS adoption in Private Sector for Projects worth RM50Mn and above to achieve a minimum 50 IBS Score to be adopted via Development Order (DO) or Building Plan approval by PBTs. The policy was also agreed by the Mesyuarat Menteri-Menteri Besar & Ketua Menteri held on 10 October 2017.
In order for the policy to be implemented by the PBTs, it has to be passed in a state EXCO meeting chaired by the Menteri Besar. CIDB is currently putting up road shows to enlighten the PBTs on the implementation and execution of the above policy through engagements with the State Secretary. The road shows were executed to all states except Terengganu and Pulau Pinang. KPKT will issue a circular to all PBTs to enforce the IBS policy approved by MNKT.
CIDB had discussed with KPKT on 20 April 2018 to review the KPI for IBS implementation mechanism as well as draft the IBS state circular for PBT. This revised KPI was presented in IWG10 Meeting Bil. 5 dated 8 June 2018 and approved by the committee.
PBTs in three states agreement to adopt IBS criteria as a prerequisite for issuance of DO
The 3 states identified were Selangor, Pulau Pinang and Johor. Pihak Berkuasa Tempatan (PBT) or Local Authorities in Selangor that had been engaged are as follows:
Majlis Daerah Hulu Selangor (MDHS)
Majlis Daerah Kuala Selangor (MDKS)
Majlis Daerah Sabak Bernam (MDSB) - 19/01/2018
Majlis Perbandaran Sepang (MPSepang)
The agreement from PBTs in Pulau Pinang and Johor Bahru have yet to be secured.

## Slide 68
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER CIDB
KPI DESCRIPTION At least 100 more new IBS component manufacturing plants established at various strategic locations by 2020
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3c - Propel IBS supply chain via economic mechanisms
This KPI is under the purview of IWG10.
In 2015, there are already 200 IBS component manufacturing plants producing various IBS components in existence.
In 2016, 27 new IBS component manufacturing plants producing 4 main components (precast concrete system, metal framing, innovative product and blockwork system) were established and registered in 7 states (Johor, Selangor, Sarawak, Pahang, Melaka, Kedah & Kelantan).
In 2017, 37 new IBS component manufacturing plants producing 5 main components (precast concrete system, metal framing, innovative product, formwork system and blockwork system) were established and registered in 8 states - Selangor (20), Johor (3), Pulau Pinang (1), Perak (1), N. Sembilan (3), Sarawak (4), Kedah (2) & Sabah (3).
A total of 96 out of 100 (as targeted until 2020) new IBS component manufacturers and suppliers have been registered.
To date, CIDB had registered a total of 296 IBS component manufacturing plants.
PRODUCTIVITY
KPI P3-066
PROGRESS REPORT UNTIL Q4 2017
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
20 new IBS manufacturer registered | 20 new IBS manufacturer registered | 20 new IBS manufacturer registered | 20 new IBS manufacturer registered | 20 new IBS manufacturer registered
NO | IBS COMPONENTS | NEW IBS MANUFACTURINGPLANTS |  |  | 
 |  | 2016 | 2017 | 2018 (Q1) | 2018 (Q2)
1 | Precast Concrete System | 9 | 9 | 2 | 5
2 | Metal Framing | 9 | 11 | 4 | 4
3 | Innovative Product | 8 | 10 | 3 | 9
4 | Blockwork System | 1 | 3 | 0 | 0
5 | Formwork System | 0 | 4 | 1 | 4
SUB TOTAL: |  | 27 | 37 | 10 | 22
TOTAL |  | 96 |  |  | 

## Slide 69
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER CIDB
KPI DESCRIPTION At least 5,000 professionals (engineers, architects & quantity surveyors) trained to apply IBS and modular coordination from design phase by 2020
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3c - Propel IBS supply chain via economic mechanisms
This KPI is under the purview of IWG10.
Training in IBS takes 3 days covering 5 modules in these areas:
M01 – Pengenalan kepada IBS untuk bangunan
M02 – Sistem Koordinasi modular (MC)
M03 – Pengiraan skor IBS
M04 – Konsep rekabentuk sistem konkrit pra-tuang
M05 – Pengurusan projek IBS
Professionals trained in IBS and Modular Coordination (MC) :
The statistic on professionals trained are as follows :
Cumulatively 3,282 professionals (529 Architects, 2,160 Engineers & 593 QSs) out of 5,000 (as targeted until 2020) professionals were trained in IBS and Modular Coordination.
Directory of trained professionals published
The directory of certified IBS professionals as of September 2017 were published in the Orange Book by CIDB. It also comprised directories for:
registered IBS suppliers/manufacturers, distributors and on site precast concrete casting
IBS consultants
statistics of IBS contractors
PRODUCTIVITY
KPI P3-067
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 5% | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020 Weightage : 5%
250 professionals trained in IBS and MC Directory of trained professionals published | 1500 professionals trained in IBS and MC Directory of trained professionals published | 1500 professionals trained in IBS and MC Directory of trained professionals published | 1500 professionals trained in IBS and MC Directory of trained professionals published | 250 professionals trained in IBS and MC Directory of trained professionals published
NO | PROFESSIONALS | 2016 | 2017 | 2018 (Q1) | 2018 (Q2)
1 | Architect | 46 | 264 | 115 | 104
2 | Engineer | 201 | 1128 | 495 | 336
3 | Quantity Surveyor | 109 | 321 | 140 | 23
SUB TOTAL: |  | 356 | 1713 | 750 | 463
TOTAL |  | 3,282 |  |  | 

## Slide 70
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER MIDA
KPI DESCRIPTION At least two economic mechanisms to propel adoption of IBS introduced by 2017
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3c - Propel IBS supply chain via economic mechanisms
This KPI is under the purview of IWG10.
Economic Mechanism to Propel IBS Adoption
The first economic mechanism was a tax holiday for qualified local IBS manufacturers introduced in 2016.
There were two qualified manufacturers that had enjoyed the tax holiday incentive, one in 2016 and another in 2017.
The second economic mechanism proposed was an import duty exemption for heavy machinery and equipment. CIDB’s application was submitted to MOF on 14 April 2016. MOF requested for an impact study to be conducted to analyse the implementation to include productivity issues, machineries issues and revenue losses to the Government. The draft of the impact study was submitted to KKR on 9 August 2017. The findings of the study are as follows :
Loss to government income is not significant
Advanced countries no longer impose tax on machineries
Increase in capital expenditure on machineries will lead to productivity increase
On 5 December 2017, KKR requested for 3 issues to be addressed :
Focus on 5 machines i.e tower crane, gantry crane, crawler crane, overhead crane and mobile crane
Assurance that the incentives benefit the contractors not machineries rental companies
The necessity for tax exemption of the machineries since tax exemptions have been covered under FTA
The revised study on exemption of tax for heavy machineries and equipment related to IBS was completed and submitted to KKR on 12 Mac 2018.
Cost Benefit Analysis (CBA)
The Construction Research Institute of Malaysia (CREAM) was appointed by CIDB to conduct the CBA in Oct 2016 and the study was completed in Jun 2017. CBA means a procedure to estimate all the costs involved and the expected benefits of a business opportunity proposal. The study analyses four (4) Impacts of IBS implementation that is; a) Business Perspective, b) Socioeconomic and Political Perspective, c) Public Administration and Governance Perspective and d) Sustainability, Safety, and Health Perspective.
The study covers all building projects built from 2008 to 2016. The study concluded that with the assumption that all these projects had adopted 100% IBS, a 24% cost savings can be generated (RM14Bn against approximate total cost of work done of RM58Bn in 2008 and RM30.4Bn against approximate total cost of work done of RM125Bn in 2016). Based on the 4 main perspectives in the CBA, the study concluded that the monetisable benefits amounted to RM21.8Bn.
The report on CBA was published in 2017 as “CIDB Technical Report No.1117- Cost Benefit Analysis for Industrialised Building System (IBS) Industry in Malaysia”.
KKR is currently reviewing the Paper to MoF on the approval for exemption of tax for machineries and equipment related to IBS.
PRODUCTIVITY
KPI P3-068
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 40% | 2017 Weightage : 30% | 2018 | 2019 | 2020
 |  | Weightage : 30% |  | 
Tax Holiday incentive for new IBS manufacturing plants approved and implemented. Cost Benefit Analysis (CBA) for IBS developed Report on IBS Tax Holiday incentive recipients published. | Second Incentive on economic mechanism to propel IBS adoption proposed and submitted to MOF. Report on CBA for IBS & incentive recipients published |  |  | 
Note 2018-2020
Target to be determined after proposal on second incentive approved

## Slide 71
SPONSOR Datuk Ir Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Jasni Ismail
KPI LEADER JKR
KPI DESCRIPTION 40% of public project above RM100Mn use BIM level 2 by Q1 2019
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4a - Facilitate BIM adoption in construction industry via regulation
PRODUCTIVITY
KPI P4-069
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 40% | 2020
BIM Level 1 implemented at JKR level | BIM transformation fund for contractor & consultant secured from EPU BIM Level 2 implemented by JKR | Circular on BIM implementation for above 100mn project issued by JKR and MOF | 40% of public projects above RM100mn use BIM Level 2 | 
BIM Level 2 Implementation
Definition of BIM Level 2 - Sharing of object based models and data between two or more disciplines to create federated models.
By Q2 2018, the following JKR projects are using BIM Level 2 :-
Hospital Parit Buntar, Perak
Hospital Kemaman, Terengganu
Kompleks Endokrin Hospital Putrajaya
Politeknik Bagan Datuk, Perak
Politeknik Besut, Terengganu
Hospital Pasir Gudang
Hospital Kajang, Selangor
Hospital Pendang, Kedah
Current status : 33% of public projects above RM100mn use BIM Level 2.
Site visit by JKR to Brunsfield's projects to study BIM implementation was held on 9 March 2017. Later, a workshop with Brunsfield, professionals and related agencies such as BEM, LAM, PAM, IEM, MAMPU and MyIPO was held on 27 Nov 2017.
Circular On BIM Implementation For Projects Above RM100Mn
The above circular is still being drafted for further discussion with MOF.
This KPI is under the purview of IWG11.
Definition of BIM Level 1 - Single disciplinary use of object based 3D modelling within one discipline.
BIM Level 1 implementation
BIM Level 1 implemented by JKR in 2016 for the following projects :
Sekolah Kebangsaan Meru Raya, Ipoh, Perak
(Blok Akademik dan kantin)
SK Tanjung Minyak 2 Melaka (Blok Akademik)
Makmal Sains Kolej Mara Banting, Selangor
BIM Transformation Fund
In December 2017, CIDB had allocated a budget of RM1,068,050.00 for consultants and contractors involved in BIM’s project. A total of 25 companies have been selected to receive RM33,000 incentive in the form of 3 Autodesk AEC licenses valid for one year and 3 free training seats for related myBIM training programs. These 25 companies are from the following 5 public projects :
Hospital Kemaman
Kompleks Endokrin Putrajaya
Politeknik Bagan Datuk
Istana Raja Muda Perlis, Arau
ABM Johor
ABM Sabah
The recipients consists of contractor, architect, C&S and M&E and they had received the 3 Autodesk AEC licenses on 25 May 2018.

## Slide 72
SPONSOR Datuk Ir Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Jasni Ismail
KPI LEADER CIDB
KPI DESCRIPTION BIM Object Library developed by Q1 2017
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4a - Facilitate BIM adoption in construction industry via regulation
This KPI is under the purview of IWG11.
BIM Object Library
MyBIM Library was envisioned since 2015 to facilitate and expedite the development of BIM models by design consultants. Components can be downloaded at no cost to the user as part of CIDBs initiative to facilitate and encourage the adoption of BIM by the industry.
Developed by CIDB E-Construct Services Sdn. Bhd. (a wholly owned subsidiary of CIDB Malaysia) since 2017, the enhanced version of the portal is accessible via www.mybimlibrary.my
The library is fully functioning and ready for use with a total of 6,829 components populated into the library. It comprised of 829 IBS and 6,000 Medical components, and is currently used to support the development of Level of Detail (LOD) for 300 models. The number of IBS components populated into the BIM Object library has surpassed the targeted 700.
A few manufactures have already expressed interest to populate the library with their products such as Honeywell International Sdn. Berhad (M&E products), Hauslife Furniture and Prihoda (M) Sdn. Bhd. (HVAC products).
myBIM Library was officially launched by Chief Executive of CIDB on 29 March 2018 during the BIM Day 2018 and myBIM Centre is actively promoting the library to increase awareness through nationwide BIM road tour and industry engagement programs.
500 Manufacturing components had been added and 1000 component will be added into BIM Library platform within 2018.
The BIM Library’s promotion will be held at these 3 big events :
International Architecture, Interior Design and Building Exhibition (ARCHIDEX) on 4 July 2018 at KLCC
Engineering Exhibition And Show (EES 2018) on 16 – 18 August 2018 at the MINES Convention Center
Strategic Alliance with Innovation & Human Capital Kuala Lumpur (IFAWPCA) on 12 – 16 Nov 2018 at KLCC
PRODUCTIVITY
KPI P4-070
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 30% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 10%
User Requirement for BIM Object Library rolled out | BIM Object Library completed 700 IBS components populated into BIM object library | 6000 hospital components populated into BIM Object Library | BIM IBS Object Library updated with 1000 new components | BIM IBS Object Library updated with 1000 new components

## Slide 73
SPONSOR Datuk Ir Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Jasni Ismail
KPI LEADER CIDB
KPI DESCRIPTION 1000 BIM Personnel Trained And Certified by Q4 2018
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4b - Establish reference centre to support the development and adoption of BIM and modern methods
This KPI is under the purview of IWG11.
In order to support the development and adoption of BIM and modern methods, seven (7) BIM training modules were developed by CIDB Malaysia and endorsed by a panel of industry experts in 2016. Training courses offered by myBIM Centre and four (4) satellite centres are as follows:
BIM Concept & Theory
BIM Modelling of Architecture
BIM Modelling of Structure
BIM Coordinator Part 1
BIM Coordinator Part 2
BIM Manager 01
BIM Manager 02
The Mechanical, Electrical and Plumbing Module is completed and will be endorsed by ‘Jawatankuasa Teknikal Pembangunan Modul Latihan BIM ‘ on 16 July 2018.
Visit www.mybimcentre.com.my/product-category/training/bim-module-training/ for more information on duration, costs and pathway.
As of Q2 2018, 316 BIM personnel were trained. To-date, a total of 3,115 BIM personnel including professionals were trained since 2016.
PRODUCTIVITY
KPI P4-071
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 30% | 2017 Weightage : 30% | 2018 Weightage : 40% | 2019 | 2020
‘National BIM Training Module completed 300 BIM professional trained & certified | 300 BIM professional trained & certified | 400 BIM professional trained & certified | 300 BIM professional trained & certified | 300 BIM professional trained & certified
Courses | 2016 |  | 2017 |  | 2018 | 
 | Classes | Attended | Classes | Attended | Classes | Attended
BIM Concept & Theory | 13 | 308 | 9 | 184 | 8 | 208
BIM Modeller | 59 | 1130 | 58 | 1123 | 7 | 82
BIM Coordinator | 5 | 30 | 2 | 6 | 3 | 24
BIM Manager | 2 | 10 | 1 | 8 | 1 | 2
Total | 79 | 1478 | 70 | 1321 | 19 | 316

## Slide 74
SPONSOR Datuk Ir Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Jasni Ismail
KPI LEADER CIDB
KPI DESCRIPTION BIM Submission using 4 pilot projects for 4 selected PBT by Q1 2020
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4b - Establish reference centre to support the development and adoption of BIM and modern methods
This KPI is under the purview of IWG11.
Agreement to Adopt BIM eSubmission by PBT
Four (4) PBTs agreed to adopt BIM e-Submission by 2017. They are Putrajaya Corporation (PJC), Majlis Bandaraya Petaling Jaya (MBPJ), Majlis Perbandaran Kangar (MPK) and Majlis Bandaraya Melaka Bersejarah (MBMB).
User Requirement Studies (URS)
By Q2 2018, URS for BIM based building design review and checking system have been completed for 4 PBTs which are PJC, MBPJ MPK and MBMB.
System Development
By Q2 2018, system development for all 4 PBTs have been completed and User Acceptance Test (UAT) is on-going.
System Operator Training
Seven (7) personnel from PJC were trained as system operator.
Pilot Project Roll-out
Four (4) residential projects (one from each PBT) will be identified and used for pilot implementation of BIM eSubmission by 2020.
National BIM eSubmission (NBeS) phase II for BOMBA is in progress and will be completed by end of 2019.
PRODUCTIVITY
KPI P4-072
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 10% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 30%
4 selected PBT agreement to adopt BIM e-submission (MBPJ, PJC, Melaka & Perlis ) secured | User requirement study for BIM based building design review & checking system completed for 2 PBTs BIM operators from selected 2 PBTs trained | BIM based building design review & checking system developed for selected 2 PBTs User requirement study for BIM based building design review & checking system completed for 2 more PBTs | Pilot project BIM Based Submission System on selected 2 PBTs launched BIM operator s for selected 2 PBTs trained BIM based building design review & checking system developed for 2 more PBTs | BIM Based Submission System operated by the selected 2 PBTs
Milestones | PJC | MBPJ | MPK | MBMB | BOMBA
Agreement to adopt BIM eSubmission | √ | √ | √ | √ | √
User Requirement Specification | √ | √ | √ | √ | 
System Development | √ | √ | √ | √ | 
System Operator Training | √ |  |  |  | 
Pilot Project Roll-out |  |  |  |  | 

## Slide 75
SPONSOR Datuk Ir Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Jasni Ismail
KPI LEADER JKR
KPI DESCRIPTION 5 Public Pilot Project Use BIM Level 3 by Q3 2020
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4b - Establish reference centre to support the development and adoption of BIM and modern methods
This KPI is under the purview of IWG11.
BIM Level 3 is defined as the sharing and integration of several multi-disciplinary models and data using model servers or other cloud based technology.
National BIM Guide
This was completed in November 2016 covering aspects of BIM awareness, readiness and adoption. Copies of the BIM Guide can be downloaded from https://www.mybimcentre.com.my/knowledge-base/
BIM Procurement Specification (BPS)
JKR published the BPS in 2017 comprising of:
JKR BIM Requirement For Design & Build Projects
Manual Proses Kerja BIM JKR (Fasa Perancangan)
Manual Proses Kerja BIM JKR (Fasa Rekabentuk Awalan)
Manual Proses Kerja BIM JKR (Fasa Rekabentuk Terperinci)
JKR Software/Hardware Customization
In order to achieve BIM Level 3 environment, certain complementing softwares called plug-ins need to be used. The list of plug-ins software have been selected by JKR for every disciplines (ie: architectural, structural, mechanical & electrical). CIDB had assisted JKR to acquire the plug-ins to complement JKR’s current capacity.
JKR Projects for BIM Level 3
The following are JKR projects secured for BIM implementation :
  Politeknik Bagan Datuk (Project Design & Build)
  Hospital kemaman (Project Design & Build)
  Hospital Parit Buntar (project Convensional In House)
  Hospital Kajang (Project Design & Build)
  Hospital Pasir Gudang (Project Design & Build)
  Hospital Pendang (Project Design & Build)
  Hospital Kajang Selangor
  Hospital Pasir Gudang Johor
  Workshops with MAMPU, NACSA Majlis Keselamatan Negara ​​and Chief Government Security Officer (CGSO) will be held in Oct and Nov 2018 to discuss the use and application of cloud servers in BIM data management. Cloud-based data sharing proposals will be presented during the workshop.
BIM Operators For JKR Projects Trained
8 training sessions for JKR BIM operators has been scheduled in Q3 until Q4 2018 at MyBIM Centre to support BIM Level 3 implementation by JKR.
PRODUCTIVITY
KPI P4-073
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
National BIM Guide completed | BIM Procurement Specification (JKR) rolled out Software/Hardware for JKR customized | JKR agreement to BIM 5 public projects secured BIM operators for JKR projects trained | BIM operators for JKR projects trained | BIM Level 3 adopted by 5 JKR projects
  Projects awarded
  Tender evaluation stage

## Slide 76
SPONSOR Datuk Ir Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Jasni Ismail
KPI LEADER CIDB
KPI DESCRIPTION MyBIM Centre established by Q2 2016
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4b - Establish reference centre to support the development and adoption of BIM and modern methods
This KPI is under the purview of IWG11.
MyBIM Centre was established in March 2016 at ABM Wilayah Tengah. The main function of myBIM Centre is to provide affordable, high quality training for industry players. The centre aspires to become the BIM One-Stop Centre, offering BIM technical services to the industry.
The new MyBIM Centre has been relocated to Menara Sunway. The centre is now fully completed and was officiated by the Minister of Works on 20 November 2017. t is equipped with up-to-date facilities including large capacity training rooms and the latest BIM software and hardware. It is opened to the public on weekdays from 9.00am to 5.00pm.
As of today, several organisations have utilised the facilities offered at myBIM Centre that includes MRT Corp., 3D Tech Parametric Sdn. Bhd., Jabatan Kerja Raya, Gabungan Jurutera Perunding Bumiputra and many more. Enhancements are on-going with plans to deploy more BIM softwares.
MyBIM Centre Address:
Level 11, Sunway Putra Tower
Lot 100, Jalan Putra
50350 Kuala Lumpur.
Tel: 03 4040 0399
Visit www.mybimcentre.com.my for more information on myBIM Centre.
MyBIM Centre is also being supported by MyBIM Satellites (regional BIM reference centres) established at University Malaysia Pahang (UMP), University Malaysia Perlis (UniMAP), University Technology Malaysia (UTM) and University Malaysia Sabah (UMS). These satellites will serve the need to train and accredit more BIM personnel nationwide.
MyBIM Centre Strengthened
BIM Guides, BIM Malaysian Government Initiatives, magazines and BIM Adoption Report 2016 published to help enrich BIM resources for public references
3 new softwares added (Tekla, Primavera & Bentley)
This KPI is 100% completed.
PRODUCTIVITY
KPI P4-074
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 100% | 2017 | 2018 | 2019 | 2020
MyBIM Centre launched | myBIM Center’s role as national reference center strengthened | myBIM Center’s role as national reference center strengthened | myBIM Center’s role as national reference center strengthened | myBIM Center’s role as national reference center strengthened

## Slide 77
SPONSOR Datuk Ir Elias Ismail
OWNER Hj. Razuki Ibrahim
OIC Jasni Ismail
KPI LEADER CIDB
KPI DESCRIPTION Online Reference Center established by Q4 2017
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4b - Establish reference centre to support the development and adoption of BIM and modern methods
This KPI is under the purview of IWG11.
MyBIM Centre web portal was completed on 18 May 2017 and will serve as an online reference centre. The portal is accessible via www.mybimcentre.com.my
The role of myBIM Portal is to promote the services provided at myBIM Centre such as BIM Studio, BIM Lab, Tehnology showcase and seminar hall.
The new and improved portal was commissioned recently and is now live via the same address.
This KPI is 100% completed.
PRODUCTIVITY
KPI P4-075
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 80% | 2017 Weightage : 20% | 2018 | 2019 | 2020
User Requirement Study on Online Reference Center completed | Online Reference Center launched and in operation |  |  | 

## Slide 78
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Haniza Soid Hamidi
OIC Mohd Jazlan Mohd Raffee
KPI LEADER CIDB
KPI DESCRIPTION At least 100 approved construction-related modules available online by Q4 2019
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4c -Implement competency and learning management system
CMS is a comprehensive set of online tools for tracking, measuring and improving the competency of construction personnel. Competency for these three major categories of personnel have been identified :
‘Kompetensi Kemahiran Personel Binaan’
‘Kompetensi Penyeliaan & Pengurusan Personel Binaan’
‘Kompetensi Pengurusan Kontraktor’.
As of Q2 2018, a total of 120 construction related modules have been converted into e-learning format and approved by the respective Committees within CIDB. These modules are ready to be uploaded into the Competency Management System (CMS) once it is fully functional which is targeted towards the end of Q2 2019.
The first version of CMS will consist of 32 modules incorporating 142 functions which include training, competency monitoring & reporting, assessment, certification & accreditation, financial management and enforcement. Additional modules are being identified.
Once uploaded, the CMS will be accessible by the construction personnel for online trainings from anywhere, 24 hours a day, seven days a week. Progress of trainings will be tracked and competency level of personnel updated. While most modules are free some will be charged a nominal fee.
PRODUCTIVITY
KPI P4-076
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 35% | 2017 Weightage : 50% | 2018 Weightage : 10% | 2019 Weightage : 5% | 2020
35 construction related modules converted and approved | 65 construction related modules converted and approved | Another 20 construction related modules converted and approved | 120 converted and approved construction related modules uploaded into the CIMS beginning Q2 2019 | 

## Slide 79
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Haniza Soid Hamidi
OIC Mohd Jazlan Mohd Raffee
KPI LEADER CIDB
KPI DESCRIPTION CMS operational and at least 80% personnel profiles in all 25 trades uploaded by Q4 2020
INITIATIVE P4 - Roll out technology advantage across project life-cycle advantage across project life-cycle
SUB-INITIATIVE P4c -Implement competency and learning management system modern methods
PRODUCTIVITY
KPI P4-077
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 15% | 2018 Weightage : 15% | 2019 Weightage : 20% | 2020 Weightage : 30%
Construction personnel profiles collected and updated | Construction personnel profiles collected and updated | Construction personnel profiles collected and updated | Construction personnel profiles collected and updated 20% of the personnel profiles uploaded into the CMS beginning Q2 2019 | Construction personnel profiles collected and updated 60% of the personnel profiles uploaded into the CMS by Q4 2020
Construction Personnel Profiles
Construction personnel profiles in all trades including the 25 skill trades as referred to Schedule 3 of CIDB Act (Act 520) will be collected and uploaded to CMS database by Q4 2020.
Until June 2018, 793,069 construction personnel profiles including 259,454 profiles belonging to the following occupational categories have been collected and updated.
All construction personnel profiles will be uploaded to the system database once CMS is fully operational.
Occupational Category | Local | Foreign | Total
Skills Worker | 69,169 | 3,517 | 72,686
Trainee | 81,234 | 14 | 81,248
Construction Project Manager | 82,199 | 3,063 | 85,262
Site Supervisor | 19,955 | 303 | 20,258
Total | 252,557 | 6,897 | 259,454

## Slide 80
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION 10,000 new users on myN3C portal registered by 2020 and 11 products on construction price and index published by 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
PRODUCTIVITY
KPI P5-078
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
2,000 new users on myN3C portal registered myN3C portal launched | 2,000 new users on myN3C portal registered 7 products on construction price and index published in myN3C portal | 2,000 new users on myN3C portal registered 7 products on construction price and index published in myN3C portal | 2,000 new users on myN3C portal registered 7 products on construction price and index published in myN3C portal | 2,000 new users on myN3C portal registered 4new product on construction price and index published in myN3C portal
The benefits of the myN3C portal are :-
It serves as a guide and indicator of price and cost behavior
Supports policy formulation
Supports appraisal of industry performance
Enables business risk assessment and planning
Serves as input for projection of construction demand
Enables CIDB to provide advisory services
Impact of myN3C at National Level
Khazanah Research Institutes (KRI) had used data derived from myN3C Portal to publish the book on ‘Making Housing Affordable’.
Malaysia Competition Commission (MyCC) ) had used the data derived from myN3C Portal to publish the report on ‘Market Review of Building Materials in Construction Industry’ in 2017.
This KPI is under the purview of IWG12.
National Construction Cost Centre (myN3C)
The National Construction Cost Centre portal or myN3C is an online data bank for all construction related costs
as follows :-
Building materials price, labor wage rate, machinery hire rate, & equipment purchase
Cost indices pertaining to building materials, labour, machineries & equipment.
Construction costs indices for major building categories.
myN3C Users
Until June 2018, 12,000 unique users have registered as follows :
Contractors (5760, 48%)
Consultants (2520, 21%)
Developers (1440, 12%)
Others (2280, 19%)
On average, documents were downloaded 4000 times monthly.
myN3C Products
7 products on construction prices and indices have been published as follows :-
Building Materials Price
Labour Wage Rate
Machinery Hire Rate & Equipment Purchase Price
Building Materials Cost Index
Building Labour Cost Index
Machinery & Equipment Cost Index
Building Cost Index

## Slide 81
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION Construction Cost Information on 60 models covering 18 categories published by Q3 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
60 Prototype Models
CIDB appointed RISM in 2016 to develop 60 prototype models of construction projects and these were completed in 2018. RISM developed 63 models covering 18 categories as follows:
Automation of Construction Cost Information (CCI) on the 60 Models
The automation process is 30% completed.
PRODUCTIVITY
KPI P5-079
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 35% | 2017 Weightage : 25% | 2018 Weightage : 15% | 2019 Weightage : 15% | 2020 Weightage : 10%
60 prototype models of construction project 50 % completed | 60 prototype models of construction project 100 % completed | 60 models of construction project & automation of construction cost information 50 % completed | 60 models of construction project & automation of construction cost information 100 % completed | Online Construction Cost Information Published
No | Categories | No. of Model(s)
1 | Office | 5
2 | Education | 6
3 | Health | 4
4 | Security | 1
5 | Mosque | 2
6 | Sports & Recreational Facilities | 2
7 | External Works | 1
8 | Residential | 12
9 | Hotel | 1
10 | Industrial | 7
No | Categories | No. of Model(s)
11 | Commercial | 15
12 | Parking | 1
13 | Highway & Road | 1
14 | Bridge | 1
15 | Jetty | 1
16 | Drainage, Irrigation & Flood Mitigation | 1
17 | Railways | 1
18 | Reclamation | 1
Total |  | 63

## Slide 82
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION Public & Private Tender Price Indices published by Q3 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
Tender Price Index (TPI)
Tender Price Index (TPI) is to measure the movement of construction prices over time (in both private and public projects) by establishing a comparison between the level of pricing in a sample of project and a standard price base.
Methodology of TPI
CIDB had adopted the methodology of TPI from the Royal Institution of Chartered Surveyor (RICS) United Kingdom in developing the TPI for the local construction industry. The Malaysia methodology which requires the enhancement to the RICS TPI was successfully completed within 6 weeks on 14 October 2016.
Ready Reckoner (RR)
The Ready Reckoner is the standard price base that will be used to develop the TPI. Royal Institution of Surveyor Malaysia (RISM) was appointed on 12 Dec 2017 as the consultant to develop the RR and to prepare the TPI with a completion date of 12 Dec 2018 .The RR will be developed by taking into consideration the following factors :
Standard Method of Measurement 2 (SMM2)
The base year is 2016
The location base rate is in the Klang Valley area (KL and Selangor)
As of June 2018, the Ready Reckoner is 60% completed.
PRODUCTIVITY
KPI P5-080
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 25% | 2017 Weightage : 15% | 2018 Weightage : 15% | 2019 Weightage : 35% | 2020 Weightage : 10%
Methodology of Tender Price Index completed | Ready Reckoner (RR) 30% completed | Ready Reckoner (RR) 100% completed | Automation of Tender Price Index completed | Online Tender Price Index published

## Slide 83
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION Lifecycle Costing Information covering residential, commercials and highways published by Q3 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
Life Cycle Costing (LCC)
LCC is an economic assessment that covers the total cost of an asset which converts initial and future costs including maintenance, operation and disposal costs throughout its life span to the present year. The study focuses on the LCC at the project level for selected construction projects, namely highway, social housing and office building.
Study on Proposal on Management of LCC Data
MCM Value was appointed to conduct the Life Cycle Costing Study and the study was completed on 15 Sep 2017. The LCC study was presented and endorsed at the IWG-12 meeting on 29 Dec 2017. The recommendations of the study are as follows :
Greater awareness and commitment from authorities for LCC data collection
CIDB will champion the preparation of National LCC Guide
More advanced study at elemental and component level to be pursued by CIDB
CIDB to regulate the LCC requirements to be submitted by facility management and maintenance contractors as part of their license renewal
CIDB to spearhead the possibility of enacting an Act of Parliament that requires the assets of certain value to have LCC database
Automation of LCC
The LCC automation system is at 30% progress and ready for tendering process.
PRODUCTIVITY
KPI P5-081
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 30% | 2019 Weightage : 20% | 2020 Weightage : 10%
Study on the Proposal for Management of Data Life Cycle Costing (LCC) for Construction Projects in Malaysia15% completed | Study on the Proposal for Management of Data Life Cycle Costing (LCC) for Construction Projects in Malaysia 100% completed | Automation of LCC 50% completed | Automation of LCC 100% completed | Online LCC published

## Slide 84
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION Labour and Plant Constant covering 4 major trade and type of plants published by Q3 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
Labour & Plant Constant (LPC)
LPC provides basic information for manpower and will be used as plant planning and a reference to gauge the efficiency of labour & plant constant in the building and civil works. It is aimed at achieving higher productivity as well as cost saving and maximizing margin. LPC facilitates the comparison and analyzing of project performance against the industry norms. At the same time, it also assists in rectifying or mitigating the problems as they exist.
Development of LPC
A technical committee has been established, chaired by JKR with members drawn from the industry, including MBAM, RISM, JUBM, UTM, UNITAR, UITM, UM and CIDB to steer the development of the LPC.
KH Alliance was appointed on the 6 Dec 2017 to develop the LPC for a period of 13 months to be completed by Jan 2019.
Until June 2018, the progress of the LPC development is 25%. The pilot test was done for the high rise apartment project for labour productivity in 3 trades for suspended floor consisting of concreting works, formwork and steel reinforcement works. In cooperation with JKR and the public sector, about 10 sites had been identified as case studies for data collection and analysis. The sites are in Putrajaya, N. Sembilan, Selangor Johor, Kuala Lumpur and Penang.
PRODUCTIVITY
KPI P5-082
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 50% | 2020 Weightage : 10%
 | Methodology for Labour & Plant Constant 30% completed | Methodology for Labour & Plant Constant 100% completed | Labour & Plant Constant on Site Studies 50% completed | Labour & Plant Constant on Site Studies 100% completed Labour & Plant Constant Published

## Slide 85
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION Awarded and prospective projects to be published online annually beginning 2018
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5b - Enhance awareness and certainty on upcoming construction demand
This KPI is under the purview of IWG13 and serves as one of the head of contents under KPI P5-085 on National Construction Industry Information Centre (NCIIC).
Approval From Central Agencies
The Economic Planning Unit (EPU) has agreed to share the annual aggregated data on government construction projects in social, security, administration and economic sectors. The aggregated data was submitted by the EPU regularly since 2016 for CIDB analysis.
Jabatan Kerajaan Tempatan (JKT) allows access to information on approved private construction projects with ‘Kebenaran Merancang (KM)’. This data is also analysed by CIDB.
JKT during technical meeting on 6 March 2018 agreed to integrate information on private upcoming projects with ‘Kebenaran Merancang (KM)’ from JKT’s One Stop Centre Portal (OSC) to NCIIC Portal. CIDB was requested to write officially to Director General, JKT for this purpose. A letter dated 14 March was sent to this effect. JKT had decided to get all state secretary office view on CIDB’s proposal for the integration and publication of private upcoming projects with ‘Kebenaran Merancang’ (KM) under each state in NCIIC Portal. A letter dated 12 April 2018 was issued by JKT to the state secretary office to this effect.
Data analytics on Construction Projects Awarded Nationwide
Information on construction projects awarded are published quarterly by CIDB in the Construction Quarterly Statistical Bulletin. The information is accessible from http://www.cidb.gov.my/index.php/my/maklumat-pembinaan/statistik-industri-pembinaan/buletin-statistik-pembinaan-suku-tahunan
Data analytics on construction projects awarded nationwide are published annually by CIDB in Chapter 2 of the Construction Industry Review and Prospects. The data analytic covers registration of construction projects according to categories, location, grades of contractors, types of work, contract size and projects awarded to foreign contractors. The data analytic is accessible from http:/www.cidb.gov.my/index.php/my/bidang-utama/ekonomi-pembinaan/penerbitan-statistik-dan-permintaan-pembinaan
The analysis on data for construction projects awarded in 2017 until Q1 2018 is being finalised with 70% completion.
PRODUCTIVITY
KPI P5-083
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 60% | 2017 Weightage : 10% | 2018 Weightage : 20% | 2019 Weightage : 5% | 2020 Weightage : 5%
Approval from central agencies on data sharing and data types secured Data analytics on construction projects awarded nationwide published | Data analytics on construction projects awarded nationwide published | Data analytics on prospective private construction demand published Data analytics on construction projects awarded nationwide published | Data analytics on prospective private construction demand published Data analytics on construction projects awarded nationwide published | Data analytics on prospective private construction demand published Data analytics on construction projects awarded nationwide published

## Slide 86
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION Construction demand on 8 major materials and workers in 7 trades to be published online annually beginning 2019
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5b - Enhance awareness and certainty on upcoming construction demand
This KPI is under the purview of IWG13 and serves as one of the head of contents under KPI P5-085 on National Construction Industry Information Centre (NCIIC).
Projection for 8 major materials and 7 trades of workers demand is generated through an automation system called Projection of Construction Demand (myPROJEXIS). The myPROJEXIS has been developed and used by CIDB since March 2016. The Manual for projection of construction demand describes the formula to calculate the upcoming demand for major materials and workers trade. The manual can be used as a guide in manually projecting the construction demand. The 8 major material and 7 trades of workers are as follows :
The projection covers the following categories:
Data Analytics on Projection of Materials Demand
Currently, the Projection for Construction and Material Demand for 2017 and 2018 has been published for internal use.
Data preparation on construction projects awarded for myPROJEXIS report is being updated.
Study on Workers Demand
Initial discussion with 3 potential quantity surveyor (QS) consultants was held in January and March 2018. They were requested to propose their methodology in this regard. The objective of the study is to develop workers constant projection of its demand according to different types of construction element, duplication of works, and workers trade.
Terms of Reference (TOR) for ‘Kajian Pembangunan Profil Pekerja dalam Industri Pembinaan’ was finalised on 25 June 2018. Request for Quotation (RFQ) will be issued in first week of July 2018.
PRODUCTIVITY
KPI P5-084
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 40% | 2017 Weightage : 25% | 2018 Weightage : 10% | 2019 Weightage : 15% | 2020 Weightage : 10%
Manual and system on projection of construction demand validated Interim projection on materials demand published | Projection on materials demand validated and published | Data analytics on projection on materials demand published 40% study on workers demand completed | Data analytics on projection on materials demand published 100% study on workers demand completed Interim projection on workers demand published | Data analytics on projection on materials and workers demand published
8 major materials: Steel reinforcement Ready mixed concrete Plywood Bricks Paint Sand (finishes) Glass Cement (finishes) | 7 trades of worker: Bricklayer Concretor Steel barbender Carpenter (formwork) Painter Plasterer General worker

## Slide 87
This KPI is under the purview of IWG13.
National Construction Industry Information Centre (NCIIC)
NCIIC aims to make available strategic information on construction industry through integration with different sources of information. The information released can be used to facilitate policy formulation, strategic planning, investment decision, scientific research and forecasting on matters related to the construction industry.
NCIIC framework with 16 head of contents approved are as follows:
Construction Projects (Domestic & Abroad) Contractors Construction Personnel Construction Professionals Construction Products and Material Manufacturer Construction Ratings (SHASSIC & QLASSIC) Sustainable Building Ratings (MyCREST) Industrialised Building System (IBS) Trade Agreement MyCESMM Construction Cost & Prices Upcoming Construction Projects Projection of Construction Demand Construction Industry Review and Prospects Decided Construction Cases Publication | 
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION NCIIC portal established with 16 construction related data integrated and updated quarterly by 2018
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5c - Integrate construction related data into National Construction Industry Information Centre (NCIIC)
PRODUCTIVITY
KPI P5-085
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 10% | 2020 Weightage : 10%
NCIIC framework with 16 head of contents approved. | Vendor to develop portal appointed 30% development of NCIIC portal completed | 100% development of NCIIC portal completed NCIIC portal and CIMS full integrated 16 of 16 NCIIC content published | Periodic portal and content maintenance carried out Promotion activities to enhance usage of portal conducted 5,000 unique portal users registered | Periodic portal and content maintenance carried out Promotion activities to enhance usage of portal conducted 5,000 unique portal users registered

## Slide 88
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION NCIIC portal established with 16 construction related data integrated and updated quarterly by 2018
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5c - Integrate construction related data into National Construction Industry Information Centre (NCIIC)
PRODUCTIVITY
KPI P5-085
PROGRESS REPORT UNTIL Q2 2018
Development of NCIIC Portal
Zanko Sdn Bhd, the vendor to develop NCIIC portal was appointed on 6 June 2017 and development is expected to be completed in May 2018. The development is being monitored by Technical Committee (TC) and Steering Committee (SC) headed by CIDB.
To date, the portal development progress is 76% with the following achievements:
Proof of Concept (POC) for Content Management System (CMS) endorsed by TC on 27 October 2017.
User Requirement Study (URS) framework endorsed by TC on 9 October 2017.
System Requirement Specification (SRS) was endorsed by TC on 6 November 2017.
System Database Design (SDD) with reviews by CIDB’s IT Division was endorsed by TC on 27 December 2017.
User Acceptance Test (UAT) 1 of 3 involving 4 modules (Trade Agreement, Decided Construction Cases, Upcoming Construction Demand and Construction Economic Report) was held on 21 December 2017 .
Preliminary Acceptance Test (PAT) 1 of 3 involving 4 modules was held on 15 January 2018
User Acceptance Test (UAT) 2.1 of 3 involving 2 modules (FAQ, Report Request) was held on 22 February 2018.
TC Meeting No. 3 on physical and financial progress was held on 8 March 2018.
MyCESMM and Construction Projects Module data format confirmed on 9 March 2018.
Access to Production Server of Centralised Information Management System (CIMS) for Projects, Contractors, Construction Personnel and Enforcement along with Portal MyCREST and IBS was granted on 19 March 2018.
Proposed portal design with 3 options was presented to Superintending Officer on 29 March 2018.
First phase testing on manual data upload and report generating for public and internal user.
Confirmation on portal design (fonts and colour scheme), layout and logo has been finalised on 6 June 2018.
Module development :
i. Construction Professionals:
Board of Engineers Malaysia (BEM) has given the engineering firms data, in forms of excel directory to CIDB.
Board of Quantity Surveyor Malaysia (BQSM) is pending for the permission from the BQSM’s Technical Committee.
LAM refused to integrate after several discussion and letters exchanged. It was proposed to link NCIIC Portal to LAM’s website for information on architects registration.
  ii. Construction Products and Material Manufacturer Module:
  Confirmation on data format for manual upload on 8 May 2018.
  Integration between NCIIC database and Certification of Local Construction Product & Material (CCPM) database completed on 4 June 2018.
  iii. Construction Rating Module (SHASSIC & QLASSIC) Module:
    User Acceptance Test (UAT) on 24 April 2018.
  15. Statistics for 13 modules are ready in the NCIIC Portal and being tested internally. These modules are:
Construction Projects (Domestic & Abroad) Contractors Construction Personnel Sustainable Building Ratings (MyCREST) Industrialised Building System (IBS) Trade Aggrement MyCESMM | viii. Construction Cost & Prices Upcoming Construction Projects Projection of Constrction Demand ConstructionIndustry Review and Prospects Decided Construction Cases Publication

## Slide 89
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION Construction Industry appraisal (Construction Industry Review & Prospect) published annually beginning 2016
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5c - Integrate construction related data into National Construction Industry Information Centre (NCIIC)
This KPI is under the purview of IWG13 and serves as one of the head of contents under KPI P5-085 on National Construction Industry Information Centre (NCIIC).
Construction Industry Review & Prospects is structured into 5 chapters with 4 standard chapters (Chapter 1 to Chapter 4) and a special chapter (Chapter 5) as follows:
Chapter 1: Malaysian Economy at a Glance
Chapter 2: Construction Projects, Contractors and Personnel
Chapter 3: Price, Wage and Hire Rates
Chapter 4: Construction Industry Prospect
Chapter 5: Focus Topic (Special chapter on the current construction industry and the theme of this chapter changes from year to year)
Construction Industry Review & Prospects is published annually by CIDB since 2016 and accessible via http://www.cidb.gov.my/index.php/my/bidang-utama/ekonomi-pembinaan/penerbitan-statistik-dan-permintaan-pembinaan.
The focus topic for Chapter 5 of the previous publications are as follows:
Construction Industry Review & Prospect 2015/2016 – Liberalisation of Construction Services.
Construction Industry Review & Prospect 2016/2017 – Competency Development in the Malaysian Construction Industry.
Construction Industry Review & Prospects 2017/2018
Structure of contents for Chapter 1 to 4 is confirmed.
Chapter 1: Malaysian Economy at a Glance - data preparation is completed
Chapter 2: Construction Projects, Contractors and Personnel - Information on category, subcategory and products in construction projects 2017 is being updated. Data on construction projects awarded until Q1 2018 is being updated with 70% completion.
Chapter 3: Data preparation for year 2015 until 2017 is being generated, filtered and arranged with 30% completion.
Chapter 4: Data preparation is being updated with 50% completion.
Chapter 5: Topic has been confirmed on IBS.
PRODUCTIVITY
KPI P5-086
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
Construction Industry Review & Prospect 2015/2016 published | Construction Industry Review & Prospect 2016/2017 published | Construction Industry Review & Prospect 2017/2018 published | Construction Industry Review & Prospect 2018/2019 published | Construction Industry Review & Prospect 2019/2020 published

## Slide 90
SPONSOR Sr. Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Md Yusoff
OIC Mohd Azmi Dzulkifli
KPI LEADER CIDB
KPI DESCRIPTION 7,500 Bumiputera contractors trained under Continuous Contractor Development Programme (CCD) per year (total of 37,500 by 2020)
INITIATIVE P6 - Advance SME Bumiputera capacity and capability-building
SUB-INITIATIVE -
This KPI is under the purview of IWG14.
Bumiputera contractors are required to be trained under Continuous Contractor Development Programme (CCD) in the areas of technical, managerial and financial. Each training day represents 10 CCD points and a maximum of 40 CCD points are awarded for training of more than 4 days. These CCD points are essential for renewal of contractor’s registration.
As of Q2 2018, 3,615 contractors had been trained against the target of 7,500 for 2018. A total of 32,065 contractors had been trained since 2016. The following statistic were recorded for Bumiputera Contractors trained under CCD based on states :
PRODUCTIVITY
KPI P6-088
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
7,500 Bumiputra contractors trained under CCD | 7,500 Bumiputra contractors trained under CCD | 7,500 Bumiputra contractors trained under CCD | 7,500 Bumiputra contractors trained under CCD | 7,500 Bumiputra contractors trained under CCD
NO | STATE | BUMIPUTERA CONTRACTORS TRAINED |  | 
 |  | 2016 | 2017 | 2018 (Q2)
1 | Johor | 883 | 909 | 256
2 | Melaka | 367 | 542 | 145
3 | Negeri Sembilan | 754 | 879 | 134
4 | Selangor & Kuala Lumpur | 2,886 | 2,764 | 1,213
5 | Perak | 796 | 825 | 196
6 | Kedah | 645 | 673 | 226
7 | Pulau Pinang | 1,582 | 1,484 | 315
8 | Perlis | 175 | 239 | 28
9 | Pahang | 668 | 794 | 164
10 | Terengganu | 432 | 474 | 127
11 | Kelantan | 1,189 | 1,306 | 232
12 | Sarawak | 2,598 | 2,872 | 346
13 | Sabah | 866 | 848 | 233
SUB TOTAL: |  | 13,841 | 14,609 | 3,615
TOTAL |  | 32,065 |  | 

## Slide 91
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Md Yusoff
OIC Mohd Azmi Dzulkifli
KPI LEADER CIDB
KPI DESCRIPTION 900 Bumiputera contractors trained to become Facility Management Contractors by 2020
INITIATIVE P6 - Advance SME Bumiputera capacity and capability-building
SUB-INITIATIVE -
This KPI is under the purview of IWG14.
Bumiputera contractors are given the opportunity to be trained in Facilities Management (FM) to enable them to be registered as Facilities Management Contractor (FMC). Only the owner or the director of the company are allowed to be trained. At the end of the training programme which consists of 13 Learning Packages (LP), the company will be awarded with Sijil Kecekapan Pengurusan (SKP) as a registration requirement with CIDB under two (2) specialization;
FM01 General Building & Infrastructure Facilities
FM02 Healthcare Facilities
As of Q2 2018 , 78 contractors against the target of 200 in 2018 have been successfully trained in FM.
PRODUCTIVITY
KPI P6-089
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 12% | 2017 Weightage : 22% | 2018 Weightage : 22% | 2019 Weightage : 22% | 2020 Weightage : 22%
Training module completed 100 Bumiputra contractors trained in FM | 200 Bumiputra contractors trained in FM | 200 Bumiputra contractors trained in FM | 200 Bumiputra contractors trained in FM | 200 Bumiputra contractors trained in FM
NO | SPECIALIZATION | NO. OF BUMIPUTERA CONTRACTORS TRAINED |  | 
 |  | 2016 | 2017 | 2018 (Q2)
1 | FM01 General Building & Infrastructure Facilities | 139 | 274 | 78
2 | FM02 Healthcare Facilities | - | - | -
SUB TOTAL |  | 139 | 274 | 78
TOTAL |  | 491 |  | 

## Slide 92
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Md Yusoff
OIC Mohd Azmi Dzulkifli
KPI LEADER CIDB
KPI DESCRIPTION 2,500 Bumiputera IBS contractors trained per year
INITIATIVE P6 - Advance SME Bumiputera capacity and capability-building
SUB-INITIATIVE -
This KPI is under the purview of IWG14.
Bumiputera contractors are given the opportunity to be trained in Industrialised Building System (IBS) to enable them to be registered as IBS Contractor. Only the owner or the director of the company are allowed to be trained. At the end of the training programme which consists of 10 Learning Packages (LP), the company will be awarded with Sijil Kecekapan Pengurusan (SKP) as a registration requirement with CIDB under these four (4) specialisations :
B01 – IBS : Prefabricated concrete system
B19 – IBS : Formwork system
B22 – IBS : Block system
B23 – IBS : Timber framing system
The following table shows the statistics of G1-G7 Bumiputera contractors trained in IBS covering six (6) IBS systems.
As of Q2 2018, another 665 G1-G7 Bumiputera contractors were trained in IBS against the target of 2,500 in 2018.
PRODUCTIVITY
KPI P6-090
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
2,500 Bumiputra contractors trained in IBS | 2,500 Bumiputra contractors trained in IBS | 2,500 Bumiputra contractors trained in IBS | 2,500 Bumiputra contractors trained in IBS | 2,500 Bumiputra contractors trained in IBS
NO | IBS SYSTEM | NO. OF BUMIPUTERA CONTRACTORS TRAINED |  | 
 |  | 2016 | 2017 | 2018 (Q2)
1 | Precast System | 952 | 1,127 | 287
2 | Steel Frame System | - | - | 164
3 | Timber Frame System | - | - | -
4 | Formwork System | 138 | 76 | 68
5 | Block System | 1,964 | 2,059 | 146
6 | Innovative System | - | - | -
SUB TOTAL: |  | 3054 | 3262 | 665
TOTAL |  | 6981 |  | 

## Slide 93
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Md Yusoff
OIC Mohd Azmi Dzulkifli
KPI LEADER CIDB
KPI DESCRIPTION 700 Bumiputera contractors trained in specialist trade per year (2017-2020)
INITIATIVE P6 - Advance SME Bumiputera capacity and capability-building
SUB-INITIATIVE -
This KPI is under the purview of IWG14.
Bumiputera contractors are given the opportunity to be trained in specialized trades/areas, either to enhance their knowledge and capability, or to enable them to be registered as a specialist contractor. Existing companies who have already registered with CIDB may send their suitable personnel to attend the training programme . However, for new contractors, only the owners or the directors of the companies are allowed to be trained. At the end of the training programme, the company/ personnel will be awarded either with a Sijil Kecekapan Pengurusan (SKP) or Sijil Kehadiran/ Pencapaian.
Specialist Trade Training
As of June 2018, 472 Bumiputera contractors against the target of 700 have been trained in the following areas :
PRODUCTIVITY
KPI P6-091
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 4% | 2017 Weightage : 24% | 2018 Weightage : 24% | 2019 Weightage : 24% | 2020 Weightage : 24%
6 specialist trades identified and approved by IWG14 6 specialist trades training module rolled out | 700 Bumiputra contractors trained in specialist trade | 700 Bumiputra contractors trained in specialist trade | 700 Bumiputra contractors trained in specialist trade | 700 Bumiputra contractors trained in specialist trade
Specialization / Area | Existing Company |  | New Company | 
 | SKP | Sijil Kehadiran/ Pencapaian. | SKP | Sijil Kehadiran/ Pencapaian.
BuiIding Information Modelling (BIM) |  | √ |  | √
Maintenance, Refurbishment and Operation (MRO) |  | √ |  | √
Piling Works (B05) |  | √ | √ | 
Demolition Work (B26) |  | √ | √ | 
Lifts & Escalators (M03) |  | √ | √ | 
Hospital Building Works (B29) |  | √ | √ | 
Specialization / Area | 2017 | 2018 (Q2)
Building Information Modelling (BIM) | 410 | 326
Piling Works (B05) | 105 | 40
Demolition Work (B26) | 76 | 70
Hospital Building Works (B29) | 114 | 36
Total | 705 | 472

## Slide 94
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Md Yusoff
OIC Mohd Azmi Dzulkifli
KPI LEADER CIDB
KPI DESCRIPTION 1,250 Bumiputera Entrepreneurs trained per year (2017-2020)
INITIATIVE P6 - Advance SME Bumiputera capacity and capability-building
SUB-INITIATIVE -
This KPI is under the purview of IWG14.
Bumiputera entrepreneurs refer to both existing contractors/ other construction industry players and young graduates/ youth aspiring to become one. CIDB with the collaboration of other interested organizations such as MRT Corp., BPKU, PUNB and local manufacturers has embarked on several programmes to develop existing/ future Bumiputera entrepreneurs.
Bumiputra Contractors Trained In Entrepreneurship
As of Q2 2018, 951 Bumiputera against the target of 1,250 have been trained in entrepreneurship in the following categories :
PRODUCTIVITY
KPI P6-092
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 4% | 2017 Weightage : 24% | 2018 Weightage : 24% | 2019 Weightage : 24% | 2020 Weightage : 24%
Training provider appointed | 1,250 Bumiputra contractors trained in entrepreneurship | 1,250 Bumiputra contractors trained in entrepreneurship | 1,250 Bumiputra contractors trained in entrepreneurship | 1,250 Bumiputra contractors trained in entrepreneurship
Collaborator | Existing Entrepreneur |  | Aspiring Youth | 
 | Programs | No. of Participant | Programs | No. of Participant
CEDAR (Centre For Entrepreneur Development & Research) | Vendor Development Programme | 42 | - | -
ABM | - |  | Entrepreneurship Awareness Programme throughout Malaysia | 909
TOTAL |  | 42 |  | 909

## Slide 95
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Md Yusof
OIC Mohd Azmi Dzulkifli
KPI LEADER CIDB
KPI DESCRIPTION 800 Bumiputera construction entrepreneurs receive Financial Assistance by 2020
INITIATIVE P6 - Advance SME Bumiputera capacity and capability-building
SUB-INITIATIVE -
This KPI is under the purview of IWG14.
As of Q2 2018, 154 Bumiputera construction entrepreneurs have received financial assistance worth RM146.7 Mn from the following agencies / institutions as follows:
PRODUCTIVITY
KPI P6-093
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 10% | 2017 Weightage : 22.5% | 2018 Weightage : 22.5% | 2019 Weightage : 22.5% | 2020 Weightage : 22.5%
Funding mechanism (by TERAJU) approved by IWG14 | 200 Bumiputera construction entrepreneurs receive Financial Assistance | 200 Bumiputera construction entrepreneurs receive Financial Assistance | 200 Bumiputera construction entrepreneurs receive Financial Assistance | 200 Bumiputera construction entrepreneurs receive Financial Assistance
NO | FINANCIER | 2018 (Q2) | 
 |  | NO. OF BUMIPUTERA CONSTRUCTION ENTREPRENUERS | FUNDING VALUE (RM)
1 | TERAJU | 6 | 8.8Mn
2 | KEMENTERIAN KERJA RAYA (KKR) via Skim Kumpulan Wang Amanah Kontraktor (SKWAK) | 7 | 2.8Mn
3 | PERBADANAN USAHAWAN NASIONAL BERHAD (PUNB) | 4 | 4.1Mn
4 | MAJLIS AMANAH RAKYAT (MARA) via PUTEK, SPIKE II, PUTERA & Usahawan Hardware schemes | 42 | 23Mn
5 | CREDIT GUARANTEE CORPORATION MALAYSIA BHD (CGC) | 95 | 108 Mn
TOTAL |  | 154 | 146.7Mn

## Slide 96
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Md Yusoff
OIC Mohd Azmi Dzulkifli
KPI LEADER CIDB
KPI DESCRIPTION Baseline study on Bumiputera participation in construction supply chain completed by Q4 2017
INITIATIVE P6 - Advance SME Bumiputera capacity and capability-building
SUB-INITIATIVE -
This KPI is under the purview of IWG14.
The study titled ‘Kajian Halatuju Strategik Bagi Meningkatkan Penglibatan Usahawan Binaan Bumiputera Di Dalam Rantaian Nilai Industri Pembinaan’ was undertaken by Price Waterhouse Coopers (PWC) and was completed on March 2018.
Objectives of the study:
To identify framework of Bumiputera participation in the construction industry
To identify the relevant segment for Bumiputera in the construction value chain
To identify the way forward for Bumiputera players in the construction industry in realizing national agenda
Key findings:
Small Bumiputera companies are faced with capacity and capability challenges that prevent increase in participation within profitable segments of the construction value chain. Three (3) key themes are identified to address the lack of meaningful Bumiputera participation;
Financing – Address information asymmetry in the provision of financing by commercial banks to small companies via better financial reporting and track record management as well as adoption of innovative risk allocation between financiers, borrowers and the government to mitigate inability of small companies to secure financing
Capability building – Enhance current training modules on both technical and business management training via sector-specific training to address the gap in relevant skills of small Bumiputera participants within key segments of the construction value chain
Government initiatives – Improve government programmes, ensuring that initiatives are more targeted towards building capacity and capability within key segments of the value chain
The pockets of profitable opportunities for Bumiputera are in the following areas :
Study Endorsed
The study was endorsed by IWG14 on 12 March 2018.
This KPI is 100% completed.
PRODUCTIVITY
KPI P6-094
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 10% | 2017 Weightage : 70% | 2018 Weightage : 20% | 2019 | 2020
Term of Reference for the study completed | 100% baseline study on Bumiputera participation in construction supply chain completed | Finding of study endorsed by IWG14 |  | 
Buildings
Quarrying of stone & clay
Cement, concrete & plaster
Demolition & site preparation
Transportation & machineries
Other construction products

## Slide 97
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Md Yusoff
OIC Mohd Azmi Dzulkifli
KPI LEADER CIDB
KPI DESCRIPTION Integrated database on Bumiputera companies in Malaysia established by Q4 2016
INITIATIVE P6 - Advance SME Bumiputera capacity and capability-building
SUB-INITIATIVE -
This KPI is in the preview of IWG14.
An integrated database on Bumiputera companies in Malaysia had been developed through the 'TerajuXchange' under TERAJU. It is a central system consisting information and incentives provided by the government for Bumiputera entrepreneurs. Two unique functions of TerajuXchange are :
it can be used as a medium to promote products and services produced by Bumiputera companies to local and international markets thus strengthening the business network
the system provides online software that can be used by local and international investors to assess the ability of a company based on its financial performance and projections.
The information had been integrated using data from 21 agencies/GLC/Corporate such as SSM, KLSE, SIRIM, Matrade, etc.
The TerajuXchange will be launched for utilization by relevant government agencies.
PRODUCTIVITY
KPI P6-095
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
2016 Weightage : 90% | 2017 Weightage : 10% | 2018 | 2019 | 2020
Agreement with key information providers approved by IWG14 secured Integrated database system on Bumiputera companies developed Integrated database on Bumiputera companies in construction completed | Integrated database on Bumiputera companies in construction launched |  |  | 

## Slide 98
2016 Weightage : 8% | 2017 Weightage : 30% | 2018 Weightage : 46% | 2019 Weightage : 16% | 2020
Inception report endorsed by IWG15 Study report endorsed by IWG15 | Study /Review on the scope of development of NSC Proposal on the new scope of development for NCS endorsed by IWG15 and BOD National Specification for Construction 10% completed | National Specification for Construction 70% completed | National Specification for Construction published National Specification for Construction launched | 
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Nazir Mohamad Nor
KPI LEADER CIDB
KPI DESCRIPTION National Specification for Construction introduced and published by 2018
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1a - Introduce National Specification for Construction
INTERNATIONALISATION
KPI I1-097
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG15.
National Specification for Construction (NSC) was introduced to integrate the public sector standard specifications and private sector. The aim of introducing the NSC is to reduce disputes, contradictions and uncertainties of opinions and eventually improve the uniformity of the specifications used in the construction industry. The proposed NSC will cover all specifications available including building materials, safety, environmental, methods, quality of workmanship and so on.
This specification is initially developed by National Building Specification (NBS) which was established in UK for the past 10 years. Through this successful program, CIDB took the initiative to adopt and adapt the NBS framework in developing NSC and propose to suit the contents with local requirement.
Technical Committee on NSC (TC-NSC) was established on 31 Mar 2017 to review the scope of the NSC development . The scope of work for NBS was derived from the following meetings:
TC-NSC Meeting No.1 was held on 5 Apr 2017.
TC-NSC Meeting No.2 was held on 14 Apr 2017.
Technical visit to NBS UK was held on 27 Apr2017 to overview the system performance of NBS for developing the scope of NSC.
TC-NSC Meeting No.3 was held on 6 Jun 2017. Revised scope of NSC completed & submitted. TC-NSC recommended the NSC to be developed with BIM capability.
Finalised TOR has gone through series of meeting:
Meeting with NBS was held on 27 Jul 2017, both party agreed on the commercial component.
IWG 15 Meeting No. 3 held on 8 Aug 2017, term of reference (TOR) has been endorsed by IWG members subject to further detail discussion with sub-committee.
TOR approved by sub-committee on 12 Sep 2017
NBS is expected to submit 3 options of business proposal on 20 Oct 2017. NBS only responded on 8 Dec 2017 highlighting the following issues:
1. Ownership of Intellectual Property (IP)
NBS wishes to retain its ownership of the IP on the platform system.
2. New content specification for Malaysia
NBS will share the IP on any content that will be developed for Malaysia as part of the JV Agreement.
CIDB E-Construct was instructed to undertake a parallel possibility of undertaking the above task for Malaysian market. Commercial and Technical Proposal submitted by NBS UK was generally accepted.
Two-tier Agreement has been drafted and pending final agreement from both parties.
Proposal on appointment of consultant was presented to CIDB Top Management on 19 April 2018. Final decision will be made once agreement between NBS and CIDB is finalized. CIDB is waiting for input from NBS on the Master Agreement.
A subsequent meeting between CIDB Top Management, E-Construct and Pertubuhan Arkitek Malaysia (PAM) is scheduled on 4 July 2018 to discuss “Way Forward” on the development of NSC in Malaysia.

## Slide 99
2016 | 2017 | 2018 | 2019 Weightage : 60% | 2020 Weightage : 40%
 |  |  | MOU documentation with 10 clients endorsed by IWG15 MOU signing ceremony with 10 clients on usage of NSC held | Promotion activities to enhance uptake of NSC conducted
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Nazir Mohamad Nor
KPI LEADER CIDB
KPI DESCRIPTION National Specification for Construction adopted by 10 Major Clients by 2020
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1a - Introduce National Specification for Construction
This KPI is under the purview of IWG15 and will commence in 2019.
INTERNATIONALISATION
KPI I1-098
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 100
2016 | 2017 | 2018 | 2019 Weightage : 50% | 2020 Weightage : 50%
 |  |  | Promotion activities to enhance uptake of NSC conducted 25 projects reported using NSC | Promotion activities to enhance uptake of NSC conducted 25 projects reported using NSC
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Nazir Mohamad Nor
KPI LEADER CIDB
KPI DESCRIPTION 50 projects adopt National Specification for Construction by 2020
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1a - Introduce National Specification for Construction
This KPI is under the purview of IWG15 and will commence in 2019.
INTERNATIONALISATION
KPI I1-099
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 101
2016 Weightage : 80% | 2017 Weightage : 20% | 2018 | 2019 | 2020
1st Stage of online system integrating local & imported products completed | Final Stage of online system integrating local & imported products completed and commissioned |  |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Sazali Che Amat
OIC Azlina Omar
KPI LEADER CIDB
KPI DESCRIPTION Online system for certification of construction materials conformance to standards in Schedule 4 of CIDB Act 520 established by Q4 2017
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1b - Heighten enforcement of compliance to mandatory material standards
This KPI is under the purview of IWG16.
The online system for certification of construction materials conformance to standards will enhance CIDB capability to enforce Act 520 (amendment 2011) schedule 4 which is related to construction materials. There are 13 construction materials listed in schedule 4 of Act 520 as detailed below :
Sanitary wares
Glazed and unglazed ceramic tiles
Ceramic pipes and pipe fittings
Cement
Prefabricated timber roof truss system
Precast concrete piles for foundation
Insulation materials
Glass
Fibre cement flat sheet not containing asbestos
Radiant barrier (thermal insulation foil)
Iron and steel products
Aluminium
Ready mix concrete
DagangNet Sdn Bhd was appointed to upgrade the existing “Sistem Pendaftaran Bahan Binaan Tempatan / Certification of Construction Product Material (CCPM)” to enable certification for imported construction products and materials / Pematuhan Pemerakuan Standard (PPS). The system was fully upgraded and operational with optimum performance in Q3 2017.
This KPI is 100% completed.
INTERNATIONALISATION
KPI I1-103
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 102
2016 Weightage : 4% | 2017 Weightage : 29% | 2018 Weightage : 29% | 2019 Weightage : 19% | 2020 Weightage : 19%
100 material compliance verification conducted Conformance report on material compliance visit published and endorsed by IWG16 | 500 material compliance verification conducted Conformance report on material compliance visit published and endorsed by IWG16 15% Procurement on equipment to test construction materials quality procured by Q4 2017 | 500 material compliance verification conducted Conformance report on material compliance visit published and endorsed by IWG16 85% Procurement on equipment to test construction materials quality procured by Q4 2018 | 500 material compliance verification conducted Conformance report on material compliance visit published and endorsed by IWG16 | 500 material compliance verification conducted Conformance report on material compliance visit published and endorsed by IWG16
SPONSOR Datuk Ir. Elias Ismail
OWNER Sazali Che Amat
OIC Azlina Omar
KPI LEADER CIDB
KPI DESCRIPTION 100% notice (N1/N5/N6) issued for materials non-compliance to standard following verification at construction sites commencing 2017
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1b - Heighten enforcement of compliance to mandatory material standards
This KPI is under the purview of IWG16.
Enforcement on Material Compliance
In 2016, 154 material compliance verification were conducted through 31 site visits where 44 N1/N5/N6 notices were issued on 44 non-compliance materials cases (100% issued).
In 2017, 506 material compliance verification were conducted through 2,208 site visits and 100% N1/N5/N6 notices were issued on non-compliance materials cases.
By Q2 2018, 489 material compliance verification were conducted through 1,497 site visits and 100% N1/N5/N6 notices were issued on non-compliance materials cases.
Conformance Report on Material Compliance
The conformance report on material compliance has been approved by IWG16 and published in 2018.
Procurement on Equipment to Test Construction Materials Quality
Testing equipment for the following construction materials are being procured as follows :
INTERNATIONALISATION
KPI I1-104
PROGRESS REPORT UNTIL Q1 2018
ANNUAL TARGET
TENDER | EQUIPMENT | STATUS | DELIVERY
1 | Resonant Fatigue Machine 500kN | Tender awarded | Delivered on 28 June 2018
2 | Resonant Fatigue Machine 300kN | Tender awarded | Scheduled in Aug 2018
3 | Universal Testing Machine 100kN & Universal Testing Machine 1000kN | Tender awarded | Delivered on 28 June 2018
4 | Salt Spray Chamber | Tender awarded | Scheduled in Aug 2018
5 | Bench Top OES Arc Spark | Tender awarded | Delivered on 9 April 2018
6 | UV/VIS/NIR/Spectrophotometer & Related instruments | Tender awarded | Delivered on 13 June 2018
7 | X-ray Fluorescence spectrometer & Related Instruments | Tender awarded | Delivered on 14 April 2018
8 | Weathering Chamber & Related Instruments | Tender awarded | Delivered on 14 April 2018
9 | Abrasion Tester, Emissiometer, Surface Compression Test Unit, Boiler, Pendulum Impact Test, Dimensional Test Rig & Related Instruments | Tender awarded | Delivered on 14 April 2018
10 | Brinell Hardness Tester, Rockwell Hardness Tester, Vickness Hardness Tester, Hot Mounting Machine, Grinder/Polisher Machine | Tender awarded | Delivered on 14 April 2018
11 | CNC Milling Machine | Tender awarded | Delivered on 14 April 2018
12 | Data Logging System with LVDT | To be tendered in Q3 2018 | Scheduled in Sept 2018

## Slide 103
2016 Weightage : 25% | 2017 Weightage : 25% | 2018 Weightage : 50% | 2019 | 2020
25 verification officers trained and accredited on approved categories 10 Training modules developed (cumulative) | 25 verification officers trained and accredited on approved categories 4 training modules developed | 50 verification officers trained and accredited on approved categories 4 Training modules developed |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Sazali Che Amat
OIC Azlina Omar
KPI LEADER CIDB
KPI DESCRIPTION 100 verification officers trained and accredited based on category and products by Q4 2018
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1b - Heighten enforcement of compliance to mandatory material standards
This KPI is under the purview of IWG16.
Competent Verification Officers
46 verification officers have been trained in iron and steel products in 2016.
109 verification officers were trained in scaffolding and iron & steel (1st module and advance module) in 2017.
Training in 2018
Iron and steel (Advance module) : 46 officers
Glass : 40 officers
Training and accreditation of officers are based on categories and products.
Training modules
10 training modules were developed in 2016.
6 training modules were developed in 2017
To date 3 more training modules are being developed as follows :
Radiant barrier
Fabricated Steel Structure
Sanitary Ware
Manual on product verification
Construction product verification manual for verification officers is 100% completed.
INTERNATIONALISATION
KPI I1-105
PROGRESS REPORT UNTIL Q4 2017
ANNUAL TARGET

## Slide 104
2016 Weightage : 30% | 2017 Weightage : 30% | 2018 Weightage : 20% | 2019 Weightage : 10% | 2020 Weightage : 10%
MyCESMM Reviewed and updated for conversion of MS CESMM Training on MyCESMM conducted 10 projects used MyCESMM | 10 projects used MyCESMM Final draft of MSCESMM completed Promotion activities to enhance uptake of MSCESMM conducted Training on MyCESMM conducted | 10 projects used MSCESMM / MyCESMM2 MSCESMM completed MyCESMM2 published Promotion activities to enhance uptake of MSCESMM / MyCESMM2 conducted | 10 projects used MSCESMM / MyCESMM2 Promotion activities to enhance uptake of MSCESMM / MyCESMM2 conducted | 10 projects used MSCESMM / MyCESMM2 Promotion activities to enhance uptake of MSCESMM / MyCESMM2 conducted
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Mohamad Nor
KPI LEADER CIDB
KPI DESCRIPTION 50 projects to adopt MS CESMM by Q4 2020
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1c - Enhance and expand adoption of MSCESMM
This KPI is under the purview of IWG17.
Malaysian Civil Engineering Standard Method of Measurement (MyCESMM) is a document that features the rules for measurement, definition, coverage and description for civil engineering works. It is used as a basis for the preparation of the Bills of Quantities for civil engineering works.
The purpose of MyCESMM is to deliver cost effective civil engineering projects through the adoption of best practices in the preparation of the Bills of Quantities (BQ)
MyCESMM is supported by 2 other documents:
A Guide to Civil Engineering Standard Method of Measurement
Library of Standard BQ Descriptions for Civil Engineering Standard Method of Measurement
10 Projects Using MSCESMM/MyCESMM2
In Q2 2018, the following 8 public and private projects were implemented using MyCESMM :
Projek Menaiktaraf Loji Rawatan Air Tualang, Kuala Krai, Kelantan. (KKLW – RM 48.9M)
Projek Bekalan Air Luar Bandar (BALB) Sistem Retikulasi, Negeri Pahang Zon 1 (KKLW-RM9.10M)
Projek Bekalan Air Luar Bandar (BALB) Sistem Retikulasi, Kudat, Sabah (Zon 10) (KKLW-RM10.41M)
Projek Bekalan Air Luar Bandar (BALB) Pulau Lihak-lihak, Semporna, Sabah (Zon 12c) (KKLW-RM31.78M)
Projek Bekalan Air Ke Kg. Jaya Bakti, Kg. Memanjang Dan Sekitarnya, Sabah (KKLW-RM34.05M)
Projek Bekalan Air Luar Bandar (BALB) Kawasan Mentong Merau/Mongkos, Bahagian Serian, Sarawak (KKLW-RM112.37M)
INTERNATIONALISATION
KPI I1-100
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
7) Projek Bekalan Air Luar Bandar (BALB) Kawasan Beluru, Bahagian Miri, Sarawak (KKLW-RM67.49M)
Projek Bekalan Air Luar Bandar (BALB) dari Kg. Manggut ke Kg Sg. Supa, Kg Medang, Kg. Tuei, dan Kampung Serabang, Betong Sawarak (KKLW-RM20.99)
Development of MSCESMM
Development of Malaysian Standard Civil Engineering Standard Method Measurement (MSCESMM) is 95% completed in 2018.
1st Draft of MSCESMM was approved by Technical Committee on Construction Practice (SIRIM) and advertised for public comments on 1 Feb 2017 - 31 Mar 2017.
Industry consultation was held on 22 & 23 Mar 2017 to solicit feedback from industry players on the MSCESMM draft. 33 organizations were invited and 100 participants turned up including JKR, JPS, JPP, IWK, MRT Corp., Gamuda, Prasarana.
Technical Committee on MSCESMM (TC-MSCESMM) workshop was held on 27 & 28 Apr 2017 to finalise comments received during industry consultation.
TC-MSCESMM meeting was held on 8 June 2017.
Second draft of MSCESMM was approved by Working Group on 17 Aug 2017 and TC-MSCESMM on 30 Aug 2017. It was published for second public comment on 15 Sept - 15 Nov 2017.
Second revision of Guideline and BQ library of MSCESMM were reviewed on 29 Sept 2017
Second public comments with justifications were re-submitted to SIRIM on 7 Dec 2017
Third draft of MSCESMM approved by TC-MSCESMM in February 2018

## Slide 105
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Mohamad Nor
KPI LEADER CIDB
KPI DESCRIPTION 50 projects to adopt MS CESMM by Q4 2020
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1c - Enhance and expand adoption of MSCESMM
INTERNATIONALISATION
KPI I1-100
PROGRESS REPORT UNTIL Q2 2018
An event 'Fast Forward with MyCESMM themed Adopting Standardisation in Infrastructure Works‘ for promoting MyCESMM was held on 12 Dec 2017. Contents include MoU signing ceremony, presentation of MyCESMM trainers certificates, presentations from 3 speakers from different perspectives of the usage of MyCESMM in technical agencies.
Memorandum of Understanding (MoU) with higher learning institutions ceremony was held on 27 March 2018 in conjunction with ICW 2018. 9 institutions involved are UM, UITM, USM, UTM, SEGI U, UTAR, TAR UC, UNIVERSITY OF READING MALAYSIA, AND TAYLORS. While INTI International Universities, IIUM and Jabatan Pendidikan Politeknik Malaysia are finalizing their MoU document with legal office.
Third draft of MSCESMM with justification were re-submitted to SIRIM on 14 Feb 2018 explaining on MSCESMM and MyCESMM2
Third draft of MSCESMM was published for third public comment on 1 – 31 March 2018.
MSCESMM was approved by SIRIM on 14 May 2018
SIRIM submitted MSCESMM for ministerial approval on 8 June 2018
Guide and BQ library document was finalised by Working group in January 2018 and endorsed by April 2018.
Workshop to finalised MyCESMM2, Guide and BQ Library was held on 23 - 24 April 2018. All final document has been endorsed by committee members.
MyCESMM2, Guide and BQ Library was completed in June 2018.
MyCESMM Promotion
A briefing session on MyCESMM was held on 19 Sept 2017 at JPS Penang to educate user on the method of measurement for high impact project.
22 agencies had signed MoU with CIDB to support the adoption of MyCESMM up to year 2016 which are :
Jabatan Pengairan dan Saliran Malaysia (JPS)
Jabatan Kerja Raya Sabah
Jabatan Kerja Raya Sarawak
Pengurusan Aset Air Berhad (PAAB)
Lembaga Lebuh Raya Malaysia (LLM)
Association of Consulting Engineers Malaysia (ACEM)
Lembaga Jurukur Bahan Malaysia (LJBM)
The Institution Of Engineers Malaysia (IEM)
Royal Institution of Surveyors Malaysia (RISM)
Indah Water Konsortium Sdn. Bhd. (IWK)
Jabatan Perkhidmatan Pembetungan (JPP)
Tenaga Nasional Berhad (TNB)
Jabatan Kerja Raya Malaysia (JKR)
Suruhanjaya Perkhidmatan Air Negara (SPAN)
Gamuda Berhad
Mass Rapit Tansit (MRT Corporation)
PLUS Malaysia Berhad
Prasarana Malaysia Berhad
Lembaga Jurutera Malaysia (BEM)
Kementerian Kemajuan Luar Bandar dan Wilayah (KKLW)
Real Estate and Housing Developers’ Association (REHDA)
Dewan Bandaraya Kuala Lumpur (DBKL)

## Slide 106
2016 | 2017 | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020 Weightage : 40%
 |  | MSCESMM on JKR/etc. engineering projects demonstrated and tested | Proposal paper to mandate MSCESMM approved by MOF | Circular on MSCESMM issued by MOF
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Mohamad Nor
KPI LEADER CIDB
KPI DESCRIPTION A circular issued by MOF to mandate the usage of MSCESMM for public projects by 2020
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1c - Enhance and expand adoption of MSCESMM
This KPI is under the purview of IWG17 and is scheduled to commence in Q3 2018.
INTERNATIONALISATION
KPI I1-101
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 107
2016 Weightage : 20% | 2017 Weightage : 25% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 15%
200 construction professionals trained with MyCSESMM in 10 trainings conducted | 250 construction professionals trained with MyCSESMM in 10 trainings conducted | 200 construction professionals trained on MSCESMM / MyCESMM2 in 10 trainings conducted | 200 construction professionals trained on MSCESMM / MyCESMM2 in 10 trainings conducted | 150 construction professionals trained on MSCESMM / MyCESMM2 in 10 trainings conducted
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Mohamad Nor
KPI LEADER CIDB
KPI DESCRIPTION 1000 construction industry professionals trained on MSCESMM by 2020
INITIATIVE I1- Internationalise construction practices and standards
SUB-INITIATIVE I1c - Enhance and expand adoption of MSCESMM
INTERNATIONALISATION
KPI I1-102
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG17.
MyCESMM Training
MyCESMM training was attended by the public and private sector with the following statistics :
Refresher course on train the trainer will be held on 25 July 2018
Train the trainer course will be held in August 2018
Trainers’ Training Kit for MyCESMM2 was endorsed by Technical Committee on 15 May 2018
Trainers’ Training Kit was completed on 29 June 2018 and will be printed out by mid July 2018
TRAINING | 2016 |  | 2017 |  | 2018 | 
 | NOS OF TRAINING | TRAINEES | NOS OF TRAINING | TRAINEES | NOS OF TRAINING | TRAINEES
MyCESMM | 15 | 321 | 13 | 276 | 3 | 66
Train the Trainer | 1 (7-10 Nov 2016) | 16 | 1 (11-14 Sept 2017) | 13 | - | -

## Slide 108
2016 Weightage : 30% | 2017 Weightage : 25% | 2018 Weightage : 15% | 2019 Weightage : 15% | 2020 Weightage : 15%
Study On Strengthen Access To Financing For Malaysian Champions Going Abroad In- Progress | Study on Overseas financing completed Study report endorsed by MOF, BNM and other relevant agencies 5 enhanced overseas project financing scheme communicated to main stakeholders | 2 enhanced overseas project financing scheme promoted | 1 enhanced overseas project financing scheme promoted | 2 enhanced overseas project financing scheme promoted
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Mohd Firdauz Mukhzanee Mohd Ghazali
KPI LEADER MOF & EXIM BANK
KPI DESCRIPTION 5 Enhanced Overseas Project Financing Scheme By 2020
INITIATIVE I2 - Strengthen Access to Financing for Malaysian Champion Going Abroad
SUB-INITIATIVE -
This KPI is under the purview of IWG18.
Study on Strengthening Access To Financing For Malaysian Champions Going Abroad
RSM-Arcadis was appointed in November 2016 to conduct the study and it was completed in August 2017. The study recommended 5 financing schemes comprising 12 products.
Study Endorsed by BNM, MOF & Other Agencies
The study was endorsed by the stakeholders via CITP IWG, TWG & MC held in July, August & October 2017 respectively. The 5 financing schemes were approved but 3 out of the 12 products were not approved.
5 Enhanced Overseas Financing Schemes Communicated to Stakeholders
Based on the study, the 5 financing schemes comprising the 12 products were as per table below :
INTERNATIONALISATION
KPI I2-106
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Scheme 1 : International Development Program | Scheme 2 : Focused Countries Currency Swap | Scheme 3 : Stimulus for Overseas Financing | Scheme 4 : Equity Investment Scheme | Scheme 5 : Loan Securitization
1. Guarantee Bond |  | 1. Interest Rate Support |  | 
2. Overseas Financing Procedure Advisory |  | 2. Insurance Premium Relief |  | 
3. Enhancement of MATRADE programme |  | 3. Credit Guarantee Expansion |  | 
4. Consortia Promotion Programme |  | 4. Improvement of Banking Term |  | 
5. Annual Construction Financing Symposium |  |  |  | 
2 Enhanced Overseas Financing Schemes Promoted
Communications with key stakeholders namely MOF & BNM was conducted on 28 Feb 2018 (meeting) & 30 Mac 2018 (letter). BNM has announced 2 currency swap agreement executed between Malaysia and Central Bank of Thailand & Central Bank of Indonesia effective from 2 January 2018.
A meeting has been arranged with the new Chief Secretary of Procurement Division in MOF on 20 July 2018 to obtain the endorsement and discuss further on the actions required by MOF on the proposed schemes, particularly for the GLIC Equity Financing, Stimulus for Overseas Financing and Securitization of Overseas Loans. The study will be disseminated to several stakeholders namely MOF, MOW, MITI, MATRADE, BNM, EXIM and IWG18 members for implementation and execution by Q3 2018 onwards. The study (executive summary version) will be made available for public as a guide and directory on the current financing schemes and products available in Malaysia for construction and construction related companies.

## Slide 109
2016 | 2017 Weightage : 25% | 2018 Weightage : 25% | 2019 Weightage : 25% | 2020 Weightage : 25%
 | SEF Grant For 4 Projects Approved | SEF Grant For 4 Projects Approved | SEF Grant For 4 Projects Approved | SEF Grant For 4 Projects Approved
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Mohd Firdauz Mukhzanee Mohd Ghazali
KPI LEADER MATRADE
KPI DESCRIPTION Services Export Fund (SEF) Grant For 16 Projects Approved By 2020 (4 Projects Per Year beginning 2017)
INITIATIVE I2 - Strengthen Access to Financing for Malaysian Champion Going Abroad
SUB-INITIATIVE -
This KPI is under the purview of IWG18.
Services Export Fund (SEF) is a fund allocated by the government and managed by MATRADE. The construction sector was identified as one of the eligible recipients. Information on SEF can be accessed through the website at www.matrade.gov.my/en/malaysian-exporters/services.../services-export-fund-sef. CIDB was appointed as a permanent representative in the technical evaluation committee. Further promotion to enhance awareness of the SEF is being undertaken under the Overseas Financing Procedure Advisory which is listed as one of the products under KPI i2-106.
SEF Grant For 4 Projects Approved In 2017
In 2017, the SEF was approved for 4 construction related companies for 7 projects as follows:-
INTERNATIONALISATION
KPI I2-107
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
NO | RECIPIENT | PROJECT | ACTIVITY
1 | Premier Construction Sdn Bhd | 1. British International School project, Myanmar | 2 b - Presentation to clients for assessing business/ project overseas
 |  | 2. University Udayana Hostel Development, Indonesia | 2 b - Presentation to clients for assessing business/ project overseas
 |  | 3. Presentation to Potential Clients, Yangon, Myanmar | 2 b - Presentation to clients for assessing business/ project overseas
2 | Probase Manufacturing Sdn Bhd | 4. Rehabiliation of road in Venilale - Hatulia, Timor Leste | 2 b - Presentation to clients for assessing business/ project overseas
 |  | 5. Feasibility Study On The Technical and Economic Aspect For The Construction of 241 km Rural Road In Senegal | 5 - Feasibility Study for specific international project overseas
3 | Sunway Construction Sdn Bhd | 6. Potential project in Myanmar | 2 b - Presentation to clients for assessing business/ project overseas
4 | Bina Puri Holdings Berhad | 7. Presentation to various India Ministries, India | 2 b - Presentation to clients for assessing business/ project overseas

## Slide 110
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Mohd Firdauz Mukhzanee Mohd Ghazali
KPI LEADER MATRADE
KPI DESCRIPTION Services Export Fund (SEF) Grant For 16 Projects Approved By 2020 (4 Projects Per Year beginning 2017)
INITIATIVE I2 - Strengthen Access to Financing for Malaysian Champion Going Abroad
SUB-INITIATIVE -
INTERNATIONALISATION
KPI I2-107
PROGRESS REPORT UNTIL Q2 2018
SEF Grant For 4 Projects Approved In 2018
In 2018, the SEF was approved for 13 construction related companies for several projects/events as follows:-
NO | RECIPIENT | PROJECT/EVENT | ACTIVITY
1 | Duriane Professionals S/B | 5th ASEAN-Korea Engineering Forum, Yangon, Myanmar | 1a - Speaker in International conference / forum in overseas
2 | Romstar Sdn Bhd | Guangdong, China Jan 2018 Petroexir Co. & Iranian Offshore Oil Company, Tehran, Iran 15-17 Jan 2018. BSR Refinery and Korea National Oil Corporation Vietnam (KNOC) in Quang Ngai & Ho Chi Minh on 6-7 Feb 2018. PGN Saka Pangkah Ltd. in Surabaya, Indonesia on 20-22 Feb 2018. | 2 b - Presentation to clients for assessing business/ project overseas
3 | Veritas Architects Sdn Bhd | Design Perspective Kochi Edition, India on 23 Feb 2018 | 1a - Speaker in International conference / forum in overseas
 |  | Holiday Inn Hotel Development in Katmandu, Nepal, 12-14 October 2017 ASAAS International School in Muscat, Oman 29-30 August 2017 Lingamaneni Township Private Ltd., Guntur, India, 6-8 Dec 2017 JW Marriot Hotel, Myanmar 13-14 Dec 2017 Muscat National Development & Investment Company in Oman on 20 Dec 2017 | 2a – Rendering services for projects undertaken in overseas
4 | Dreamedge Sdn Bhd | Mumbai, India Feb 2018 | 2 b - Presentation to clients for assessing business/ project overseas
5 | Global LNG Sdn Bhd | Offshore LNG Re-Gas Terminal Project in Kutubdia, Bangladesh on Mac 2018 | 5 - Feasibility Study for specific international project overseas
6 | MIT Innovation Sdn Bhd | Schlumberger, Exxon Mobil and Shell in the USA on 8-23 Oct 2017 | 2 b - Presentation to clients for assessing business/ project overseas
7 | Virtual Instrument & System Innovation Sdn Bhd | National Instruments Technical Symposium Indonesia in Feb 2018 eMethods in the Philippines on 13-15 Mac 2018 | 1a - Speaker in International conference / forum in overseas
8 | Global Success Hospitality S/B | World EQ Summit, Mumbai, India in Feb 2018 | 1a - Speaker in International conference / forum in overseas
9 | Melia Anggun Sdn Bhd | Business Management Corp in the Philippines on 5-8 March 2018 eMBM in the Philippines on 12-17 Mac 2018 eMethods in the Philippines on 13-15 Mac 2018 | 2 b - Presentation to clients for assessing business/ project overseas
10 | Signvest Sdn Bhd | PT Sinergi Patriot Kota Bekasi, Indonesia in Mac 2018 | 2 b - Presentation to clients for assessing business/ project overseas
11 | Infinecs Systems Sdn Bhd | 3 potential clients in China, 31 Jan - 8 Feb 2018 | 2 b - Presentation to clients for assessing business/ project overseas
12 | CMC Engineering S/B | Vietnam | 3 - Setting up of office in overseas
13 | Intensive Energy Sdn Bhd | Taiyo Koko Ltd, Osaka, Japan on 2 - 4 Apr 2018 | 2 b - Presentation to clients for assessing business/ project overseas

## Slide 111
2016 Weightage : 0% | 2017 Weightage : 0% | 2018 Weightage :20% | 2019 Weightage :40% | 2020 Weightage : 40%
 |  | 10% increase in number of overseas projects financed by Fis and government scheme 2 Malaysian players securing 2 overseas projects under the multi-lateral development banks & agencies | 15% increase in number of overseas projects financed by Fis and government scheme 2 Malaysian players securing 3 overseas projects under the multi-lateral development banks & agencies | 15% increase in number of overseas projects financed by Fis and government scheme 2 Malaysian players securing 5 overseas projects under the multi-lateral development banks & agencies
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Mohd Firdauz Mukhzanee Mohd Ghazali
KPI LEADER MOF & EXIM BANK
KPI DESCRIPTION 40% increase in number of overseas projects financed by FIs and government schemes by 2020 (from 2015 baseline)
INITIATIVE I2 - Strengthen Access to Financing for Malaysian Champion Going Abroad
SUB-INITIATIVE -
INTERNATIONALISATION
KPI I2-122
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG18 and will commence in Q3 2018.

## Slide 112
2016 Weightage : 12.5% | 2017 Weightage : 12.5% | 2018 Weightage : 25% | 2019 Weightage : 25% | 2020 Weightage : 25%
RM 1 billion worth of overseas projects won by Malaysian consortia and companies | RM 1 billion worth of overseas projects won by Malaysian consortia and companies | RM 2 billion worth of overseas projects won by Malaysian consortia and companies | RM 2 billion worth of overseas projects won by Malaysian consortia and companies | RM 2 billion worth of overseas projects won by Malaysian consortia and companies
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Muhammad Rizuan Hamzah
KPI LEADER CIDB & MATRADE
KPI DESCRIPTION RM 8 Billion worth of overseas projects won by Malaysian companies and/or consortia by 2020
INITIATIVE I3 - Support consortia formation and strengthen overseas market intelligence
SUB-INITIATIVE I3b - Ensure focused targeting of high potential export markets
INTERNATIONALISATION
KPI I3-110
PROGRESS REPORT UNTIL Q4 2017
ANNUAL TARGET
This KPI is under the purview of IWG18.
The statistics of projects won overseas are as follows:
As of Q2 2018, 4 projects were won by 3 Malaysian construction companies worth RM556.24 million in 2 countries which are UAE and Qatar. The details are as follows:-
NO | COMPANY | PROJECT | AMOUNT (RM Million)
1 | Eversendai Engineering | Structural steel works for One Za’abeel mix-used development Address Tower Residence II Primo luxury high and residential tower. | 272
2 | Muhibbah Engineering | 3. Design, Construction and Erection of Syncrolift and Travel Lift with Ancillaries and all Associate Works in Marsa Um Alhoul at Un Alhoul Special Economic Zone, Qatar for the Economic Zones Company, Qatar (MANATEQ) | 149
3 | Wah Seong Corporation Berhad | 4. Design, packaging and sale of gas compressor packages and associated plant and site facilities at Iraq | 135
TOTAL |  |  | 556
NO | ITEM | 2016 | 2017 | 2018 (Q2)
1. | No. of projects won | 75 | 17 | 4
2. | Project worth (RM) | 1.71 Billion | 3.14 Billion | 556.24 Million
3. | No. of companies | - | 6 | 3
4. | Project location | Qatar Cambodia Thailand India Bangladesh United Arab Emirates United Kingdom | Qatar Thailand India Bangladesh Lao PDR United Arab Emirates Saudi Arabia United Kingdom Vietnam | Qatar United Arab Emirates

## Slide 113
2016 Weightage : 0% | 2017 Weightage : 0% | 2018 Weightage : 70% | 2019 Weightage : 30% | 2020 Weightage : 0%
 |  | Framework for integration of International Database with CIMS completed Professional boards’ agreement to develop database on exports secured Criteria for exports developed by professional boards | Exporters database for consultants completed | 
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Muhammad Rizuan Hamzah
KPI LEADER CIDB
KPI DESCRIPTION One-stop integrated source for construction service providers established by 2019 and annually updated
INITIATIVE I3 - Support consortia formation and strengthen overseas market intelligence
SUB-INITIATIVE I3a - Facilitate consortia formation to promote scale of Malaysia players
INTERNATIONALISATION
KPI I3-123
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG18 and will commence in Q3 2018.

## Slide 114
2016 Weightage : 0% | 2017 Weightage : 0% | 2018 Weightage : 35% | 2019 Weightage : 35% | 2020 Weightage : 30%
 |  | 10 SMEs & 2 mid-tier Malaysian construction related players assisted | 10 SMEs & 2 mid-tier Malaysian construction related players assisted | 10 SMEs & 2 mid-tier Malaysian construction related players assisted
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Muhammad Rizuan Hamzah
KPI LEADER MATRADE
KPI DESCRIPTION 10 SMEs & 2 mid-tier Malaysian construction related players going overseas assisted every year
INITIATIVE I3 - Support consortia formation and strengthen overseas market intelligence
SUB-INITIATIVE I3b - Ensure focused targeting of high potential export markets
INTERNATIONALISATION
KPI I3-125
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG18 and will commence in Q3 2018.

## Slide 115
2016 | 2017 Weightage : 30% | 2018 Weightage : 40% | 2019 Weightage : 30% | 2020
 | SCORE version 2.0 finalized by December 2017 | SCORE version 2.0 system upgraded SCORE version 2.0 rolled out | SCORE version 2.0 implemented | 
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Mohd Yusoff
OIC Fatin Amirah Mohd Anor
KPI LEADER CIDB
KPI DESCRIPTION SCORE Version 2.0 rolled out by Q4 2018
INITIATIVE I4 – Intensify contractors’ capacity and capability building
SUB-INITIATIVE -
This KPI is under the purview of IWG20.
Universiti Utara Malaysia (UUM) was appointed on 25 May 2017 as the consultant to undertake the review on the SCORE 2.0 questionaires. First draft of SCORE Version 2.0 questionnaires was submitted by UUM on 15 Sept 2017.
The current SCORE has 7 parameters comprising business performance, financial capability, technical capability, project management, procurement management, best practices and management capability. SCORE version 2.0 include additional elements namely on current issues in construction industry, the CIDB amendment Act 520, safety features and questionnaires on capacity and capability of contractors to be export ready.
A workshop to review SCORE version 2.0 questionnaires was conducted on 15 Nov 2017 and attended by IWG20 committee members and representatives of stakeholders. The inputs from the workshop were agreed by IWG20 members and representative of stakeholders to be incorporated in the SCORE version 2.0. UUM forwarded the finalized questionnaires to CIDB on 15 Dec 2017.
A pilot project was conducted among a total of 13 companies to compare SCORE version 1.0 and 2.0. The results will be presented during the next IWG meeting which is schedule on 25 July 2018.
INTERNATIONALISATION
KPI I4-126
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 116
2016 | 2017 Weightage : 10% | 2018 Weightage : 20% | 2019 Weightage : 30% | 2020 Weightage : 40%
 | CIDB circular on mandatory G7 participation in SCORE issued for Sijil Perolehan Kerja Kerajaan (SPKK) renewal Consultant appointed to conduct study to improve G7 contractors SCORE rating Enhancement on existing modules on contractors report card in CIMS identified | Study to improve G7 contractors SCORE rating 100% completed and approved by IWG20 by Q2 2018 Programmes to improve G7 SCORE rating rolled out for implementation Contractor development monitoring system rolled out for implementation | Total 70 G7 contractors achieved 4 star SCORE rating and above Contractor development monitoring system implemented | Total 100 G7 contractors achieved 4 star SCORE rating and above
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Mohd Yusoff
OIC Fatin Amirah Mohd Anor
KPI LEADER CIDB
KPI DESCRIPTION Minimum 100 G7 contractors achieved 4 Star and above SCORE rating by 2020
INITIATIVE I4 – Intensify contractors’ capacity and capability building
SUB-INITIATIVE -
This KPI is under the purview of IWG20.
In 2017, 52 G7 contractors have achieved 4 star and above SCORE rating.
As of Q2 2018, 55 G7 contractors have achieved 4 star and above SCORE rating.
SPKK Renewal Circular
CIDB had issued circular Bil.1/2017 on 5 Dec 2017 titled “Syarat Pensijilan SCORE-CIDB Untuk Pembaharuan Sijil Perolehan Kerja Kerajaan (SPKK) Bagi Kontraktor Gred G7” to be enforced immediately. The objective of the circular is as a preparatory step for the implementation of SCORE rating in government procurement and to assist the contractor to identify the company’s weaknesses and to improve their capacity and capability to enable the contractor to compete at the international level.
The circular can be accessed through the following link :
http://www.cidb.gov.my/index.php/en/focus-areas/bahan-binaan/cidb-circular
Study to improve G7 SCORE rating
Universiti Utara Malaysia (UUM) was appointed in 19 Dec 2017 to conduct a study to improve G7 contractors SCORE rating with a completion date of 30 March 2018. The first draft of the study was submitted on 14 March 2018. The second draft was submitted on 21 March 2018. The study was completed in June 2018 and the final report was submitted on 6 July 2018. A list of training providers to provide essential trainings on SCORE parameters has been identified.
Contractor Report Card (CRC)
HeiTech Padu Sdn Bhd was appointed to develop the Centralized Information Management System (CIMS) and one of the modules included is the CRC. Contractors Continuous Development (CCD) point and various trainings undertaken have also been identified to be included to enhance the module on the CRC. As at June 2018, the CRC development is 70% completed.
Programmes To Improve G7 SCORE Rating
One of the programmes to improve G7 SCORE rating is to develop a database on training providers on the SCORE parameters.
INTERNATIONALISATION
KPI I4-127
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 117
2016 | 2017 Weightage : 40% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
 | Database on Certified Construction Project Managers established 140 Construction Project Managers Certified | List of Certified Construction Project Managers published 190 Construction Project Managers Certified | 250 Construction Project Managers Certified | 300 Construction Project Managers Certified
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Mohd Yusoff
OIC Fatin Amirah Mohd Anor
KPI LEADER CIDB
KPI DESCRIPTION Minimum 300 Construction Project Managers certified by CIDB by 2020 (2016 baseline = 110)
INITIATIVE I4 – Intensify contractors’ capacity and capability building
SUB-INITIATIVE -
This KPI is under the purview of IWG20.
Database on Certified Construction Project Managers
Database on Certified Construction Project Managers has been established. It is accessible through the CIDB website and CITP portal commencing 12 Oct 2017 through the following links :
http://www.cidb.gov.my/index.php/en/construction-info/list-of-certified-construction-project-managers
http://www.citp.my/2017/wp-content/uploads/CCPM-List.pdf
The database was last updated on 6 March 2018.
Construction Project Managers Certified
Trainings are conducted as follows :
The training of CCPM is based on modules prepared in accordance with the National Competency Standard (NCS). The trainings were conducted by CIDB Holdings with trainers from Association of Construction Project Managers (ACPM).
The training and certification of sewerage construction manager is based on modules in accordance with National Occupational Skill Standards (NOSS). The trainings were conducted by CIDB Holdings in collaboration with Indah Water Konsortium (IWK).
In 2017, 176 Construction Project Managers were certified by CIDB against the target of 140. IWG20 meeting No.6 approved for construction project manager to include certified construction project manager (CCPM) and sewerage project manager certified by CIDB.
As of Q2 2018, 183 Construction Project Managers were certified by CIDB against the target of 190 in 2018.
INTERNATIONALISATION
KPI I4-128
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 118
2016 | 2017 Weightage : 10% | 2018 Weightage : 25% | 2019 Weightage : 25% | 2020 Weightage : 40%
 | 500 G7 contractors personnel trained in construction technical and management courses | 1,500 G7 contractors personnel trained in construction technical and management courses | 2,500 G7 contractors personnel trained in construction technical and management courses | 4,000 G7 contractors personnel trained in construction technical and management courses
SPONSOR Sr Ida Zuraida Mohd Yusoff
OWNER Sr Azizah Mohd Yusoff
OIC Fatin Amirah Mohd Anor
KPI LEADER CIDB
KPI DESCRIPTION 4,000 G7 contractors’ personnel trained in construction technical and management courses by 2020
INITIATIVE I4 – Intensify contractors’ capacity and capability building
SUB-INITIATIVE -
This KPI is under the purview of IWG20.
In 2017, 706 G7 contractors' personnel were trained in technical and management courses organised by various agencies against the target of 500. These agencies include Pusat Latihan Bertauliah Kontraktor (PLBK), and CIDB Holdings together with Master Builders Association Malaysia (MBAM), Association of Construction Project Managers (ACPM), National Institute of Occupational, Safety and Health (NIOSH), etc.
As of Q2 2018, 1,230 G7 contractors' personnel were trained in finance, technical and management courses organised by various agencies against the target of 1,500.
The number of training by the various agencies are as follows :
The number of personnel trained under the 3 focus areas of training are as follows :
INTERNATIONALISATION
KPI I4-129
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
NO | TRAINING AGENCY | 2017 | Q2 2018
1 | PLBK | 579 | 744
2 | CIDBH | 127 | 486
TOTAL |  | 706 | 1,230
NO | FOCUS AREA | 2017 | Q2 2018
1 | Finance | 1 | 16
2 | Technical | 253 | 419
3 | Management | 452 | 795
TOTAL |  | 706 | 1,230

## Slide 119
2016 Weightage : 0% | 2017 Weightage : 0% | 2018 Weightage : 45% | 2019 Weightage : 35% | 2020 Weightage : 20%
 |  | 100% completion of benchmarking report on usage of Malaysian resources Domestic Sourcing Programme (DSP) for one mega project conducted | 100% completion of benchmarking report on usage of Malaysian resources Domestic Sourcing Programme (DSP) for one mega project conducted | 100% completion of benchmarking report on usage of Malaysian resources Domestic Sourcing Programme (DSP) for one mega project conducted
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Muhammad Rizuan Hamzah
KPI LEADER CIDB
KPI DESCRIPTION 30% Malaysian resources usage in foreign funded Mega-Projects in Malaysia by 2020
INITIATIVE I5 – Elevate the use of Malaysian construction resources in local and overseas Projects
SUB-INITIATIVE -
This is a new initiative endorsed during TWG4 meeting on 23 February 2018 with some of the activities initiated since 2017. The KPI is under the purview of IWG18.
Report on usage of Malaysian resources in Malaysia
Benchmarking report focusing on 4 big projects is 60% completed. The report is expected to be completed in Q4 2018.
Domestic Sourcing Programme (DSP)
A business meeting was held between 9 project owners under the Tun Razak Exchange project and local goods and services providers on 28 March 2018 to gauge projects owner’s interest in organizing a business matching/ DSP for related projects. Out of the 9 projects, 4 projects were identified to have several potential areas to be matched up with local resource providers.
Report on the business meeting held on 28 March 2018 has been finalised. Another specific meeting with related project owners (Landlease) was held on 24 May 2018 to identify details on potential opportunities.
INTERNATIONALISATION
KPI I5-133
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 120
2016 Weightage : 0% | 2017 Weightage : 0% | 2018 Weightage : 40% | 2019 Weightage : 35% | 2020 Weightage : 25%
 |  | 100% of completion of benchmarking report on usage of Malaysian resources (MATRADE) Directory of Professional Construction Services in Malaysia 2018/2019 published Domestic Sourcing Programme (DSP) for one project conducted | 100% completion of follow-through report on usage of Malaysian resources Domestic Sourcing Programme (DSP) for one project conducted | 100% completion of follow-through report on usage of Malaysian resources Directory of Professional Construction Services in Malaysia 2020/2021 published Domestic Sourcing Programme (DSP) for one project conducted
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Muhammad Rizuan Hamzah
KPI LEADER CIDB
KPI DESCRIPTION Double the percentage of Malaysian resources usage in Malaysian funded projects overseas by 2020 using 2017 baseline
INITIATIVE I5 – Elevate the use of Malaysian construction resources in local and overseas Projects
SUB-INITIATIVE -
This is a new initiative endorsed during TWG4 meeting on 23 February 2018 with some of the activities initiated since 2017. The KPI is under the purview of IWG18.
Report On Usage Of Malaysian Resources Overseas
20% completion of benchmarking report focusing on 1 big project (Battersea Power Station Development Company (BPSDC) identified.
Directory of Professional Construction Services
Google Survey Form is completed and ready for dissemination.
Domestic Sourcing Programme (DSP)
Business Matching between BPSDC and Malaysian construction related companies comprises of 25 companies was conducted on 22 April 2018 in London, United Kingdom. The objective is to provide opportunities for Malaysian construction and construction related companies to undertake and execute construction and construction related services as well as export of construction products and materials. Recommendation and follow up on the outcome of the business matching is expected to be held in Q4 2018.
INTERNATIONALISATION
KPI I5-134
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET