## Slide 1
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION Awarded and prospective projects to be published online annually beginning 2018
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5b - Enhance awareness and certainty on upcoming construction demand
This KPI is under the purview of IWG13 and serves as one of the head of contents under KPI P5-085 on National Construction Industry Information Centre (NCIIC).
Approval From Central Agencies
The Economic Planning Unit (EPU) has agreed to share the annual aggregated data on government construction projects in social, security, administration and economic sectors. The aggregated data was submitted by the EPU regularly since 2016 for CIDB analysis.
Jabatan Kerajaan Tempatan (JKT) allows access to information on approved private construction projects with ‘Kebenaran Merancang (KM)’. This data is also analysed by CIDB.
Data analytics on Construction Projects Awarded Nationwide
Information on construction projects awarded are published quarterly by CIDB in the Construction Quarterly Statistical Bulletin. The information is accessible from http://www.cidb.gov.my/index.php/my/maklumat-pembinaan/statistik-industri-pembinaan/buletin-statistik-pembinaan-suku-tahunan
Data analytics on construction projects awarded nationwide are published annually by CIDB in Chapter 2 of the Construction Industry Review and Prospects. The data analytic covers registration of construction projects according to categories, location, grades of contractors, types of work, contract size and projects awarded to foreign contractors. The data analytic is accessible from http://www.cidb.gov.my/index.php/my/bidang-utama/ekonomi-pembinaan/penerbitan-statistik-dan-permintaan-pembinaan
Progress Report Q3 2018
Approval from Central Agencies
Jabatan Kerajaan Tempatan (JKT) during technical meeting on 6 March 2018 agreed to integrate information on private upcoming projects with ‘Kebenaran Merancang (KM)’ from JKT’s One Stop Centre Portal (OSC) to NCIIC Portal. CIDB were requested to write officially to Director General, JKT for this purpose. A letter dated 14 March sent to this effect.
Jabatan Kerajaan Tempatan (JKT) had decided to get all state secretary's office view on CIDB’s proposal for the integration and publication of private upcoming projects with ‘Kebenaran Merancang’ (KM) under each state in NCIIC Portal. A letter dated 12 April 2018 was issued by JKT to the State Secretary office to this effect. State Secretary represent PBTs in their respective states.
Until 16 July 2018, 5 states (N. Sembilan, Perak, Selangor, Melaka, and Pulau Pinang) agree for information sharing, while another 6 states are yet to respond.
Data Analytics on Construction Projects Awarded Nationwide
Data for construction projects awarded analysis has been finalised with 100% completion in September.
PRODUCTIVITY
KPI P5-083
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 60% | 2017 Weightage : 10% | 2018 Weightage : 20% | 2019 Weightage : 5% | 2020 Weightage : 5%
Approval from central agencies on data sharing and data types secured Data analytics on construction projects awarded nationwide published | Data analytics on construction projects awarded nationwide published | Data analytics on prospective private construction demand published Data analytics on construction projects awarded nationwide published | Data analytics on prospective private construction demand published Data analytics on construction projects awarded nationwide published | Data analytics on prospective private construction demand published Data analytics on construction projects awarded nationwide published

## Slide 2
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION Construction demand on 8 major materials and workers in 7 trades to be published online annually beginning 2019
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5b - Enhance awareness and certainty on upcoming construction demand
This KPI is under the purview of IWG13 and serves as one of the head of contents under KPI P5-085 on National Construction Industry Information Centre (NCIIC).
Projection for 8 major materials and 7 trades of workers demand is generated through an automation system called Projection of Construction Demand (myPROJEXIS). The myPROJEXIS has been developed and used by CIDB since March 2016. The Manual for projection of construction demand describes the formula to calculate the upcoming demand for major materials and workers trade. The manual can be used as a guide in manually projecting the construction demand.
The projection covers the following categories:
Currently, the Projection for Construction and Material Demand for 2017 and 2018 has been published for internal use.
Progress Report Q3 2018
Study on Workers Demand
Initial discussion with 3 potential quantity surveyor (QS) consultants was held in January and March 2018. They were requested to propose their methodology in this regard. The objective of the study is to develop workers constant projection of its demand according to different types of construction element, duplication of works, and workers trade.
Data Analytics on Projection of Materials Demand
Data preparation on construction projects awarded for myPROJEXIS report is being updated. Due to data instability, some adjustment has been made to suit the projection’s requirement.
Study on Workers Demand
Terms of Reference (TOR) for ‘Kajian Pembangunan Profil Pekerja dalam Industri Pembinaan’ has been finalised on 25 June 2018. RFQ will be issued in first week of July 2018. As of September 2018, evaluation has been completed and sent to the secretariat. The current status is waiting decision from approval committee.
PRODUCTIVITY
KPI P5-084
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 40% | 2017 Weightage : 25% | 2018 Weightage : 10% | 2019 Weightage : 15% | 2020 Weightage : 10%
Manual and system on projection of construction demand validated Interim projection on materials demand published | Projection on materials demand validated and published | Data analytics on projection on materials demand published 40% study on workers demand completed | Data analytics on projection on materials demand published 100% study on workers demand completed Interim projection on workers demand published | Data analytics on projection on materials and workers demand published
8 major materials: Steel reinforcement Ready mixed concrete Plywood Bricks Paint Sand (finishes) Glass Cement (finishes) | 7 trades of worker: Bricklayer Concretor Steel barbender Carpenter (formwork) Painter Plasterer General worker

## Slide 3
This KPI is under the purview of IWG13.
National Construction Industry Information Centre (NCIIC)
NCIIC aims to make available strategic information on construction industry through integration with different sources of information. The information released can be used to facilitate policy formulation, strategic planning, investment decision, scientific research and forecasting on matters related to the construction industry.
NCIIC framework with 16 head of contents approved are as follows:
Development of NCIIC Portal
Zanko Sdn Bhd, the vendor to develop NCIIC portal was appointed on 6 June 2017 and development is expected to be completed in May 2018. The development is being monitored by Technical Committee (TC) and Steering Committee (SC) headed by CIDB.
Portal development progress is 50% as at Q1 2018 with following achievements:
Proof of Concept (POC) for Content Management System (CMS) endorsed by TC on 27 October 2017.
User Requirement Study (URS) framework endorsed by TC on 9 October 2017.
System Requirement Specification (SRS) was endorsed by TC on 6 November 2017.
System Database Design (SDD) with reviews by CIDB’s IT Division was endorsed by TC on 27 December 2017.
User Acceptance Test (UAT) 1 of 3 involving 4 modules (Trade Agreement, Decided Construction Cases, Upcoming Construction Demand and Construction Economic Report) was held on 21 December 2017 .
Preliminary Acceptance Test (PAT) 1 of 3 involving 4 modules was held on 15 January 2018
User Acceptance Test (UAT) 2.1 of 3 involving 2 modules (FAQ, Report Request) was held on 22 February 2018.
TC Meeting No. 3 on physical and financial progress was held on 8 March 2018.
MyCESMM and Construction Projects Module data format confirmed on 9 March 2018.
Access to Production Server of Centralised Information Management System (CIMS) for Projects, Contractors, Construction Personnel and Enforcement along with Portal MyCREST and IBS was granted on 19 March 2018.
Proposed portal design with 3 options was presented to Superintending Officer on 29 March 2018.
Construction Projects (Domestic & Abroad) Contractors Construction Personnel Construction Professionals Construction Products and Material Manufacturer Construction Ratings (SHASSIC & QLASSIC) Sustainable Building Ratings (MyCREST) Industrialised Building System (IBS) | 9. Trade Aggrement MyCESMM Construction Cost & Prices Upcoming Construction Projects Projection of Construction Demand Construction Industry Review and Prospects Decided Construction Cases Publication
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION NCIIC portal established with 16 construction related data integrated and updated quarterly by 2018
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5c - Integrate construction related data into National Construction Industry Information Centre (NCIIC)
PRODUCTIVITY
KPI P5-085
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 10% | 2020 Weightage : 10%
NCIIC framework with 16 head of contents approved. | Vendor to develop portal appointed 30% development of NCIIC portal completed | 100% development of NCIIC portal completed NCIIC portal and CIMS full integrated 16 of 16 NCIIC content published | Periodic portal and content maintenance carried out Promotion activities to enhance usage of portal conducted 5,000 unique portal users registered | Periodic portal and content maintenance carried out Promotion activities to enhance usage of portal conducted 5,000 unique portal users registered

## Slide 4
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION NCIIC portal established with 16 construction related data integrated and updated quarterly by 2018
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5c - Integrate construction related data into National Construction Industry Information Centre (NCIIC)
PRODUCTIVITY
KPI P5-085
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 10% | 2020 Weightage : 10%
NCIIC framework with 16 head of contents approved. | Vendor to develop portal appointed 30% development of NCIIC portal completed | 100% development of NCIIC portal completed NCIIC portal and CIMS full integrated 16 of 16 NCIIC content published | Periodic portal and content maintenance carried out Promotion activities to enhance usage of portal conducted 5,000 unique portal users registered | Periodic portal and content maintenance carried out Promotion activities to enhance usage of portal conducted 5,000 unique portal users registered
Portal development progress is 76% as at Q2 2018 with following achievements:
Overall development progress for NCIIC Portal:
  First phase testing on manual data upload and report generating for public and internal user.
  Confirmation on portal design (fonts and colour scheme), layout and logo has been finalised on 6 June 2018.
Development progress by module:
i. Construction Professionals:
Board of Engineers Malaysia (BEM) has given the engineering firms data, in forms of excel directory to CIDB.
Board of Quantity Surveyor Malaysia (BQSM) is pending for the permission from the BQSM’s Technical Committee.
LAM refused to integrate after several discussion and letters exchanged. It was proposed to link NCIIC Portal to LAM’s website for information on architects registration.
  ii. Construction Products and Material Manufacturer Module:
  Confirmation on data format for manual upload on 8 May 2018.
  Integration between NCIIC database and Certification of Local Construction Product & Material (CCPM) database completed on 4 June 2018.
  iii. Construction Rating Module (SHASSIC & QLASSIC) Module:
    User Acceptance Test (UAT) on 24 April 2018.
  3. Statistics for 13 modules are ready in the NCIIC Portal and being tested internally. These modules are:
Construction Projects (Domestic & Abroad) Contractors Construction Personnel Sustainable Building Ratings (MyCREST) Industrialised Building System (IBS) Trade Aggrement MyCESMM | viii. Construction Cost & Prices Upcoming Construction Projects Projection of Constrction Demand ConstructionIndustry Review and Prospects Decided Construction Cases Publication

## Slide 5
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION NCIIC portal established with 16 construction related data integrated and updated quarterly by 2018
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5c - Integrate construction related data into National Construction Industry Information Centre (NCIIC)
PRODUCTIVITY
KPI P5-085
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 10% | 2020 Weightage : 10%
NCIIC framework with 16 head of contents approved. | Vendor to develop portal appointed 30% development of NCIIC portal completed | 100% development of NCIIC portal completed NCIIC portal and CIMS full integrated 16 of 16 NCIIC content published | Periodic portal and content maintenance carried out Promotion activities to enhance usage of portal conducted 5,000 unique portal users registered | Periodic portal and content maintenance carried out Promotion activities to enhance usage of portal conducted 5,000 unique portal users registered
Portal development progress is 84% as at Q3 2018 with following achievements:
  Finalisation on data stability and statistics presentation on:
    Construction projects (18 July 2018)
    Contractors (18 July 2018)
    Construction personnel (19 July 2018)
    MyCESMM (24 July 2018)
  Decision to centralised all publication to NCIIC Portal (No duplication of function) with Corporate Communication CIDB on 27 July 2018. NCIIC Portal will act as a depository for all CIDB publication. Finalisation of publication categorisation according to topic/ menu.
  Approval from JPT Committee to charge for data request on 2 August 2018, subject to stability and readiness of data.
  PAT on 15 August 2018 for:
  Finalised statistics output for:
  SCORE/ MCORE (9 August 2018 & 3 September 2018)
  MyCREST (9 August 2018)
  Professional Bodies (20 August 2018)
  Framework for Stakeholders Dashboard, with audit trail functions developed on 28 August 2018.
  Finalisation on data formatting for Construction Cost & Prices on 29 August 2018.
  PAT on 14 September 2018 for:
      Publication - Functions for Payment Management System (PMS)
  UAT & rectification of UAT on 18 & 19 September 2018 for:
  Submit and verification for UAT 2 of 3 on 27 September 2018.
  Continuously testing the functions of PMS.
  Continuously improve on graph & charts.
  Trade Agreement
  Publication
  Projection of Construction Demand
  Decided Construction Cases
  Construction Projects
  Contractors
  Construction Personnel
  Sustainable Building Ratings – MyCREST
  Construction Ratings:
    - QLASSIC
    - SHASSIC
  Payment Gateway
  Data Request
  MyCESMM course
  Audit Trail

## Slide 6
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Che Saliza Che Soh
KPI LEADER CIDB
KPI DESCRIPTION Construction Industry appraisal (Construction Industry Review & Prospect) published annually beginning 2016
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5c - Integrate construction related data into National Construction Industry Information Centre (NCIIC)
This KPI is under the purview of IWG13 and serves as one of the head of contents under KPI P5-085 on National Construction Industry Information Centre (NCIIC).
Construction Industry Review & Prospects is structured into 5 chapters with 4 standard chapters (Chapter 1 to Chapter 4) and a special chapter (Chapter 5) as follows:
Chapter 1: Malaysian Economy at a Glance
Chapter 2: Construction Projects, Contractors and Personnel
Chapter 3: Price, Wage and Hire Rates
Chapter 4: Construction Industry Prospect
Chapter 5: Focus Topic (Special chapter on the current construction industry and the theme of this chapter changes from year to year)
Construction Industry Review & Prospects is published annually by CIDB since 2016 and accessible via http://www.cidb.gov.my/index.php/my/bidang-utama/ekonomi-pembinaan/penerbitan-statistik-dan-permintaan-pembinaan.
The focus topic for Chapter 5 of the previous publications are as follows:
Construction Industry Review & Prospect 2015/2016 – Liberalisation of Construction Services.
Construction Industry Review & Prospect 2016/2017 – Competency Development in the Malaysian Construction Industry.
Construction Industry Review & Prospect 2018 – IBS: The Way Forward.
Progress by Chapter as follows: Chapter 1: First draft completed.
Chapter 2: First draft completed.
Chapter 3: First draft is 50% completed.
Chapter 4: Sourced out to Maybank IB.
Chapter 5: First draft completed.
A meeting between CIDB and Maybank IB was held on 4 July 2018, at Bilik Keruing, Level 25, CIDB. CIDB and Maybank IB agreed to have a MOU, which CIDB will furnish aggregate data and in turn Maybank IB will prepare Chapter 4 (Prospect & Outlook) for CIDB.
MOU draft from CIDB was email to Maybank IB on 30 August 2018.
Framework for Chapter 5 (IBS) was finalised on 3 August 2018. First draft received on 6 September 2018.
Editing workshop to review the first draft of the publication was held on 19 to 21 September 2018.
PRODUCTIVITY
KPI P5-086
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
Construction Industry Review & Prospect 2015/2016 published | Construction Industry Review & Prospect 2016/2017 published | Construction Industry Review & Prospect 2017/2018 published | Construction Industry Review & Prospect 2018/2019 published | Construction Industry Review & Prospect 2019/2020 published

## Slide 7
2016 Weightage : 0% | 2017 Weightage : 0% | 2018 Weightage : 45% | 2019 Weightage : 35% | 2020 Weightage : 20%
 |  | 100% completion of benchmarking report on usage of Malaysian resources Domestic Sourcing Programme (DSP) for one mega project conducted | 100% completion of benchmarking report on usage of Malaysian resources Domestic Sourcing Programme (DSP) for one mega project conducted | 100% completion of benchmarking report on usage of Malaysian resources Domestic Sourcing Programme (DSP) for one mega project conducted
SPONSOR Sr Sariah Abd Karib
OWNER Sr Mohd Zaid Zakaria
OIC Muhammad Rizuan Hamzah
KPI LEADER CIDB
KPI DESCRIPTION 30% Malaysian resources usage in foreign funded Mega-Projects in Malaysia by 2020
INITIATIVE I5 – Elevate the use of Malaysian construction resources in local and overseas Projects
SUB-INITIATIVE -
This is new initiative endorsed in February 2018 with some of the activities initiated since 2017.
Report on usage of Malaysian resources in Malaysia
Benchmarking report is 60% completed focusing on 4 big projects identified (Forest City, Melaka Gateway, Tun Razak Exchange (TRX) and Bandar Malaysia. TRX is unique in that plot because of the land has been developed by 8 different clients.
Progress includes of collating information on usage of local resources from the project owners. Out of 11 projects owners, only 7 project owners has given feedback, with some of it is not complete. The latest feedback received from Melaka Gateway is on 17 August 2018. Further update on the development progress is still pending due to poor response from the project owners. This matters has been discussed during IWG 13 meeting dated 16 July 2018.
After the changes of government in May 2018, the new government is reviewing their stand on investment into these mega projects and their implementation. The new stand which is going to be announced during midterm review on 18 October 2018 and 2019 Budget on 3 November 2018 would effect this initiative cause of action.
Domestic Sourcing Programme (DSP)
A business meeting was held between 8 project owners and local goods and services providers on 28 March 2018 to gauge projects owner’s interest in organizing a business matching/ DSP for related project. Out of 8 projects, 4 projects were identified to have several potential areas to be matched up with local resource providers. The rest of 4 projects without potential for business matching are almost completed with most of the services providers and materials has been procured.
Another specific meeting with related project owner held on 24 May 2018 (Lendlease) to identified details on potential opportunities. Another direct business matching has been made between Lendlease and related resource providers in July 2018.
INTERNATIONALISATION
KPI I5-133
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET