## Slide 1
This KPI is under the purview of IWG8
Establishment of Construction Industry Competency Forum (CICF)
In June 2016, the CICF was established to study on existing construction related training programs and training providers. CICF is represented by related Technical & Vocational Education & Training (TVET) training providers from various government and private agencies.
Through CICF, 158 construction related TVET programs under 4 main clusters (building, civil & structural, mechanical and electrical) and 12 major training providers were identified.
The identified construction related training programs and all training providers are expected to use the same framework and approach in training and assessment so that a single certification and standardization of training courses could be implemented.
The first CICF workshop in March 2017 had concluded that in principle all construction skills training need to :
standardize the name for courses
use a common skill standard
standardize period of training
adopt a single certification
In the second workshop in October 2017, CIDB had proposed and presented the Competency Training Framework to the forum.
The forum had agreed that CIDB and Jab. Pembangunan Kemahiran (JPK) to further discuss and decide on the standardization of;
a) Competency Standards
b) Certification Schemes
Competency Standards
CIDB as the Industry Lead Body (ILB) and JPK has agreed to utilize the National Occupational Skills Standard (NOSS) as the competency standard.
Certification Schemes
Further discussion to streamline aspects of two certification schemes is on going between CIDB and JPK.
Sijil Kemahiran Malaysia (SKM)
This certification is under the purview of JPK and it conforms to the Malaysian Qualification Framework (MQF) requirements.
2) Sijil Kecekapan Kemahiran (SKK)
This certification is under the purview of CIDB in fulfilling the provision under Act 520.
Construction Training Registered
The registration will commence in Q2 2018.
2016 Weightage : 40% | 2017 Weightage : 40% | 2018 Weightage : 20% | 2019 | 2020
Construction Industry Competency Forum established Construction related TVET training programs and providers compiled and validated | Construction related trainings and programs streamlined Streamlined training programs validated and endorsed | Construction related trainings and programs registered by CIDB |  | 
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION All construction related training programs and institutions streamlined and registered by CIDB by Q4 2018
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1a - Streamline construction-related training programmes in Malaysia
PRODUCTIVITY
KPI P1-048
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET

## Slide 2
Discussion with JPK on streamlining of standards and certifications for construction industry have been held on 4th June 2018. As agreed by CICF meeting held on 15th January 2018, in principal it is agreed that JPK/CIDB to work closely to coordinate the certification by both agencies.
2016 Weightage : 40% | 2017 Weightage : 40% | 2018 Weightage : 20% | 2019 | 2020
Construction Industry Competency Forum established Construction related TVET training programs and providers compiled and validated | Construction related trainings and programs streamlined Streamlined training programs validated and endorsed | Construction related trainings and programs registered by CIDB |  | 
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION All construction related training programs and institutions streamlined and registered by CIDB by Q4 2018
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1a - Streamline construction-related training programmes in Malaysia
PRODUCTIVITY
KPI P1-048
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET

## Slide 3
2016 Weightage : 40% | 2017 Weightage : 40% | 2018 Weightage : 20% | 2019 | 2020
Construction industry blueprint on skilled trades completed Top ten highly demanded construction related skilled trades validated by industry | 1st draft on training maps for top ten skilled trades validated | Training maps for top ten skilled trades published |  | 
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION Top ten highly demanded skilled trades have training need analysis, occupational analysis and training maps by Q4 2018
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1a - Streamline construction-related training programmes in Malaysia
This KPI is under the purview of IWG8.
Construction Industry Competency Blueprint (CICB)
CICB will be the roadmap for the enhancement of the existing competence standards and the development of new competence standards. This blueprint will lead to other aspects of the competency processes such as the need for competence standards, the improvement of the existing competence standards, course of study and training pathways. This development will also lead to the introduction or the improvement of the assessment, internal and external verification processes and will later be identified as the Construction Industry Competency Framework (CICF).
This blueprint was completed by Saiful Training & Consultancy and presented and validated by IWG8 on 3 Aug 2016
The Top Ten High Impact Construction Related Skilled Trades
They are as follows:
Scaffolding Erection
Welding 3G and 6G
Wireman (PW1, PW2, PW3, and PW4)
Chargeman (A0, A1, B0, B1 and B4)
Gas Pipe Fitting (Fitting / Insulation)
Blasting & Painting
Non Destructive Testing (NDT)
Crane Operation
Plant Operation
Plumbing
Training Maps For Top Ten Skilled Trades
Saiful Training & Consultancy was appointed on 15 May 2017 to develop the training map for the 10 Construction Industry Occupational Title (CIOT) identified by IWG8.
Training Map Published
Final draft of the training maps for the top ten skilled trades were submitted by the consultant on 18 Dec 2017 and have been validated in IWG 8 meeting on 16th January 2018. Training map will be published in Q2 2018.
Training maps for the top ten skilled trades published and distributed to TVET agencies, related training centers and all CIDB offices.
This KPI is 100% completed.
PRODUCTIVITY
KPI P1-049
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET

## Slide 4
2016 Weightage : 10% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 30%
500 on-the-job apprentices in approved fields produced. | 700 on-the-job apprentices in approved fields produced. | 1000 on-the-job apprentices in approved fields produced. | 1,300 on-the-job apprentices in approved fields produced. | 1,500 on-the-job apprentices in approved fields produced.
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 5,000 on-the-job apprentices produced by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8.
Construction Apprenticeship Program
This program is aimed at producing high skill workers in three (3) main categories i.e.,
Construction Skilled Worker
Construction Site Supervisor
Construction Site Manager
This is done through placement of apprentices with various construction stakeholders such as Petronas Chemical Group, Malaysia Mobile Crane Operators Association (MMCOA), Malaysia Offshore Contractors Association (MOCA), PUNB, Jabatan Pembangunan Kemahiran, Lendlease, West Coast Expressway Sdn. Bhd., Ceteau Malaysia Sdn. Bhd., Muhibbah Engineering (M) Bhd, Vision Thermoplastic Sdn. Bhd., Putra Perdana Sdn. Bhd. and others.
Table below shows the number of on-the-job apprentices produced in various skill trades:
PRODUCTIVITY
KPI P1-050
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
CONSTRUCTION SKILLED WORKER | 2016 | 2017 | 2018 (Q3)
Mechanical Fitter | 60 | 117 | 0
Crane Operator | 10 | 31 | 106
Scaffolding | 39 | 109 | 124
Rigging | 20 | N/A | 4
Landscape, Building, Plumbing, Building Maintenance , Decorative Painting | 251 | 119 | 69
Architectural Drafting | 20 | 21 | 28
Welding | 34 | 35 | 53
Wet Skills, Blasting & Painting, Aircond | 52 | 165 | 250
Gas Pipe Installer | N/A | 18 | 136
Gas Pipe Insulation | N/A | N/A | 95
IBS | N/A | 17 | 21
Electrical | N/A | 130 | 67
Plant Operation | N/A | 80 | 62
TOTAL: | 486 | 842 | 1,015
SUPERVISORY | 2016 | 2017 | 2018 (Q3)
Site Supervisor (Building & Architectural, Civil, M&E) | 52 | 18 | 39
TOTAL: | 52 | 18 | 39
MANAGEMENT | 2016 | 2017 | 2018 (Q3)
Contractor Management | 66 | 0 | 0
TOTAL: | 66 | 0 | 0
TOTAL ACHIEVEMENT | 2016 | 2017 | 2018 (Q3)
Skilled Worker | 486 | 842 | 1,015
Supervisory | 52 | 18 | 39
Management | 66 | 0 | 0
TOTAL: | 604 | 860 | 1,054
To date, 2,518 against the target of 1,950 in 2018 on-the-job apprentices produced in various skill trades mentioned.

## Slide 5
This KPI is under the purview of IWG8
Training and certification of supervisory and management personnel
This training and certification program is aimed at producing site supervisors and site managers in four (4) main areas i.e.:
Building & Architectural
Civil & Structural
Mechanical
Electrical
Site supervisor and site manager can be certified through 3 methods:
Training and assessment
Assessment only
Interview
The training and assessment is conducted by Accredited Training Centre certified by CIDB.
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
3,000 supervisory and management personnel in approved fields trained and certified. | 3,000 supervisory and management personnel in approved fields trained and certified. | 3,000 supervisory and management personnel in approved fields trained and certified. | 3,000 supervisory and management personnel in approved fields trained and certified. | 3,000 supervisory and management personnel in approved fields trained and certified.
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 15,000 supervisory and management personnel (including QA/QC, site safety etc) trained and certified by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
PRODUCTIVITY
KPI P1-051
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
To date, 12,760 site supervisors and managers were trained and certified in the above four (4) main areas against the target of 8,250 until 2018.
TOTAL ACHIEVEMENT | 2016 | 2017 | 2018 (Q3)
Supervisory | 4123 | 3095 | 3010
Management | 966 | 880 | 686
TOTAL: | 5089 | 3975 | 3696

## Slide 6
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
20,000 construction personnel in approved CPD fields trained | 20,000 construction personnel in approved CPD fields trained | 20,000 construction personnel in approved CPD fields trained | 20,000 construction personnel in approved CPD fields trained | 20,000 construction personnel in approved CPD fields trained
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 100,000 construction personnel completed Continuous Professional Development training by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8
Continuous Professional Development (CPD)
CPD is a continuous program conducted by registered training providers to improve the knowledge and skills of construction personnel in technical, management and finance. Each participant will be eligible for CCD points.
To date, 170,080 personnel completed Continuous Professional Development (CPD) Program.
The targeted 55,000 construction personnel in approved CPD fields trained is achieved until 2018.
PRODUCTIVITY
KPI P1-052
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET

## Slide 7
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
20,000 graduates in approved skills trained and certified. | 20,000 graduates in approved skills trained and certified. | 20,000 graduates in approved skills trained and certified. | 20,000 graduates in approved skills trained and certified. | 20,000 graduates in approved skills trained and certified.
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 100,000 construction personnel graduated in construction related skills trained and certified by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8
Graduates In Approved Skills
These skills trainings are organized by Akademi Binaan Malaysia (ABM) and Pusat Latihan Bertauliah (PLB) that produce graduates in nine (9) construction related skills and accredited by CIDB.
The Table below shows the number of graduates produced :
To date, 75,483 construction personnel in approved construction related skills trained and certified in the above trades against the target of 55,000 until 2018.
PRODUCTIVITY
KPI P1-053
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
NO | TRADE CATEGORIES | 2016 | 2017 | 2018 (Q3)
1. | Building | 7348 | 8124 | 5958
2. | Industrialized Building System | 872 | 595 | 534
3. | Crane Operation | 1247 | 2390 | 2066
4. | Plant Operation | 2703 | 1755 | 1232
5. | Mechanical & Electrical | 7991 | 4397 | 4383
6. | Drafting | 855 | 634 | 580
7. | Civil | 375 | 150 | 176
8. | Welding | 4273 | 2619 | 1575
9. | Blasting & Painting | 511 | 383 | 230
10. | Non Destructive Testing | 967 | 455 | 105
TOTAL: |  | 37,142 | 21,502 | 16,839

## Slide 8
2016 Weightage : 20% | 2017 Weightage : 80% | 2018 | 2019 | 2020
Study to identify source countries for assessment centers completed and validated | 2 Skill Assessment Center in major foreign worker source country audited and registered |  |  | 
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 2 assessment centers in major foreign worker source countries established by Q4 2017
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8
Many foreign countries have recognised CIDB’s credibility in assessing and accrediting construction workers assessment centres. CIDB’s accreditation is seen as an added value in recognising the assessment centres overseas. Hence, many requests have been received from major foreign worker source countries for CIDB to accredit their respective assessment centres.
Skill Competency Assessment Centres Accredited In Foreign Worker Source Countries
The targeted numbers of assessment centers in major foreign worker source countries to be audited and registered have been achieved. However CIDB will continue to accredit assessment centers worker source countries from time to time as requested.
This KPI is 100% completed.
PRODUCTIVITY
KPI P1-054
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
NO | SOURCE COUNTRIES | 2016 | 2017 | 2018
1. | Bangladesh | 10 | 0 | 0
2. | India | 9 | 0 | 0
3. | Indonesia | 3 | 0 | 0
4. | China | 3 | 0 | 1
5. | Vietnam | 0 | 2 | 0
6. | Thailand | 1 | 0 | 0
7. | Myanmar | 1 | 0 | 0
8. | Pakistan | 1 | 0 | 0
 | SUB-TOTAL | 28 | 2 | 1
 | TOTAL | 31 |  | 

## Slide 9
2016 | 2017 Weightage : 25% | 2018 Weightage : 25% | 2019 Weightage : 25% | 2020 Weightage : 25%
 | 50 documents of Competency Standards, Training Modules and Assessment Questions to be developed/reviewed. 50 Nos of skill trainers/assessors undergo Train the Trainer/Assessors programs. | 50 documents of Competency Standards, Training Modules and Assessment Questions to be developed/reviewed. 50 Nos of skill trainers/assessors undergo Train the Trainer/Assessors programs. | 50 documents of Competency Standards, Training Modules and Assessment Questions to be developed/reviewed. 50 Nos of skill trainers/assessors undergo Train the Trainer/Assessors programs. | 50 documents of Competency Standards, Training Modules and Assessment Questions to be developed/reviewed. 50 Nos of skill trainers/assessors undergo Train the Trainer/Assessors programs.
SPONSOR Megat Kamil Azmi Megat Rus Kamarani
OWNER Ir Raslim Salleh
OIC Aljuffry Mohd Ariffin
KPI LEADER CIDB
KPI DESCRIPTION 200 competency related documents completed and 200 trainers undergo train the trainer program by Q4 2020
INITIATIVE P1 - Continue investment in human capital development in construction
SUB-INITIATIVE P1b - Strengthen reach, effectiveness and comprehensiveness of training
This KPI is under the purview of IWG8
In streamlining all training programs and training providers towards enhancing the competency of the skilled workers in the construction industry, CIDB also undertakes to develop the relevant Competency Standards, Training Modules and Assessment Questions
Until Q3 2018, 157 documents on Competency Standards, Training Modules and Assessment Questions were developed/reviewed against the target of 88 documents until 2018.
Until Q3 2018, 182 Nos of skill trainers/assessors under the Train the Trainer/Assessors programs against the target of 88 trainers and assessors until 2018.
PRODUCTIVITY
KPI P1-134
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
TYPE OF DOCUMENTS | 2016 | 2017 | 2018 (Q3)
Competency Standards | - N/A - | 17 | 3
Training Modules | - N/A - | 18 | 4
Assessment Questions | - N/A - | 81 | 34
TOTAL: | - N/A - | 116 | 41
TRAINER/ASSESSOR | 2016 | 2017 | 2018 (Q3)
Trainer | - N/A - | 92 | 90
Assessor | - N/A - |  | 
TOTAL: | - N/A - | 92 | 90