## Summary
Summary of Change Request (CR) for Convince Portal
Latest Update : 09/07/2019
No | Category | Total CR | CR Value (RM)
1 | Accepted & Done | 17 | 84000
2 | In Progress | 2 | 48000
3 | Accepted - Top Priority | 14 | 232000
4 | Accepted - Medium Priority | 3 | 75000
5 | Accepted - Low Priority | 1 | 18000
| Total : | 37 | 457000
No | Category | Total CR
1 | Keep-In-View (KIV) | 1
2 | Rejected | 7
3 | Rejected with workaround solution | 3
| Total : | 11

## Done
No | Reported Date | Reported By | CR Reference ID | Phase | Issues | Module / Functionality | Man days | [9 empty] | Cost | Remarks
[7 empty] | SA (requirement) | SA (document) | Developer | CMS Developer | DBA | SA (Internal Testing) |  | User (Testing)
[12 empty] | UAT | PAT | UAT | PAT | FAT
1 | 07.12.2017 | Zanko | CIDB/ZSB_NCIIC/CR001 | Proof Of Concept | Change CMS Platform from UMBRACO to DNN | Content Management System(CMS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DONE
2 | 30.01.2018 | Zanko | CIDB/ZSB_NCIIC/CR002 | Development | Change Scope Of Work. Initial contract, system vendor E-construct required to prepare the access to DB and perform scheduling work for integration activity for IBS module. Due to cost of the integration, ZSB has proposed to CIDB to get the direct access from CIDB BPM to perform the activity. | Industrial Building System (IBS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DONE | 0 | 0
3 | 30.01.2018 | Zanko | CIDB/ZSB_NCIIC/CR003 | Development | Change Scope Of Work. Initial contract, system vendor E-construct required to prepare the access to DB and perform scheduling work for integration activity for MyCREST module. Due to cost of the integration, ZSB has proposed to CIDB to get the direct access from CIDB BPM to perform the activity. | Sustainable Building Rating(MyCREST) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DONE | 0 | 0
4 | 25.01.2018 | CIDB | CIDB/ZSB_NCIIC/CR004 | Development | Change method from to Integration Upload Excel | Construction Cost & Prices (N3C) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DONE | 0 | 0
5 |  | CIDB | CIDB/ZSB_NCIIC/CR005 | Development | Change method from Upload Excel to Integration | Professional Bodies (BEM, LAM & BQSM) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DONE | 0 | 0
6 |  | CIDB | CIDB/ZSB_NCIIC/CR006 | Development | Change method from Publication to Integration | Upcoming Construction Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DONE | 0 | 0
7 | 28.03.2018 | Zanko | CIDB/ZSB_NCIIC/CR007 |  | Change of project implementation approach for NCIIC project to ensure project deliverables are met and aligned with the project objective. The new implementation approach is due to the constraints faced by Zanko related to the NCIIC portal integration process with the identified current CIDB systems | New Project Implementation Approach | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DONE | 0 | 0
8 | 30.01.2018 | Zanko | CIDB/ZSB_NCIIC/CR008 | Development | Proforma invoice number is not appear before user proceed to Payment Management System (PMS) | Payment Management System (PMS) | 1 | 1 | 5 | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 12000 | DONE | 12 | 13
10 |  | CIDB | CIDB/ZSB_NCIIC/CR010 | User Acceptance Test | User Registration Tambah function register System Admin untuk peranan Super Admin | User Management | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 8 | 1
17 |  | CIDB | CIDB/ZSB_NCIIC/CR017 | User Acceptance Test | Change word MSCESMM to MyCESMM. Apply to all (menu, form, screen, etc) | MyCESMM | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 0 | 0
20 |  | CIDB | CIDB/ZSB_NCIIC/CR020 | User Acceptance Test | Project Registration Could it be directed to the incomplete fields | MyCESMM | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 0 | 0
27 |  | CIDB | CIDB/ZSB_NCIIC/CR027 | User Acceptance Test | Update Requester Change section c. Cidb Section to c .Prices & Duration | Data Request | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 8 | 9
31 |  | CIDB | CIDB/ZSB_NCIIC/CR031 | User Acceptance Test | Document Link Display Document Link for the user (Request Details) | Data Request | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 8 | 0
33 |  | CIDB | CIDB/ZSB_NCIIC/CR033 | User Acceptance Test | Data Request (Email Notification) The system does not send an email to confirm on my application or whether it is processing. I only get an email after all complete | Data Request | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 8 | 0
36 |  | CIDB | CIDB/ZSB_NCIIC/CR036 | User Acceptance Test | List Cannot auto arrange by ascending or descending order. (allow to sort at header) | Audit Trail | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 8 | 0
37 |  | CIDB | CIDB/ZSB_NCIIC/CR037 | User Acceptance Test | Change the term ‘All Categories’ to just ‘All’ | Publication | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 8 | 0
39 |  | CIDB | CIDB/ZSB_NCIIC/CR039 | User Acceptance Test | The price for the Top Seller to be put under a new row, not on the same with the title | Publication | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | DONE | 8 | 0
[7 empty] | 10 | 10 | 14 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 84000

## InProgress
No | Reported Date | Reported By | CR Reference ID | Phase | Issues | Module / Functionality | Man days | [9 empty] | Cost | Remarks
[7 empty] | SA (requirement) | SA (document) | Developer | CMS Developer | DBA | SA (Internal Testing) |  | User (Testing)
[12 empty] | UAT | PAT | UAT | PAT | FAT
47 |  | CIDB | CIDB/ZSB_NCIIC/CR047 | User Acceptance Test | Changes of report structure and list of report | All Module with Statistics | 1 | 3 | 20 |  |  | 1 | 1 | 1 | 1 | 1 | 29000 | Ongoing Report structure is referring to report visualization and data query | 29 | 20
61 |  | CIDB | CIDB/ZSB_NCIIC/CR061 | Post go Live | Statistics - Add on remarks in each report (apply to all modules) Remarks: Internal: “Internal view only” Sys/ Super Admin: “Administrator view only” - Font: red, Calibri, 10 | Statistics | NA | NA | 15 | NA | NA | NA | 1 | 1 | 1 | 1 | 19000 | In progress impacts all reports | 19 | 20
[7 empty] | 1 | 3 | 35 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 48000

## Accepted - top
No | Reported Date | Reported By | CR Reference ID | Phase | Issues | Module / Functionality | Man days | [9 empty] | Cost | Remarks
[7 empty] | SA (requirement) | SA (document) | Developer | CMS Developer | DBA | SA (Internal Testing) |  | User (Testing)
[12 empty] | UAT | PAT | UAT | PAT | FAT
9 |  | CIDB | CIDB/ZSB_NCIIC/CR009 | User Acceptance Test | Additional Role Option 1 Add 2 new roles 1) Central Agencies 2) Other Agencies User first register as Public the System Admin update the Role. Option 2 Add 1 new role 1. CIDB Counterpart) which can be registered by System Admin or registered through the Portal as Public first then reuired System Admin to update user role. And, unlock (open) CIDB Executive role to non CIDB's email. | Registration | 1 | 1 | 1 | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 8000 | As per discussed with the technical team, Zanko proposed to go with Option 1 27/6 : module owner to view the respective internal report. Issue need to be discuss further with technical team. Decission: Accept as top list CR and proceed after final view.
11 |  | CIDB | CIDB/ZSB_NCIIC/CR011 | User Acceptance Test | User Management Allow System Admin to update User role for Public user - Combine no9 | User Management | 1 | 1 | 1 | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 8000 | combine into issue no 9
13 |  | CIDB | CIDB/ZSB_NCIIC/CR013 | User Acceptance Test | Registration Projects using MyCESMM The previous information does not appear on the List of Projects after submission. Add new tab " Project History" | MyCESMM | 1 | 3 | 32 | 6 | 4 | 2 | 2 | 1 | 1 | 1 | 53000 | 27/6 : accepted as top list CR
15 |  | CIDB | CIDB/ZSB_NCIIC/CR015 | User Acceptance Test | Manage Participants (Module Owner) Cannot edit training participant information. Should be able to update trainee/trainer details | [12 empty] | 27/6 : accept as top list CR
16 |  | CIDB | CIDB/ZSB_NCIIC/CR016 | User Acceptance Test | Trainer Registration Once user key-in IC, system auto populate other details if user already has records. | [12 empty] | * To confirm business process with user 27/6 : accept as top list CR
18 |  | CIDB | CIDB/ZSB_NCIIC/CR018 | User Acceptance Test | Projects Registration Add new fields to Projects Registration form i) Contact No. ii) Email Address | [12 empty] | 27/6 : accept as top list CR
19 |  | CIDB | CIDB/ZSB_NCIIC/CR019 | User Acceptance Test | Projects Registration To create Application ID (code to be given by CIDB) | [12 empty] | 27/6 : accept as top list CR
21 |  | CIDB | CIDB/ZSB_NCIIC/CR021 | User Acceptance Test | Project Registration After submit, there is no button to ask users to go back to project history | [12 empty] | Associate to issue regarding List of Project History 27/9 : related to issue no 13, combine
22 |  | CIDB | CIDB/ZSB_NCIIC/CR022 | User Acceptance Test | MyCESMM Courses (Trainee/Trainer) Propose to put the proper address consist of address, postcode, city, state for Course Venue | [12 empty] | 27/6 : accept as top list CR
24 |  | CIDB | CIDB/ZSB_NCIIC/CR024 | User Acceptance Test | Manage Participants Allow MO to search for participant by IC | [12 empty] | 27/6 : accept as top list CR
25 |  | CIDB | CIDB/ZSB_NCIIC/CR025 | User Acceptance Test | Module Owner dashboard Wujudkan features extract database untuk Trainee & Trainer profile ke format CSV atau Excel. | [12 empty] | 27/6 : accept as top list CR. Excel format only
35 |  | CIDB | CIDB/ZSB_NCIIC/CR035 | User Acceptance Test | Audit Trail >> Report Request Change ‘Confirmation’ to ‘Confirmed’ | Audit Trail | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | Status dirujuk pada status pada module Data Request. Perubahan yang dibuat pada module Audit Trail akn melibatkan perubahan pada penggunaan terma "Confirmation' di module Data Request. 27/6 : Accept as top list CR
46 |  | CIDB | CIDB/ZSB_NCIIC/CR046 | User Acceptance Test | Put watermark (CIDB logo) when user download report statistics | All Module with Statistics | 1 | 1 | 20 | NA | NA | NA | 1 | NA | NA | 1 | 24000 | 27/6 : accept as top list CR
26 |  |  |  |  | Search Directory Wujudkan features search untuk 5 module berikut: 1) Contractor 2) Consultant (BEM, LAM, BQSM) 3) Construction Personnel 4) CCPM 5) IBS | Search Directory | 5 | 11 | 22 | 5 | 5 | 2 | 1 | 1 | 1 | 1 | 54000 | kena propose new form format for Consultant 27/6 : accept as top list CR
48 |  | CIDB | CIDB/ZSB_NCIIC/CR048 | User Acceptance Test | Rearrange the Contractor results (second layer) Rearrange the resullt as below: a) Contractor Details b) Contact Information c) Grade, Category & Specialization | [12 empty] | 27/6 : accept as top list CR
50 |  | CIDB | CIDB/ZSB_NCIIC/CR050 | User Acceptance Test | Rearrange the Contractor profile (third layer) Rearrange the resullt as below: a) PPK Registration No: b) Name c) Contractor Type d) Grade e) Registration Validity | [12 empty] | 27/6 : accept as top list CR
51 |  | CIDB | CIDB/ZSB_NCIIC/CR051 | User Acceptance Test | There should be a function for whole portal log by activity by user. Example : Search by Name / Date Result : User login 11.15am User downloaded projects statistics 11.30am User request report 11.35am Audit Trail for login and logout also activity | Stakeholder Dashboard | 1 | 1 | 17 | NA | NA | NA | 1 | NA | NA | 1 | 21000 | impact all functions that need to be log 27/6 : Accept as top list CR
54 |  | CIDB | CIDB/ZSB_NCIIC/CR054 | User Acceptance Test | Registration Please add log-in activity for each user under detailed information | [12 empty] | 27/6 : accept as top list CR
56 |  | CIDB | CIDB/ZSB_NCIIC/CR056 | Post go Live | Data Request Statistic Application turn to cancelled if there is no reply within 30 Days from requester. | Data Request | 1 | 2 | 10 | NA | NA | NA | 1 | 1 | 1 | 1 | 17000 | need to create new task scheduler that run at the back-end 27/6 : accept as top list CR
57 |  | CIDB | CIDB/ZSB_NCIIC/CR057 | Post go Live | Publication - Dropdown SortBy : change All Product > All Publication | Publication | 1 | 1 | 1 | NA | NA | NA | 1 | NA | NA | 1 | 5000 | 27/6 : accept as top list CR
59 |  | CIDB | CIDB/ZSB_NCIIC/CR059 | Post go Live | Publication - Price information : smaller font and bold | [12 empty] | 27/6 : Accept as top list CR
45 |  | CIDB | CIDB/ZSB_NCIIC/CR045 | User Acceptance Test | Statistics System generate monthly schedule report for 3 modules: 1. Construction Project (Local & Oversea) 2. Contractor 3. Construction Personnel 4. CCPM | Statistics | 1 | 3 | 15 | N/A | 10 | 1 | 1 | 1 | 1 | 1 | 34000 | 27/6 : accept as top list CR
62 |  | CIDB | CIDB/ZSB_NCIIC/CR062 | Post go Live | Statistics - Add on list of report in the report description on every page. Apply to all modules. Differentiate between the Public and Internal view | [12 empty] | impact all reports 27/6 : Accept as top list CR
44 |  | CIDB | CIDB/ZSB_NCIIC/CR044 | User Acceptance Test | Additional Platform (Archive) Allow System Admin to download and upload monthly schedule report (in pdf format) for Public view | Others | 3 | 7 | 10 | 5 | N/A | 1 | 1 | 1 | 1 | 1 | 30000 | 27/6 : accept as top list CR
64 |  | CIDB | CIDB/ZSB_NCIIC/CR064 | Post go Live | Generate Excel platform - allow System Admin to create customized report in excel format. - System Admin are allowed to select certain fields or information - Modules involved: 1) Project Local 2) Contractor 3) CCPM | [12 empty] | 27/6 : Accept as top list CR. Need to clarify with technical on the workload involved.
[7 empty] | 17 | 32 | 130 | 16 | 19 | 9 | 12 | 8 | 8 | 11 | 232000

## Accepted - med
No | Reported Date | Reported By | CR Reference ID | Phase | Issues | Module / Functionality | Man days | [9 empty] | Cost | Remarks
[7 empty] | SA (requirement) | SA (document) | Developer | CMS Developer | DBA | SA (Internal Testing) |  | User (Testing)
[12 empty] | UAT | PAT | UAT | PAT | FAT
28 |  | CIDB | CIDB/ZSB_NCIIC/CR028 | User Acceptance Test | Manage Request/ Update Requester Please arrange according to column: 1. Request Date 2. User ID 3. Title 4. Category 5. Status Please ensure the header title can be auto arranged | Data Request | 1 | 3 | 7 | 10 | 2 | 1 | 1 | 1 | 1 | 1 | 28000 | 27/6 : accept as medium list CR | 28 | 9
32 |  | CIDB | CIDB/ZSB_NCIIC/CR032 | User Acceptance Test | Data Request Design Change arranged layout | [12 empty] | 27/6 : accept as medium list CR | 0 | 23
34 |  | CIDB | CIDB/ZSB_NCIIC/CR034 | User Acceptance Test | Data Request (Application) Suggest for an application Id for each application for the unique application, and not on the title. | [12 empty] | 27/6 : accept as medium list CR | 0 | 12
42 |  | CIDB | CIDB/ZSB_NCIIC/CR042 | User Acceptance Test | Add New Product Is it possible to take fields not used for System Admin. Is it advisable to take unused functions out? | Publication | 1 | 1 | 10 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 17000 | 27/6 : accept as medium list CR | 17 | 18
52 |  | CIDB | CIDB/ZSB_NCIIC/CR052 | User Acceptance Test | Top Request Suggest add the officer in charge for each request. | Stakeholder Dashboard | 2 | 5 | 17 | NA | 1 | 1 | 1 | 1 | 1 | 1 | 30000 | 27/6 : accept as medium list CR | 30 | 14
53 |  | CIDB | CIDB/ZSB_NCIIC/CR053 | User Acceptance Test | Top Request Add audit-trail for each request | [12 empty] | 27/6 : accept as medium list CR | 0 | 15
55 |  | CIDB | CIDB/ZSB_NCIIC/CR055 | User Acceptance Test | Registration Differentiate internal and external user by: a) having outline outside pie chart b) differentiate at the legend c) put a sign to differentiate both | [12 empty] | 27/6 : accept as medium list CR | 0 | 13
[7 empty] | 4 | 9 | 34 | 10 | 3 | 3 | 3 | 3 | 3 | 3 | 75000

## Accepted - low
No | Reported Date | Reported By | CR Reference ID | Phase | Issues | Module / Functionality | Man days | [9 empty] | Cost | Remarks
[7 empty] | SA (requirement) | SA (document) | Developer | CMS Developer | DBA | SA (Internal Testing) |  | User (Testing)
[12 empty] | UAT | PAT | UAT | PAT | FAT
40 |  | CIDB | CIDB/ZSB_NCIIC/CR040 | User Acceptance Test | Products List - Display option for page numbers. Ex: 10, 20… | Publication | 1 | 1 | 11 | NA | NA | 1 | 1 | 1 | 1 | 1 | 18000 | 27/6 : accept as low list CR | 18 | 16
41 |  | CIDB | CIDB/ZSB_NCIIC/CR041 | User Acceptance Test | Put phone no as mandatory requirement. Is the phone no have dash or have numbers only. | Publication | [11 empty] | 27/6 : accept as low list CR | 0 | 15
[7 empty] | 1 | 1 | 11 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 18000

## KIV
No | Reported Date | Reported By | CR Reference ID | Phase | Issues | Module / Functionality | Man days | [9 empty] | Cost | Remarks
[7 empty] | SA (requirement) | SA (document) | Developer | CMS Developer | DBA | SA (Internal Testing) |  | User (Testing)
[12 empty] | UAT | PAT | UAT | PAT | FAT
49 |  | CIDB | CIDB/ZSB_NCIIC/CR049 | User Acceptance Test | Ensure all search results can be downloaded, save as PDF & printed | Search Directory | 1 | 1 | 5 | NA | NA | NA | 1 | 1 | 1 | 1 | 11000 | 27/6 : need to clarify with en Zaid. KIV
[7 empty] | 1 | 1 | 5 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 11000

## Rejected
No | Reported Date | Reported By | CR Reference ID | Phase | Issues | Module / Functionality | Man days | [9 empty] | Cost | Remarks
[7 empty] | SA (requirement) | SA (document) | Developer | CMS Developer | DBA | SA (Internal Testing) |  | User (Testing)
[12 empty] | UAT | PAT | UAT | PAT | FAT
12 |  | CIDB | CIDB/ZSB_NCIIC/CR012 | User Acceptance Test | Registration Projects using MyCESMM Field: Type of Procurement. If the Public choose Others, please put an additional text area for user to input. | MyCESMM | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11000 | 27/6 : Rejected
14 |  | CIDB | CIDB/ZSB_NCIIC/CR014 | User Acceptance Test | Registration Projects using MyCESMM List of Projects should have another column to indicate by CIDB verification. Verbal Discussion with Cik Nis: - Verify projects’ information with CIMS - cth project yg register dgn MSCESSM di tendering stage. After few times, MO kena verify status project tu. - Module Owner verify maklumat project dengan system CIMS (manage projects). Filter and make short list dengan maklumat yg ada (state, project name, cost, date, etc.) | MyCESMM | 1 | 1 | 3 | N/A | N/A | 1 | 1 | 1 | 1 | 1 | 10000 | To be discussed further with Module owner and Cik Nis since this will impact the work procedure. 27/6 : Rejected
23 |  | CIDB | CIDB/ZSB_NCIIC/CR023 | User Acceptance Test | MyCESMM Manage Projects Don’t want to update and just want to see the info. But the system force to update. Could the popup just say no information is updated? | MyCESMM | 1 | 1 | 2 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 10000 | * To clarify with user to appear button or pop up message 27/6 : rejected
29 |  | CIDB | CIDB/ZSB_NCIIC/CR029 | User Acceptance Test | Confirmation Request Instead of 3day change it to 3 days. For more than 1 day, system auto calculate to days. | Data Request | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | 27/6 : rejected as CR. Solution : change label "day / s"
30 |  | CIDB | CIDB/ZSB_NCIIC/CR030 | User Acceptance Test | CIDB Section Add new field : Attachment Allow system admin to upload attachment. Could there be a display attachment back for system admin to propose a new format for data request. Please provide a new field for attachment. | Data Request | 1 | 1 | 5 | N/A | 1 | 1 | 1 | 1 | 1 | 1 | 13000 | 27/6 : Rejected
38 |  | CIDB | CIDB/ZSB_NCIIC/CR038 | User Acceptance Test | Automatically saw the Categories & Products, NOT the Top Sellers. The Top Sellers could be put optionally at the bottom | Publication | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 8000 | To be discussed further with business unit 27/6 : Rejected. Reword top seller title.
43 |  |  | CIDB/ZSB_NCIIC/CR043 |  | to include GST platform calculation to relace back end calculation. Example: 6% to 0% (DROP) | Publication | 1 | 1 | NA | NA | NA | 1 | 1 | 1 | 1 | 1 | 7000 | not recommended to change cause will impact the whole dnn formula
58 |  | CIDB | CIDB/ZSB_NCIIC/CR058 | Post go Live | Publication - Addon Publisher information in product details | Publication | 1 | 1 | NA | NA | NA | NA | 1 | 1 | 1 | 1 | 6000 | no need customization, just insert publisher information in product description field. If need to add Publisher field, the impact is huge, 20 developer mandays 27/6 : agree with work around solution. If required by en zaid, it will be put under future enhancement
60 |  | CIDB | CIDB/ZSB_NCIIC/CR060 | Post go Live | Publication - Change trolley logo to basket logo - Change Add to Cart > Add to Basket | Publication | 1 | 1 | 3 | NA | NA | NA | 1 | 1 | 1 | 1 | 9000 | 27/6 : Rejected
63 |  | CIDB | CIDB/ZSB_NCIIC/CR063 | Post go Live | Changes of current design (Homepage) | Design | 1 | 3 | NA | 20 | NA | NA | 1 | 1 | 1 | 1 | 28000 | developer's mandays is including ui designer mandays 27/6 : Rejected. Put into future enhancement.
[7 empty] | 10 | 12 | 17 | 22 | 2 | 7 | 10 | 10 | 10 | 10 | 110000