## Slide 1
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION 10,000 new users on myN3C portal registered by 2020 and 11 products on construction price and index published by 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
National Construction Cost Centre (myN3C)
The National Construction Cost Centre portal or myN3C is an online data bank for all construction related costs as follows :-
1. Building materials price, labor wage rate, machinery hire rate, & equipment purchase
2. Cost indices pertaining to building materials, labour, machineries & equipment.
3. Construction costs indices for major building categories.
myN3C Users
Until September 2018, more than 12,500 unique users have registered as follows :-
Contractors (3668, 29%)
Consultants (1935, 15%)
Developers (906, 7%)
Government (711, 6%)
Manufacturer (251, 2%)
Supplier (174, 1%)
GLC (278, 2%)
Financial Institution (234, 2%)
Others (4343, 35%)
On average, documents were downloaded 4000 times monthly.
myN3C Products
7 products on construction prices and indices have been published as follows :-
Building Materials Price
Labour Wage Rate
Machinery Hire Rate & Equipment Purchase Price
Building Materials Cost Index
Building Labour Cost Index
Machinery & Equipment Cost Index
Building Cost Index
The benefits of the myN3C portal are :-
It serves as a guide and indicator of price and cost behavior
Supports policy formulation
Supports appraisal of industry performance
Enables business risk assessment and planning
Serves as input for projection of construction demand
Enables CIDB to provide advisory services
Impact of myN3C at national level
1. Khazanah Research Institutes (KRI) had used data derived from myN3C Portal to publish the book on ‘Making Housing
Affordable’.
2. Malaysia Competition Commission (MyCC) ) had used the data derived from myN3C Portal to publish the report on ‘Market
Review of Building Materials in Construction Industry’ in 2017.
PRODUCTIVITY
KPI P5-078
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
2,000 new users on myN3C portal registered myN3C portal launched | 2,000 new users on myN3C portal registered 7 products on construction price and index published in myN3C portal | 2,000 new users on myN3C portal registered 7 products on construction price and index published in myN3C portal | 2,000 new users on myN3C portal registered 7 products on construction price and index published in myN3C portal | 2,000 new users on myN3C portal registered 4new product on construction price and index published in myN3C portal

## Slide 2
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION Construction Cost Information on 60 models covering 18 categories published by Q3 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
60 Prototype Models
CIDB appointed RISM in 2016 to develop 60 prototype models of construction projects and these were completed in 2018 covering 18 categories as follows: ; (1) Office – 4 models, (2) Education – 3 models, (3) Health – 6 models, (4) Security – 4 model, (5) Masjid – 1 models, (6) Sports & Recreational Facilities – 3 models, (7) External Works – 2 model, (8) Residential – 9 models, (9) Hotel – 3 model, (10) Industrial – 4 models, (11) Commercial – 1 model, (12) Parking – 2 model, (13) Highway & Road – 7 model, (14) Bridge – 4 model, (15) Jetty- 1 model, (16) Drainage, Irrigation& Flood Mitigation – 3 model, (17) Railways – 2 model, (18) Reclamation – 1 model.
Automation of Construction Cost Information (CCI) on the 60 Models
The automation process is 35% completed.
PRODUCTIVITY
KPI P5-079
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 35% | 2017 Weightage : 25% | 2018 Weightage : 15% | 2019 Weightage : 15% | 2020 Weightage : 10%
60 prototype models of construction project 50 % completed | 60 prototype models of construction project 100 % completed | 60 models of construction project & automation of construction cost information 50 % completed | 60 models of construction project & automation of construction cost information 100 % completed | Online Construction Cost Information Published
NO | Categorie | No. of Model(s)
1 | Office | 4
2 | Education | 3
3 | Health | 6
4 | Security | 4
5 | Mosque | 1
6 | Sports & Recreational Facilities | 3
7 | External Works | 2
8 | Residential | 9
9 | Hotel | 3
10 | Industrial | 4
NO | Categories | No. of Model(s)
11 | Commercial | 1
12 | Parking | 2
13 | Highway & Road | 7
14 | Bridge | 4
15 | Jetty | 1
16 | Drainage, Irrigation & Flood Mitigation | 3
17 | Railways | 2
18 | Reclamation | 1
Total |  | 60

## Slide 3
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION Public & Private Tender Price Indices published by Q3 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
Tender Price Index (TPI)
Tender Price Index (TPI) is to measure the movement of construction prices over time (in both private and public projects) by establishing a comparison between the level of pricing in a sample of project and a standard price base.
Methodology of TPI
CIDB will adopt the methodology of TPI from the Royal Institution of Chartered Surveyor (RICS) United Kingdom in developing the TPI for the local construction industry. The Malaysia methodology which requires the enhancement to the RICS TPI was successfully completed within 6 weeks on 14 October 2016.
Ready Reckoner (RR)
The Ready Reckoner is the standard price base that will be used to develop the TPI. Royal Institution of Surveyor Malaysia (RISM) was appointed on 12 Dec 2017 as the consultant to develop the RR and to prepare the TPI. The RR will be developed by taking into consideration the following factors :
Standard Method of Measurement 2 (SMM2)
The base year is 2016
The location base rate is in the Klang Valley area (KL and Selangor)
As of September 2018, the Ready Reckoner is 80% completed.
PRODUCTIVITY
KPI P5-080
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 25% | 2017 Weightage : 15% | 2018 Weightage : 15% | 2019 Weightage : 35% | 2020 Weightage : 10%
Methodology of Tender Price Index completed | Ready Reckoner (RR) 30% completed | Ready Reckoner (RR) 100% completed | Automation of Tender Price Index completed | Online Tender Price Index published

## Slide 4
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION Lifecycle Costing Information covering residential, commercials and highways published by Q3 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
Life Cycle Costing (LCC)
LCC is an economic assessment that covers the total cost of an asset which converts initial and future costs including maintenance, operation and disposal costs throughout its life span to the present year. The study focuses on the LCC at the project level for selected construction projects, namely highway, social housing and office building.
Study on Proposal on Management of LCC Data
MCM Value was appointed to conduct the Life Cycle Costing Study and the study was completed on 15 Sep 2017. The LCC study was presented and endorsed at the IWG-12 meeting on 29 Dec 2017. The recommendations of the study are as follows :
Greater awareness and commitment from authorities for LCC data collection
CIDB will champion the preparation of National LCC Guide
More advanced study at elemental and component level to be pursued by CIDB
CIDB to regulate the LCC requirements to be submitted by facility management and maintenance contractors as part of their license renewal
CIDB to spearhead the possibility of enacting an Act of Parliament that requires the assets of certain value to have LCC database
Automation of LCC
The LCC automation process is 35% completed.
PRODUCTIVITY
KPI P5-081
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 30% | 2019 Weightage : 20% | 2020 Weightage : 10%
Study on the Proposal for Management of Data Life Cycle Costing (LCC) for Construction Projects in Malaysia15% completed | Study on the Proposal for Management of Data Life Cycle Costing (LCC) for Construction Projects in Malaysia 100% completed | Automation of LCC 50% completed | Automation of LCC 100% completed | Online LCC published

## Slide 5
SPONSOR Sr Sariah Abdul Karib
OWNER Sr Mohd Zaid Zakaria
OIC Sr Nazir Muhamad Nor
KPI LEADER CIDB
KPI DESCRIPTION Labour and Plant Constant covering 4 major trade and type of plants published by Q3 2020
INITIATIVE P5 - Enhance availability of strategic information via NCIIC
SUB-INITIATIVE P5a - Enhance price and cost information on industry resources
This KPI is under the purview of IWG12.
Labour & Plant Constant (LPC)
LPC provides basic information for manpower and will be used as plant planning and a reference to gauge the efficiency of labour & plant constant in the building and civil works. It is aimed at achieving higher productivity as well as cost saving and maximizing margin. LPC facilitates the comparison and analyzing of project performance against the industry norms. At the same time, it also assists in rectifying or mitigating the problems as they exist.
Development of LPC
A technical committee has been established, chaired by JKR with members drawn from the industry, including MBAM, RISM, JUBM, UTM, UNITAR, UITM, UM and CIDB to steer the development of the LPC.
KH Alliance was appointed on the 6 Dec 2017 to develop the LPC for a period of 13 months to be completed by Jan 2019.
Until September 2018, the progress of the LPC development for:-
Methodology for Labour is 100% and Plant is 65%.
Labour Constant on Site Studies is approximately 40% and Plant Constant on site Studies is 50%.
In cooperation with JKR and public sector, about 10 sites had been identified which is in Putrajaya, Negeri Sembilan, Selangor Johor, Kuala Lumpur and Penang.
PRODUCTIVITY
KPI P5-082
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 50% | 2020 Weightage : 10%
 | Methodology for Labour & Plant Constant 30% completed | Methodology for Labour & Plant Constant 100% completed | Labour & Plant Constant on Site Studies 50% completed | Labour & Plant Constant on Site Studies 100% completed Labour & Plant Constant Published