## Slide 1
2016 Weightage : 80% | 2017 Weightage : 20% | 2018 | 2019 | 2020
Sustainability assessment on 2 pilot projects using CEEQUAL identified | Sustainability assessment on 2 pilot projects using CEEQUAL completed |  |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 2 Projects piloted for infrastructure sustainability rating using CEEQUAL by 2017
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
ENVIRONMENTAL SUSTAINABILITY
KPI E1-030
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
This KPI is under the purview of IWG6.
CEEQUAL (Civil Engineering Environmental Quality Assessment & Award Scheme), ENVISION and other infrastructure sustainability rating tools were benchmarked by USM from Feb – May 2016 to analyse the benefits, cost comparison and suitability of the tools to be used in the Malaysian construction industry. The objective of this study are:
Benchmark available sustainable infrastructure rating tools worldwide.
Benchmark and compare selected available sustainable infrastructure rating tools worldwide.
Categorise strengths and weaknesses of sustainable infrastructure rating tools assessed.
After conducting the study, CEEQUAL was chosen as fundamental towards the development of Malaysia Infrastructure Sustainable Rating Tool based on its broad applicability and adoptability in the global perspective.
These two (2) pilot infrastructure sustainability assessments were performed to test the suitability of CEEQUAL in Malaysia :
West Coast Expressway (WCE) Section 4 by IJM Construction
DUKE Phase 3 by Ekovest
IWG6 Meeting No.3 on 26 May 2017 approved the assessment report that concluded CEEQUAL is suitable for the development of the Malaysia sustainable infrastructure rating tool.
The infrastructure sustainability assessments using CEEQUAL for the 2 pilot projects were completed in June 2017.
This KPI is 100% achieved.

## Slide 2
2016 | 2017 Weightage : 100% | 2018 | 2019 | 2020
 | 16 CEEQUAL assessors trained and accredited |  |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 16 assessors being trained in CEEQUAL by Q2 2017
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
This KPI is under the purview of IWG6.
In order to test CEEQUAL for use in Malaysia, it is critical to have qualified assessors to test the tool. The criteria for the selection of assessors are background in build environment, construction and engineering. 16 assessors were trained by CEEQUAL for 3 days in March 2017. Below are the list of CEEQUAL assessors trained :
Ir. Chua Soo Kok (DUKE)
Ir. Mohd Zaini Abu Hassan (Green Tech Malaysia)
Ir. Md Zarulazam Md Eusofe - Konsortium Lebuhraya Utara- Timur (KL) SdnBhd
Khoo Sik Khui (IJM Corporation)
S. Ramesh A/L V. Subramaniam (IJM Corporation)
Timothy Pang - Konsortium Lebuhraya Utara- Timur (KL) SdnBhd
Yuvabalan A/L Govindasamy (CAST JKR)
Ab Halim Hussein (IJM Corporation)
Dr. Farid Ezanee Mohamed Ghazali (USM)
Dr. Mohd Rosli (USM)
Dr. Rozana Zakaria (UTM)
Zuraihi Abd Ghani (CIDB)
Emasria Ismail (CIDB- MAMPAN)
Noor FazierahYaakub (CIDB)
Fuhairah Ahmad Fuad (CIDB)
Norzaidi Nordin (CIDB-MAMPAN)
All the trained 16 CEEQUAL Assessors were appointed as Technical Committee members for the development of Malaysia Sustainable Infrastructure Rating Tool. The appointment starts from January 2018 until the completion of the Rating Tool.
This KPI is 100% achieved.
ENVIRONMENTAL SUSTAINABILITY
KPI E1-031
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 3
2016 Weightage : 30% | 2017 Weightage : 10% | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020
1st batch of 3 qualifying research partnerships approved 1st batch of 3 research MOU signed | 4 R&D topics identified 100% R&D commenced Board of Advisory under CREAM established | Hazard map, risk map & risk assessment on flood for critical infrastructure established Hazard map, risk map & risk assessment on land slide for critical infrastructure established Guidelines for construction on peat & organic soil in Malaysia improved Roadmap on Peat and Organic Soils in Malaysian Construction Industry established | Guidelines for flood assessment of Critical Infrastructure in specified areas established Guidelines for land slide assessment of Critical Infrastructure in specified areas established | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION At least 3 sustainable R&D by MAMPAN completed by Q4 2019
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
This KPI is under the purview of IWG6.
Four (4) qualifying research partnerships with Universiti Malaya (UM), Universiti Sains Malaysia (USM), Universiti Teknologi Malaysia (UTM) and Universiti Kebangsaan Malaysia (UKM) were approved and MoU signed.
Sustainable Excellence Centre (MAMPAN) launched on 1 Dec 2016 is a unit under Construction Research Institute of Malaysia (CREAM) as a reference center for sustainable construction and development. Later on 20 Feb 2017, the Research Advisory Council (RAC) also under CREAM was established to advise on the research areas. From the Five (5) topics identified by RAC, 4 topics were enhanced & endorsed by the Board of Trustee (BOT) of CREAM. The 4 topics that are managed by MAMPAN are as follows :
ENVIRONMENTAL SUSTAINABILITY
KPI E1-032
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
R&D Title | Start | End | Output | Progress
Development of Flood Risk Assessment (FRA) and Flood Vulnerability Index (FVI) for Critical Infrastructure (CI) in Malaysia | Dec 2017 | Dec 2019 | Flood risk map, FVI for CI, Flood & development zoning and guidelines of FVI for critical infrastructure (CI) | Content manual guidelines was revised according to the latest template from PLANMalaysia. GIS process of FVI and flood hydrodynamic model of the study area in Kelantan and Penang being develop. The flood data (DTM, flood model, and flood hazard map) obtained from JPS Malaysia. Technical Working Group held 3 meetings to monitor and comment on the development of R&D. 40% progress on track
Guidelines for Landslides Vulnerability Assessment for Critical Infrastructure (CI) in Malaysia (Parameters, Vulnerability Index, Risk Index, Vulnerability Assessment) | Dec 2017 | Dec 2019 | Parameters for landslides vulnerability assessment and risk index for CI, landslides vulnerability assessment, risk index for CI, guidelines for landslides vulnerability assessment and risk index for CI | Content manual guidelines was revised according to the latest template from PLANMalaysia. Characterization of critical element-at-risk mapped. The vulnerability determination for identified CI has been addressed. Technical Working Group held 3 meetings to monitor and comment on the development of R&D. 45% progress on track.
Review on Adequacy of Guidelines for Construction on Peat & Organic Soils in Malaysia | Dec 2017 | June 2018 | Reviewed Guidelines on Peat Soils | Guidelines for construction on Peat soils was completed on 30 June 2018. 100% completed.
Geotechnical Engineering on Peat & Organic Soils in Malaysian Construction Industry Roadmap | Dec 2017 | Dec 2018 | Implementation strategy for the Roadmap | Technical Working Group committee has been identified. Workshop on identification of research themes and titles was held on 22 Feb 2018. Term & Condition for the appointment of consultant has been finalized and RFP was called in May 2018. The appointment of the consultant is expected to be finalized by Aug 2018. 45% progress on track.
2 years period
2 years period
7 mths period
12 mths period

## Slide 4
2016 | 2017 Weightage : 20% | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020 Weightage : 20%
 | 1st Draft of Malaysia sustainability infrastructure rating tool completed by Q4 2017 4 pilot infrastructure projects identified for sustainability rating | 4 infrastructure projects piloted using Malaysia sustainability infrastructure rating tool Stakeholder engagement to refine sustainability infrastructure rating tool conducted Malaysia sustainability infrastructure rating tool finalised by Q4 2018 | Malaysia sustainability infrastructure rating tool adopted for government projects Report on adoption of Malaysia sustainability infrastructure rating tool produced | Cabinet paper/ Circular on adoption Malaysia sustainability infrastructure rating tool for public projects submitted
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION Malaysia environmental sustainability rating tool for infrastructure projects established by 2018
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG6.
First Draft of Malaysia Sustainability Infrastructure Rating Tool
The draft of Malaysia Sustainability Infrastructure Rating Tool was developed and finalised by USM in Dec 2017 and ready to be tested for viability in 2018.
Sustainable Infrastructure Rating Tool Task Force Committee chaired by CIDB agreed on four (4) types of infrastructure projects to be piloted for Malaysia Sustainability Infrastructure Rating Tool. They are :
Highway Project
Jetty / Port Project
Dam Project
Utility Services Project
Infrastructure Projects Piloted Using Malaysia Sustainability Infrastructure Rating Tool
The four (4) infrastructure projects piloted for Malaysia Sustainability Infrastructure Rating Tool and its assessment results are as follows :
ENVIRONMENTAL SUSTAINABILITY
KPI E1-118
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
TYPE OF INFRASTRUCTURE | PROJECTS | DESIGN SCORE (%) | CONS. SCORE (%)
Highway | Projek Setia Pantai – Express way (DUKE 3) |  | NA
Sewerage Treatment Plant | Loji Rawatan Kumbahan Serantau & Rangkaian Paip Pembentungan, Bandar Indera Mahkota, Kuantan Pahang | 54.99 | NA
Dam | Pembinaan Empangan Kahang, Kluang | 33.81 | 2.5
Utility Services | Projek Penghantaran 132:33kV (PMU) Bukit Nanas, Sandakan Sabah | 43.62 | NA
Stakeholder engagement to refine sustainability infrastructure rating tool :
From the result of the pilot projects, industry engagement was held on 8 June 2018 involving 30 experts and industry players from various background including SME’s to review and comment the draft on sustainable infrastructure rating tool. Some minor refinement were made to the document.
Malaysia sustainability infrastructure rating tool finalized :
The Malaysia sustainability infrastructure rating tool is 80% completed and expected to be finalized by Q4 2018.

## Slide 5
2016 | 2017 | 2018 | 2019 Weightage : 60% | 2020 Weightage : 40%
 |  |  | Malaysia sustainability infrastructure rating tool training modules developed | 25 trainers on Malaysia sustainable infrastructure rating tool trained and certified
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 25 trainers certified in Malaysia environmental sustainability rating tool by Q4 2019
INITIATIVE E1- Drive innovation in sustainable construction
SUB-INITIATIVE -
This KPI is under the purview of IWG6 and was initially targeted to commence in 2018. However due to delay in the completion of Malaysia Sustainability Infrastructure Rating Tool, the target is now rescheduled to commence in 2019.
Development of training modules will commence after the completion of Malaysia Sustainability Infrastructure Rating Tool under KPI E1-118.
ENVIRONMENTAL SUSTAINABILITY
KPI E1-119
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 6
2016 Weightage : 40% | 2017 Weightage : 20% | 2018 Weightage : 40% | 2019 Weightage : 0% | 2020 Weightage : 0%
70% Study on building rating tools in Malaysia completed by Q4 2016 | 100% Study on building rating tools in Malaysia completed by Q4 2017 | Study on building rating tools in Malaysia published by Q1 2018 |  | 
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION Building rating tools available in Malaysia analysed and indexed for industry reference and utilization by Q4 2018
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This KPI is under the purview of IWG6.
Study on Analysing and Indexing Building Rating Tools in Malaysia was completed by CREAM in March 2017.
The aim of the study is to ease the industry in selecting the best sustainability rating tool to be implemented in building projects by providing analysis on all sustainability building rating tools in Malaysia.
The study analysed 6 currently available sustainability building rating tools in Malaysia as follows:
MyCREST (CIDB)
Green PASS (CIDB)
Penarafan Hijau (PH-JKR)
Green Building Index (GBI)
GreenRE (REHDA)
IRDA-CASBEE (IRDA)
The outcome of the study was presented to IWG6 in August 2017 and endorsed by TWG2 on 30 Jan 2018. It was published on 30 March 2018.
This KPI is 100% achieved.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-037
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 7
2016 Weightage : 0% | 2017 Weightage : 0% | 2018 Weightage : 30% | 2019 Weightage : 35% | 2020 Weightage : 35%
 |  | Guideline for the implementation of MS 1525 established Engagement session to all states on adoption of MS 1525 conducted Training Module on MS 1525 developed | Training on MS 1525 to 6 states conducted 3 Training on MS 1525 to stakeholders conducted Report on adoption of MS 1525 by all states Requirements of MS 1525 as a condition for building plan approval implemented by 10 local authorities | Training on MS 1525 to 6 states conducted 3 Training on MS 1525 to stakeholders conducted Report on adoption of MS 1525 by all states Requirements of MS 1525 as a condition for building plan approval implemented by 10 local authorities
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER JKT
KPI DESCRIPTION By Law No. 38A on Energy Efficiency Implemented by 20 Local Authorities by Q4 2020
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This KPI is under the purview of IWG6.
The original KPI was ‘UBBL No.38A on Energy Efficiency gazetted for all states by Q4 2020’. Since its endorsement by MNKT in 2012, only 3 states (Penang, Selangor & Terengganu) had gazetted it. Due to the slow uptake by other states in gazetting UBBL No.38A, TWG2 had endorsed the amendment to the KPI on 30 Jan 2018. The revised KPI is 'By Law No 38A on Energy Efficiency Implemented by 20 Local Authorities by Q4 2020'.
Guideline on Implementation of MS 1525
JKT is in the process of preparing the guideline for MS 1525. CIDB provided guideline samples to JKT which were jointly developed by the industry players to be used by JKT as reference document in their development process of the above guideline. The planning for the implementation of MS 1525 on targeted Local Authorities was developed.
Engagement Session on Adoption of MS 1525
The engagement sessions with all states will be initiated by JKT after the completion of the guideline. The first engagement session is scheduled to be held on 9 July 2018.
Training Module on UBBL No 38A
The module will be developed in parallel with the above guideline.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-039
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 8
2016 | 2017 | 2018 Weightage : 30% | 2019 Weightage : 35% | 2020 Weightage : 35%
 |  | 2 awareness programs on ISO14001 to 4 and 5 Star (Rated under SCORE) Contractors 30% of 4 and 5 Star (Rated under SCORE) Non-Certified ISO 14001:2015 Contractors being certified with ISO 14001:2015 | 2 awareness programs on ISO14001 to 4 and 5 Star (Rated under SCORE) Contractors 70% of 4 and 5 Star (Rated under SCORE) Non-Certified ISO 14001:2015 Contractors being certified with ISO 14001:2015 | 2 awareness programs on ISO14001 to 4 and 5 Star (Rated under SCORE) Contractors 100% of 4 and 5 Star (Rated under SCORE) Non-Certified ISO 14001:2015 Contractors being certified with ISO 14001:2015
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 70% of 4 and 5 Star (Rated under SCORE) Non-Certified ISO 14001:2015 Contractors being certified with ISO 14001:2015 by 2020
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This is a new KPI under the purview of IWG6 commencing in 2018.
Awareness Program
One workshop was conducted on 14 May 2018 to raise awareness on ISO 14001:2015 EMS to 8 contractors. Another awareness workshop is scheduled to be conducted on 25 July 2018 which will be participated by at least 18 contractors.
4 and 5 Star SCORE Rated Contractors Certified With ISO 14001:2015
By Q2 2018, the statistics of 4 and 5 star SCORE rated contractors certified with ISO 14001:2015 are as follows :
Contractors are expected to attend the DIY ISO14001:2015 certification program after attending the awareness course.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-135
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
SCORE | No. of Contractors | Certified With ISO 14001:2015 | Non-Certified With ISO 14001:2015 | 2018 Target (30%) | Q2 2018 Achievement
4 Star | 52 | 31 | 21 | 6 | 0
5 Star | 7 | 7 | 0 | - | -

## Slide 9
2016 | 2017 Weightage : 25% | 2018 Weightage : 25% | 2019 Weightage : 25% | 2020 Weightage : 25%
 | 50 MyCREST Qualified Professionals accredited | 100 MyCREST Qualified Professionals accredited | 100 MyCREST Qualified Professionals accredited | 100 MyCREST Qualified Professionals accredited
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 350 MyCREST qualified professionals accredited by Q4 2020
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG6.
MyCREST stands for Malaysia Carbon Reduction and Environmental Sustainability Rating Tool. MyCREST Qualified Professionals are the personnel accredited by CIDB whose role is to facilitate the industry in adopting MyCREST in building construction projects.
MyCREST Qualified Professionals Accredited :
The statistics of MyCREST Qualified Professionals Accredited are as follows :
As of 2017, there were 164 accredited MyCREST Qualified Professionals of which 133 are representative from government agencies and 31 are representative from private sectors, academicians and associations.
As of Q2 2018, 3 training courses were conducted as follows :
Out of 101 participants who attended the above courses, 91 passed the MyCREST QP Exam. The accreditation for qualified candidates are expected to be completed in Q4 2018.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-120
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
DATE | COLLABORATION | NO. OF PARTICIPANTS
13-15 Mar 2018 | JKR Putrajaya | 35
10-12 April 2018 | JKR Putrajaya | 34
17-19 April 2018 | Open to public | 32
Total |  | 101
 | Prior 2016 | 2017 | 2018 | 2019 | 2020
Target | - | 50 | 100 | 100 | 100
Achievement | 55 | 109 | 91 (Q2 2018) | - | 
Achievement % | - | 218% | 91% | - | 

## Slide 10
2016 | 2017 Weightage : 20% | 2018 Weightage : 40% | 2019 Weightage : 20% | 2020 Weightage : 20%
 | 25 Assessors Accredited | 25 Assessors Accredited MyCREST enhanced | 25 Assessors Accredited | 25 Assessors Accredited
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 100 MyCREST assessors (MA) accredited by Q4 2020
INITIATIVE E2-Drive compliance to environmental sustainability ratings and requirements
SUB-INITIATIVE -
This is a new KPI introduced in 2017 under the purview of IWG6.
Malaysia Carbon Reduction and Environmental Sustainablity Rating Tool (MyCREST) Assessors are personnel accredited by CIDB whose role is to assess building construction projects using MyCREST. Only MyCREST Qualified Professionals are eligible to become MyCREST Assessors (MA).
Assessors Accredited
The statistics of MA accredited are as follows :
As of 2017, there were 59 MA accredited of which 51 are representative from government agencies and 8 are representative from private sectors, academicians and associations.
For 2018, the arrangement to accredit all 25 Assessors is expected to be held on 15 – 16 August 2018.
MyCREST Enhanced
The consultant to enhance MyCREST was appointed in May 2018. A workshop with projects that adopted MyCREST was conducted on 5 June 2018 to gain feedback for Design and Construction Stage. The same session was conducted on 11 June 2018 for Operation and Maintenance Stage. The Calculator review workshop was conducted on 21 June 2018. The output of all sessions were presented to CIDB on 29 June 2018.
ENVIRONMENTAL SUSTAINABILITY
KPI E2-121
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
 | Prior 2016 | 2017 | 2018 | 2019 | 2020
Target | - | 25 | 25 | 25 | 25
Achievement | 30 | 29 | 0 (Q2 2018) | - | 
Achievement % | - | 116% | - | - | 

## Slide 11
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
Sustainable specification completed by JKR 3 pilot projects for the implementation of sustainable specification identified by JKR | Sustainable specification in pilot projects implemented Status on the implementation of sustainable specification in procurement for public building and infrastructure reported | Report on sustainable specification (GPSS Design Score) in procurement for public building and infrastructure issued | Report on sustainable specification (GPSS Construction Score) in procurement for public building and infrastructure issued | Final report on sustainable specification in procurement for public building and infrastructure issued Circular on implementation of sustainable specification in procurement for public building and infrastructure issued by MOF
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER MOF
KPI DESCRIPTION Sustainable specification mandated in procurement for public buildings/ infrastructure by Q4 2020
INITIATIVE E3-Focus on public projects to lead the charge on sustainable practices
SUB-INITIATIVE -
This KPI is under the purview of IWG7.
Report On Sustainable Specification In Procurement For Public Building
Sustainable specification was included in the contract document for the three (3) pilot projects under JKR in 2016. The Green Product Scoring System (GPSS) was used to measure the percentage of green products used in these projects and the respective cost in monetary value.
Status report on the projects are as follows :
1) Pusat pengajian pengurusan pelancongan Hospitaliti dan Alam Sekitar UUM Colgis
GPSS Score : 1 Star
GPSS design score is 45.78% (1 Star). The Report on GPSS Design Score was submitted to CIDB on 25 April 2018.
2) Fakulti pendidikan teknikal dan vokasional di kampus UPSI Teluk Intan Fasa 2- Bangunan
GPSS Score : Assessment is on-going
MyCREST and GPSS workshop on the design score is scheduled on 4 July 2018 by Head of Project Team, HOPT Cawangan Kerja Pendidikan.
3) Pusat Latihan Keselamatan Perlindungan Malaysia (PLKPM) Bandar Baru Enstek, N.Sembilan
GPSS Score : Assessment is on-going
GPSS workshop for the project has been highlighted in the GGP Committee Meeting on 26 Jun 2018.
In addition, these pilot projects will be used as a reference to develop the Guideline on Government Green Procurement (GGP) for Works. The GGP Guideline for works will be issued by MoF to mandate sustainable specification for public projects as the final outcome by 2020.
ENVIRONMENTAL SUSTAINABILITY
KPI E3-041
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 12
2016 | 2017 | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020 Weightage : 40%
 |  | Status report on 2017 CO2 reduction in new public buildings published | Status report on 2018 CO2 reduction in new public buildings published | Status report on 2019 CO2 reduction in new public buildings published Study on achievement of carbon reduction published
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER CIDB
KPI DESCRIPTION 6% CO2 emission reduction in new public buildings exceeding RM50Mn by 2020
INITIATIVE E3-Focus on public projects to lead the charge on sustainable practices
SUB-INITIATIVE -
This is a new KPI under the purview of IWG7 commencing in 2018.
Status report on 2017 CO2 reduction in new public buildings :
CO2 emission reduction in new public buildings exceeding RM50Mn by 2020 will be calculated using MyCREST assessment. The assessment was conducted in 2017 and its report published in 2018. Only 1 public project that is Menara KKR2 was assessed in 2017. Menara KKR2 was designed to emit 6302.22 ktCO2e/year and it achieved 64% CO2 emission reduction from its conventional design.
The report is expected to be published by Q4 2018.
2018 CO2 reduction in new public buildings Status Report :
MyCREST assessment on public buildings for 2018 is on going.
ENVIRONMENTAL SUSTAINABILITY
KPI E3-136
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 13
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 10% | 2019 Weightage : 30% | 2020 Weightage : 20%
Green technology tax incentives GITA and GITE mechanism established | Study on the potential of green incentives completed 2 companies benefitted from green incentive 5 promotional activities/programs on green incentives | Stakeholder engagements on the outcome of the study conducted 5 companies benefitted from green incentives 5 promotional activities/programs on green incentives conducted | Recommendations to the Government on the new green incentives 7 companies benefitted from green incentives 5 promotional activities/programs on green incentives conducted | New/ improved green incentives mechanism introduced 10 companies benefitted from green incentives 5 promotional activities/programs on green incentives conducted
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER KeTTHA
KPI DESCRIPTION At least 10 companies benefitted from green incentive for sustainable buildings by Q4 2020
INITIATIVE E4-Facilitate industry adoption of sustainable practices
SUB-INITIATIVE -
This KPI is under the purview of IWG7.
Study on the potential of green incentives
IIUM had completed the study on the potential green incentives in Aug 2017 and the report was submitted to KeTTHA for evaluation on Nov 2017. The study concluded these 10 potential green incentives are suitable to be applied in Malaysia for all stakeholders :
Investment Tax Incentive
Production Tax Incentive
Property Tax Incentive
Value Added Tax (VAT) Reduction
Excise Tax Reduction
Import Duty Reduction
Accelerated Depreciation
R&D Tax Incentive
Tax Holiday
Tax on Conventional Fuels
Guideline for Green Technology Tax Incentive was published by MGTC. 3 types of available tax incentive offered specially to the construction industry are :
1. Green Investment Tax Allowance for Projects (GITA-Project & Assets)
2. Green Income Tax Exemption (GITE) for green technology services
3. MyCREST
ENVIRONMENTAL SUSTAINABILITY
KPI E4-045
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET
Stakeholder engagements on the outcome of the study :
Engagement with Stakeholder to discuss on the outcome of the study is expected to be held in Q3 2018.
Companies Benefitted From Green Incentives
These six (6) companies have benefitted from Green Income Tax Exemption (GITE) Green Building :
1) DME Solutions Sdn Bhd
2) Exergy CX Sdn Bhd
3) Fenestra Green Sdn Bhd
4) Love Way Avenue Sdn Bhd
5) Green Urban Matters Solution Sdn Bhd
6) Light and Energy Sdn Bhd
Promotional Activities
As of 2017, 12 Nos of promotional activities/programs on green incentives was conducted and participated by 245 companies.
KeTTHA is expected to organise more promotional activities in Q3 and Q4 2018.

## Slide 14
2016 | 2017 | 2018 Weightage : 35% | 2019 Weightage : 35% | 2020 Weightage : 30%
 |  | The regulation gazetted Implementation framework established Stakeholders engagement with 20 Local authorities conducted At least 1 promotional activities / program on the regulation conducted | Regulation incorporated in the construction contract Stakeholders engagement with 13 Local authorities conducted At least 1 promotional activities / program on the regulation conducted | At least 7 states enforce the regulation
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER JPSPN / SW CORP
KPI DESCRIPTION 7 states establish Peraturan-Peraturan Pengurusan Sisa Pepejal dan Pembersihan Awam (Skim bagi Sisa Pepejal Pembinaan) 2018 dan Peraturan-Peraturan Pengurusan Sisa Pepejal dan Pembersihan Awam (Lesen bagi Sisa Pepejal Pembinaan ) 2018
INITIATIVE E5-Reduce irresponsible waste during construction
SUB-INITIATIVE -
This is a new KPI under the purview of IWG7 commencing 2018
Peraturan-Peraturan Pengurusan Sisa Pepejal dan Pembersihan Awam
Draft regulation was submitted and commented by Attorney General. Amendments had been finalized and expected to be approved by the Minister in Q3 2018.
Implementation Framework
Implementation framework will be prepared upon the above regulation is being gazetted.
Promotional Activities
Promotional activities will commence once the implementation framework is ready.
ENVIRONMENTAL SUSTAINABILITY
KPI E5-137
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET

## Slide 15
2016 | 2017 | 2018 Weightage : 40% | 2019 Weightage : 30% | 2020 Weightage : 30%
 |  | Final report on baseline study published Construction & demolition online system completed by Q1 2018 At least 1 awareness seminar on construction waste conducted Status report on the construction and demolition waste recycled published | At least 1 awareness seminar on construction waste conducted Status report on the construction and demolition waste recycled published Collection of construction & demolition waste data through online system gazetted | At least 1 awareness seminar on construction waste conducted Status report on the construction and demolition waste recycled published Study on achievement of construction and demolition waste recycled published
SPONSOR Datuk Ir. Elias Ismail
OWNER Ir. M. Ramuseren Muthu
OIC Zuraihi Abdul Ghani
KPI LEADER JPSPN / SW CORP
KPI DESCRIPTION 20% annual increment in construction and demolition waste (tonnage) recycled
INITIATIVE E5-Reduce irresponsible waste during construction
SUB-INITIATIVE -
This is a new KPI under the purview of IWG7 commencing 2018
Baseline Study
Baseline for the waste recycling rate was established based on data collected from February 2017 till January 2018. The rate of C&D waste that was recycled in 2017 was 13.7%.
C&D Waste Management Online System
The online C&D waste management system was completed in Jan 2018. The system will provide a platform for both waste collectors and waste producers to key-in data on C&D waste generated to assist the relevant authorities in implementing waste management programmes towards sustainability of the environment.
Awareness Seminar
Awareness seminar on construction waste management is scheduled to be held in Sept 2018.
Report on C&D Waste Recycled
Data collection on C&D waste for 2018 is on-going. The report will be prepared when sufficient data is ready.
ENVIRONMENTAL SUSTAINABILITY
KPI E5-138
PROGRESS REPORT UNTIL Q2 2018
ANNUAL TARGET