## Slide 1
2016 Weightage : 30% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 15% | 2020 Weightage : 15%
2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action on non-compliance AG agreement to audit on IBS non-compliance secured | 2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action non- compliance. Audit Report on IBS non compliance published by AG | 2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action non- compliance JKR corrective action on AG report on IBS | 2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action non-compliance | 2 Report on status of IBS adoption submitted by ICU JPM to MOF & AG for action non-compliance
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER ICU / CIDB
KPI DESCRIPTION 2 reports annually on status of IBS adoption, submitted by Implementation Coordination Unit (ICU-JPM) to Ministry of Finance (MOF) and Auditor General (AG) for action on non-compliance beginning 2016
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
PRODUCTIVITY
KPI P3-060
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
This KPI is under the purview of IWG10.
Report on Status of IBS Adoption
ICU JPM produced 1 report on the status of IBS adoption in government projects and submitted to MOF and AG in June 2016. It was reported that 69.4% (465 out of 670 project) of public projects adopted IBS and achieved 70 IBS score. ICU JPM confirmed that the 2nd report for year 2016 will not be issued as the level of IBS adoption is status quo.
For 2017, ICU JPM produced 1 report on the status of IBS adoption in government projects and submitted to MOF and AG on 31 July 2017 . The title of the report is “Laporan Pematuhan Pelaksanaan Untuk Projek-Projek Kerajaan RMKe-11 Bil.1/2017 (Januari-Jun 2017)”. It was reported that 77.8% (1113 out of 1431 projects) of public projects adopted IBS and achieved 70 IBS score. The 2nd report for year 2017 will not be issued .
ICU JPM informed that the next report will be submitted by June 2018.
Audit Report on IBS Non-compliance
ICU JPM have submitted the report on the status of IBS adoption to AG for AG to audit on IBS non-compliance. No audit report has been received from AG.
Q2 2018
ICU JPM has submitted the 1st report for year 2018 (Jan-Apr) on 25 May 2018 and the level of adoption was 64%.
Q3 2018
ICU JPM has submitted the 2nd report for year 2018 (Jan-July) on 10 August 2018 and the level of adoption was 80.8%

## Slide 2
2016 Weightage : 40% | 2017 Weightage : 40% | 2018 | 2019 | 2020
 |  | Weightage : 20% |  | 
50% of JKR Pre Approved Plan (PAP) comply to IBS and MC. JKR IBS-PAP drawings documented. | 100% of JKR Pre Approved Plan (PAP) comply to IBS and MC. JKR IBS-PAP drawings documented. |  |  | 
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER JKR/ CIDB
KPI DESCRIPTION All JKR Pre-Approved Plans (PAPs) comply to IBS and Modular Coordination by 2017
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
This KPI is under the purview of IWG10.
JKR Pre-Approved Plan in Compliance to IBS and MC (PAP2.0)
PAP means “reka bentuk bangunan yang tersedia dan lengkap dengan input seni bina, struktur, mekanikal, elektrikal dan ukur bahan yang menepati keperluan teknikal dan perundangan kerajaan iaitu Akta Jalan, Parit dan Bangunan 1974 (Akta 133)”.
The objectives of PAP are to reduce the time for planning and design processes, and to give option and alternative to existing building designs. PAP2.0 refers to Pre-Approved Plan in compliance to IBS and MC.
JKP PAP2.0 included drawings for various types of buildings namely school, quarters, klinik kesihatan, dewan, surau and masjid, taska , office etc.
In 2016, 78 out of 120 JKR PAP2.0 were completed by JKR.
In 2017, all 130 JKR PAP2.0 were completed by JKR.
Q2 2018
Until Jun 2018, 15/30 PAPs have been completed by JKR that incorporate IBS and Modular Coordination.
Q3 2018
Until Sept 2018, 23/30 PAPs have been completed by JKR that incorporate IBS and Modular Coordination.
PRODUCTIVITY
KPI P3-061
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
Note: 2018-2020
All new JKR PAP comply to IBS and MC
(Annual target to be determined later)

## Slide 3
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER JKR/ CIDB
KPI DESCRIPTION All JKR and CIDB’s IBS components catalogue harmonised and issued by 2017
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
PRODUCTIVITY
KPI P3-062
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 70% | 2017 Weightage : 30% | 2018 | 2019 | 2020
Harmonization of JKR and CIDB IBS component catalogue completed | Harmonized IBS component catalogue for Industry reference published |  |  | 
This KPI is under the purview of IWG10.
The JKR and CIDB IBS component catalogue on precast concrete components was harmonised and completed in 2016.
This catalogue was later published as “IBS Component Catalogue For Precast Concrete Building System (Revision 2017)” on 27 September 2017.
The catalogue produced by CIDB will be the basic reference for the design, detailing and manufacturing of IBS components. It aims to provide designers i.e Architects & Engineers and Quantity Surveyors (QS) key information and references, including the description, sizing and detailing of pre-cast concrete components.
The objectives of producing the catalogue are outlined as follows:
To assist the Architects as guide in the preparation of architectural drawings
To assist the Engineers in producing the tender drawings during the designing process
To assist the QS in providing the tender documents during the procurement process
To assist the manufacturers/suppliers in producing shop drawings
The pre-cast concrete components in the catalogue consist of these elements:
Structural elements covering the precast concrete beam, column, load-bearing wall panel and floor slab.
Non-structural elements covering the precast concrete non load-bearing wall and staircase
Connection details covering connections of column to base; pocket foundation; steel base plate; column to column; beam to column; beam to beam; slab to beam; slab to slab; slab to wall and wall to wall.
Other design considerations covering structural stability & integrity; floor diaphragm; fire rating; mechanical & electrical services and site management.
The IBS Catalogue For Precast Concrete Building System Revision 2017 has been launched during the MIIE 2018 Official Opening on 28 March 2018.
This KPI is 100% completed.

## Slide 4
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER JKR/ CIDB
KPI DESCRIPTION 80% compliance to amended MOF Circular 1 PPK 1/2013 by 2018
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
This KPI is under the purview of IWG10.
In 2008, the Ministry of Finance (MOF) issued a circular Surat Pekeliling Perbendaharaan Bil. 7 2008 (SPP Bil. 7 2008) to inform all Government Agencies to implement IBS in all public building projects worth RM10Mn and above and to achieve 70 IBS score.
IBS adoption for projects RM5mn and above
In 2016, JKR agreed in principle to broaden IBS adoption for projects RM5Mn and above. However MOF was in the opinion that adoption of IBS for public projects between RM5Mn to RM10Mn is encouraged (not mandated).
Study on non-compliance of IBS adoption in public projects worth RM10 Mn and above
In IWG10 meeting dated 9 June 2017, the committee agreed to include the above study as the annual target for 2017. The study was conducted by USAINS Holding Sdn Bhd beginning July 2017 and was completed on 30 October 2017. The study utilised data from ICU covering projects executed in 2010-2013, 2015 and 2016. The objectives of this study are:
To identify compliance and non-compliance of IBS adoption in the procurement of public sector building projects
To determine the causing factor towards a non-compliance of IBS adoption in public projects worth RM10Mn and above
To recommend viable improvements that can be made to ensure a full compliance of IBS adoption in all projects worth RM10Mn and above
The study found that the factors causing non compliance are as follows:
The contractors of PDP/PFI procured projects make their own discretion to decide whether to use IBS in their projects
Cost overrun may trigger budget constraints
Achievement of mandatory IBS score in design stage may not be achievable during construction
Insufficient expertise in designing and constructing IBS
Conventional design developed by consultants do not comply with available IBS components
Projects were situated in remote areas where IBS components are not accessible for transportation
Insufficient financial capacity of contractors due to high deposits required
Annual targets for 2018 – 2020 need to be determined after MOF circular issued to achieve the over-arching initiative of P3 i.e. accelerate the adoption of IBS, mechanisation and modern practices across project life-cycle.
Q1 2018
Technical Committee has been formed and first meeting will be held on 20 April 2018 to discuss on the requirement to broaden IBS adoption for Government Projects.
Q2 2018
Technical Committee has been formed and first meeting was held on 20 April 2018 to discuss on the requirement to broaden IBS adoption for Government Projects. MoF has issued a letter to ICUJPM with the instruction not to review the value for IBS implementation in Government project from RM10 Million to RM5 Million.
CITP IWG10 Bil. 5 dated on 8 June 2018 agreed to drop this KPI.
PRODUCTIVITY
KPI P3-063
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
Note 2018-2020
Target to be determined after MOF Circular issued
2016 Weightage : 10% | 2017 Weightage : 40% | 2018 | 2019 | 2020
 |  | Weightage : 50% |  | 
JKR agreement to broaden IBS adoption for projects RM5mn and above secured. | Study on non-compliance of IBS adoption in public projects worth RM10 Mn and above |  |  | 

## Slide 5
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER JKR/ CIDB
KPI DESCRIPTION 80% compliance to amended MOF Circular 1 PPK 1/2013 by 2018
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3a - Drive scale of IBS adoption via public sector projects
This KPI is under the purview of IWG10.
Technical Committee has been formed and first meeting was held on 20 April 2018 to discuss on the requirement to broaden IBS adoption for Government Projects. MoF has issued a letter to ICUJPM with the instruction not to review the value for IBS implementation in Government project from RM10 Million to RM5 Million.
CITP IWG10 Bil. 5 dated on 8 June 2018 agreed to drop this KPI
PRODUCTIVITY
KPI P3-063
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
Note 2018-2020
Target to be determined after MOF Circular issued
2016 Weightage : 10% | 2017 Weightage : 40% | 2018 | 2019 | 2020
 |  | Weightage : 50% |  | 
JKR agreement to broaden IBS adoption for projects RM5mn and above secured. | Study on non-compliance of IBS adoption in public projects worth RM10 Mn and above |  |  | 

## Slide 6
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER KPKT/ CIDB
KPI DESCRIPTION 100% new Development Order in Greater Klang Valley for projects RM50 Mn and above achieved minimum 50 IBS Score by 2018
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3b - Drive scale of IBS adoption via private sector projects
PRODUCTIVITY
KPI P3-064
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 30% | 2017 Weightage : 30% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020
Criteria to mandate IBS in Private Sector established and approved by MNKT IBS criteria for new private sector projects announced by KPKT | PBTs in Greater Klang Valley agreement to adopt IBS criteria as a prerequisite for issuance of DO secured and implemented | KPKT Report on IBS adoption for private sector project published. Corrective action for non- compliance of IBS adoption proposed and implemented | KPKT Report on IBS adoption for private sector project published. Corrective action for non- compliance of IBS adoption proposed and implemented | 
This KPI is under the purview of IWG10.
Criteria to mandate IBS in Private Sector
A guideline to mandate IBS adoption in Private Sector for Projects worth RM50Mn and above to achieve a minimum 50 IBS Score was established and submitted to Ministry of Works in 2016. KPKT was to table the guideline to the MNKT for approval. MNKT Meeting held on 10 July 2017 approved the policy to mandate IBS adoption in Private Sector for Projects worth RM50Mn and above to achieve a minimum 50 IBS Score to be adopted via Development Order (DO) or Building Plan approval by PBTs. The policy was also agreed by the Mesyuarat Menteri-Menteri Besar & Ketua Menteri held on 10 October 2017.
In order for the policy to be implemented by the PBTs, it has to be passed in a state EXCO meeting chaired by the Menteri Besar. CIDB is currently putting up road shows to enlighten the PBTs on the implementation and execution of the above policy through engagements with the State Secretary. The road shows were executed to all states except Terengganu and Pulau Pinang only. KPKT will issue a circular to all PBTs to enforce the IBS policy approved by MNKT.
CIDB is currently in discussion with KPKT to prepare and review the IBS implementation mechanism as well as to draft the IBS state circular for PBT.
PBTs in Greater Klang Valley agreement to adopt IBS criteria as a prerequisite for issuance of DO
Pihak Berkuasa Tempatan (PBT) or Local Authorities in Greater Klang Valley are as follows:
Dewan Bandaraya Kuala Lumpur (DBKL) – 17/10/2017
Perbadanan Putrajaya (PJC) – 17/10/2017
Majlis Bandaraya Petaling Jaya (MBPJ) – 18/05/2017
Majlis Bandaraya Shah Alam (MBSA)
Majlis Perbandaran Subang Jaya (MPSJ)
Majlis Perbandaran Kajang (MPKJ)
Majlis Perbandaran Selayang (MPS) 19/01/2018
Majlis Perbandaran Klang (MPK)
Majlis Perbandaran Ampang Jaya (MPAJ)
Majlis Daerah Kuala Langat (MDKL)
IBS adoption had been agreed in principal by DBKL and MBPJ with further details to be refined at the implementation level.
CIDB have discussed with KPKT on reviewing the KPI for IBS implementation mechanism as well as to draft the IBS state circular for PBT on 20 April 2018. This revised KPI has been presented in IWG10 Meeting Bil. 5 dated 8 June 2018 and approved by the committee.
Q3 2018
The Circular from Secretary General of KPKT to mandate the use of IBS in private sector project has been issued on 10 January 2018.
CIDB have met with the followings to explain the policy to mandate IBS in private sector projects;
1. President of Majlis Perbandaran Subang Jaya (MPSJ) on 17 August 2018.
2. Executive Director (Planning) of Dewan Bandaraya Kuala Lumpur (DBKL) on 30 August 2018.
3. Mayor of Majlis Bandaraya Shah Alam (MBSA) on 7 Sept 2018.
DBKL have implemented the policy while the MBSA and MPSJ still under due consideration.

## Slide 7
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER KPKT/ CIDB
KPI DESCRIPTION 100% new Development Order by identified Local Authorities in three states (Selangor, Johor & Pulau Pinang) for projects RM50Mn and above achieved minimum 50 IBS Score by 2020
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3b - Drive scale of IBS adoption via private sector projects
PRODUCTIVITY
KPI P3-065
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
Weightage : 20%
2016 Weightage : 30% | 2017 Weightage : 30% | 2018 Weightage : 15% | 2019 Weightage : 15% | 2020 Weightage : 10%
Criteria to mandate IBS in Private Sector established and approved by MNKT IBS criteria for new private sector projects announced by KPKT | PBTs in three states agreement to adopt IBS criteria as a prerequisite for issuance of DO secured and implemented | KPKT Report on IBS adoption for private sector project in three states published. Corrective action for non- compliance of IBS adoption proposed and implemented | KPKT Report on IBS adoption for private sector project in three states published. Corrective action for non- compliance of IBS adoption proposed and implemented | KPKT Report on IBS adoption for private sector project in three states published. Corrective action for non- compliance of IBS adoption proposed and implemented
This KPI is under the purview of IWG10.
Criteria to mandate IBS in Private Sector
A guideline to mandate IBS adoption in Private Sector for Projects worth RM50Mn and above to achieve a minimum 50 IBS Score was established and submitted to Ministry of Work in 2016. KPKT was to table the guideline to the MNKT for approval. MNKT Meeting held on 10 July 2017 approved the policy to mandate IBS adoption in Private Sector for Projects worth RM50Mn and above to achieve a minimum 50 IBS Score to be adopted via Development Order (DO) or Building Plan approval by PBTs. The policy was also agreed by the Mesyuarat Menteri-Menteri Besar & Ketua Menteri held on 10 October 2017.
In order for the policy to be implemented by the PBTs, it has to be passed in a state EXCO meeting chaired by the Menteri Besar. CIDB is currently putting up road shows to enlighten the PBTs on the implementation and execution of the above policy through engagements with the State Secretary. The road shows were executed to all states except Terengganu and Pulau Pinang only. KPKT will issue a circular to all PBTs to enforce the IBS policy approved by MNKT.
CIDB is currently in discussion with KPKT to prepare and review the IBS implementation mechanism as well as to draft the IBS state circular for PBT.
PBTs in three states agreement to adopt IBS criteria as a prerequisite for issuance of DO
Pihak Berkuasa Tempatan (PBT) or Local Authorities in Selangor, Pulau Pinang and Johor are as follows:
Majlis Daerah Hulu Selangor (MDHS)
Majlis Daerah Kuala Selangor (MDKS)
Majlis Daerah Sabak Bernam (MDSB) Selangor -19/01/2018
Majlis Perbandaran Sepang (MPSepang)
The agreement from PBTs in Pulau Pinang and Johor Bahru have yet to be secured.
CIDB have discussed with KPKT on reviewing the KPI for IBS implementation mechanism as well as to draft the IBS state circular for PBT on 20 April 2018. This revised KPI has been presented in IWG10 Meeting Bil. 5 dated 8 June 2018 and approved by the committee.
Q3 2018
The Circular from Secretary General of KPKT to mandate the use of IBS in private sector project has been issued on 10 January 2018.
CIDB have met with Pengerusi Jawatankuasa Kerajaan Tempatan Sains dan Teknologi, Johor Y.B Tan Hong Ping to explain the policy to mandate IBS in private sector projects on 2 October 2018.
Y.B Tan Hong Ping has suggested that a dialouge session between CIDB, KPKT and all PBT in Johor to discuss on the implementation on this policy to be held on 30 October 2018.

## Slide 8
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER CIDB
KPI DESCRIPTION At least 100 more new IBS component manufacturing plants established at various strategic locations by 2020
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3c - Propel IBS supply chain via economic mechanisms
This KPI is under the purview of IWG10.
In 2015, there are already in existence 200 IBS component manufacturing plants producing various IBS components.
In 2016, 27 new IBS component manufacturing plants producing 4 main components (precast concrete system, metal framing, innovative product and blockwork system) were established and registered in 7 states (Johor, Selangor, Sarawak, Pahang, Melaka, Kedah & Kelantan).
In 2017, 37 new IBS component manufacturing plants producing 5 main components (precast concrete system, metal framing, innovative product, formwork system and blockwork system) were established and registered in 8 states - Selangor (20), Johor (3), Pulau Pinang (1), Perak (1), N. Sembilan (3), Sarawak (4), Kedah (2) & Sabah (3). A total of 64 out of 100 (as targeted until 2020) new IBS component manufacturers and suppliers have been registered.
In 2018, 26 new IBS component manufacturing plants producing 5 main components (precast concrete system, metal framing, innovative product, formwork system and blockwork system) were established and registered in 8 states - Selangor (9), Johor (6), Pahang (1), Perak (2), N. Sembilan (1), Sarawak (2), Kedah (1) & Sabah (4). A total of 90 out of 100 (as targeted until 2020) new IBS component manufacturers and suppliers have been registered.
To date, CIDB had registered a total of 290 IBS component manufacturing plants.
PRODUCTIVITY
KPI P3-066
PROGRESS REPORT UNTIL Q4 2017
ANNUAL TARGET
2016 Weightage : 20% | 2017 Weightage : 20% | 2018 Weightage : 20% | 2019 Weightage : 20% | 2020 Weightage : 20%
20 new IBS manufacturer registered | 20 new IBS manufacturer registered | 20 new IBS manufacturer registered | 20 new IBS manufacturer registered | 20 new IBS manufacturer registered
NO | IBS COMPONENTS | NEW IBS MANUFACTURINGPLANTS |  | 
 |  | 2016 | 2017 | 2018 (Q3)
1 | Precast Concrete System | 9 | 9 | 6
2 | Metal Framing | 9 | 11 | 6
3 | Innovative Product | 8 | 10 | 10
4 | Blockwork System | 1 | 3 | 0
5 | Formwork System | 0 | 4 | 4
SUB TOTAL: |  | 27 | 37 | 26
TOTAL |  | 90 |  | 

## Slide 9
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER CIDB
KPI DESCRIPTION At least 5,000 professionals (engineers, architects & quantity surveyors) trained to apply IBS and modular coordination from design phase by 2020
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3c - Propel IBS supply chain via economic mechanisms
This KPI is under the purview of IWG10.
Training in IBS takes 3 days covering 5 modules in these areas:
M01 – Pengenalan kepada IBS untuk bangunan
M02 – Sistem Koordinasi modular (MC)
M03 – Pengiraan skor IBS
M04 – Konsep rekabentuk sistem konkrit pra-tuang
M05 – Pengurusan projek IBS
Professionals trained in IBS and Modular Coordination (MC)
Cumulatively 3,898 professionals (633 Architects, 2484 Engineers & 781 QSs) out of 5,000 (as targeted until 2020) professionals were trained in IBS and Modular Coordination.
Directory of trained professionals published
The directory of certified IBS professionals as of September 2017 and 2018 were published in the Orange Book by CIDB. It also comprised directories for:
registered IBS suppliers/manufacturers, distributors and on site precast concrete casting
IBS consultants
Statistics of IBS contractors
Q3 2018
1,829 out of 1,500 (as targeted) professionals have been trained in IIBS and Modular until September 2018.
The cumulative total is 3,898 out of 5,000 (as targeted) professionals trained in IBS and Modular Coordination since January 2016.
PRODUCTIVITY
KPI P3-067
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 5% | 2017 Weightage : 30% | 2018 Weightage : 30% | 2019 Weightage : 30% | 2020 Weightage : 5%
250 professionals trained in IBS and MC Directory of trained professionals published | 1500 professionals trained in IBS and MC Directory of trained professionals published | 1500 professionals trained in IBS and MC Directory of trained professionals published | 1500 professionals trained in IBS and MC Directory of trained professionals published | 250 professionals trained in IBS and MC Directory of trained professionals published
NO | qq | 2016 | 2017 | 2018 (Q3)
1 | Architect | 46 | 264 | 323
2 | Engineer | 201 | 1128 | 1155
3 | Quantity Surveyor | 109 | 321 | 351
SUB TOTAL: |  | 356 | 1713 | 1,829
TOTAL |  | 3,898 |  | 

## Slide 10
SPONSOR Datuk Ir Elias Ismail
OWNER Ahmad Farrin Mokhtar
OIC Mohd Idrus Din
KPI LEADER MIDA
KPI DESCRIPTION At least two economic mechanisms to propel adoption of IBS introduced by 2017
INITIATIVE P3 - Accelerate adoption of IBS, mechanisation and modern practices advantage across project life-cycle
SUB-INITIATIVE P3c - Propel IBS supply chain via economic mechanisms
This KPI is under the purview of IWG10.
Economic Mechanism to Propel IBS Adoption
The first economic mechanism - tax holiday for qualified local IBS manufacturers was introduced in 2016.
There are two qualified manufacturers that have enjoyed the tax holiday incentive, one in 2016 and 2017 respectively.
The second economic mechanism –is with regards to heavy machinery and equipment import duty exemption. CIDB’s application was submitted to MOF on 14 April 2016. MOF requested for an impact study to be conducted to analyse the implementation to include productivity issues, machineries issues and revenue losses to the Government. The draft of the impact study was submitted to KKR on 9 August 2017. The findings of the study are as follows :
Loss to government income is not significant
Advanced countries no longer impose tax on machineries
Increase in capital expenditure on machineries will lead to productivity increase
On 5 December 2017, KKR requested for 3 issues to be addressed :
Focus on 5 machines i.e tower crane, gantry crane, crawler crane, overhead crane and mobile crane
Assurance that the incentives benefit the contractors not machineries rental companies
The necessity for tax exemption of the machineries since tax exemptions have been covered under FTA
Revised study on exemption of tax for heavy machineries and equipment related to IBS has been completed and submitted to KKR on 12 Mac 2018.
KKR is currently reviewing the Paper to MoF on the approval for exemption of tax for machineries and equipment related to IBS.
Q3 2018
KKR is still reviewing the Paper to MoF on the approval for exemption of tax for machineries and equipment related to IBS.
PRODUCTIVITY
KPI P3-068
PROGRESS REPORT UNTIL Q3 2018
ANNUAL TARGET
2016 Weightage : 40% | 2017 Weightage : 30% | 2018 | 2019 | 2020
 |  | Weightage : 30% |  | 
Tax Holiday incentive for new IBS manufacturing plants approved and implemented. Cost Benefit Analysis (CBA) for IBS developed Report on IBS Tax Holiday incentive recipients published. | Second Incentive on economic mechanism to propel IBS adoption proposed and submitted to MOF. Report on CBA for IBS & incentive recipients published |  |  | 
Note 2018-2020
Target to be determined after proposal on second incentive approved